## Slide 1
Introduction to Personal Process
Module 2: Team Software Process

## Slide 3: Module Objectives
At the end of this module, you will
  understand why the Team Software Process (TSP) was developed
  be familiar with key TSP concepts

## Slide 4: Module Overview
Building effective teams
The PSP/TSP foundation
TSP overview

## Slide 5: Working in Teams
Successful teams are both satisfying and rare.
Although many teams come close to meeting their product and business goals, they often do so at the expense of the team members.
We describe a team that works together smoothly and efficiently as being a “jelled team.”
“A jelled team is…greater than the sum of its parts… and the enjoyment people derive from the work is greater than you would expect.”
- Peopleware, DeMarco and Lister

## Slide 6: Building Jelled Teams
Artificially-jelled teams can be built quickly through “team-building” exercises.
  retreats, seminars, workshops
  games (paintball, laser tag, etc.)
  contrived challenges (e.g., blind obstacle courses)
Team-building activities are unlikely to produce long-term team success unless they address real workplace issues.
  common understanding of roles, goals, products
  management support of team needs
The TSP is a proven-effective way of building jelled teams quickly.

## Slide 7: Accelerating Team-building
The TSP was developed to address the need for
  software engineering teams who can build quality products within cost and schedule constraints
  building teams quickly and reliably
  optimizing team performance throughout a project
  accelerating software process improvement
  making use of mature processes normal and expected
If you are familiar with the SEI Capability Maturity Model or the Capability Maturity Model Integration, think of TSP as a CMM/CMMI maturity level 5 process for teams.

## Slide 8: The Need for Personal Discipline
Building successful high-performance teams requires more than technical ability; team members must be committed to the concept of personal discipline.
Personal discipline means that all team members understand their own abilities and can make realistic commitments to each other and to management.
Team members develop personal discipline by learning the principles of the Personal Software Process (PSP).

## Slide 9: The Personal Software Process
PSP-trained engineers learn process discipline by using
  defined methods to do their work
  data to plan and manage their work
The essential elements learned in PSP are
  performance measures
  estimating and planning skills
  quality management skills
Modules 3 through 9 of this course will provide you with a sufficient overview of PSP principles to enable you to work on a TSP team.

## Slide 10: The TSP Strategy Rests on PSP
The TSP strategy improves performance from the bottom-up.
Team
Member
Skills
Team
Building
Team
Management
Process discipline
Performance measures
Estimating & planning skills
Quality management skills
Goal setting
Role assignment
Tailored team process
Detailed balanced plans
Team communication
Team coordination
Project tracking
Risk analysis
Personal Software Process
Team Software Process

## Slide 11: Building Teams with TSP
TSP facilitates team-building
through a defined team launch
process.
The launch process kicks off
each major project phase.
  The team establishes a common understanding of the work and the development approach.
  A plan is produced to guide the next development phase.
  Subsequent phases kick off with a relaunch process.
Launch
Development Phase A
Postmortem
Development
Phase B
Relaunch
Postmortem

## Slide 12: TSP Process Structure and Flow -1
TSP has four principal
development phases.
  requirements
  high-level design
  implementation
  test
TSP projects can start or
end on any phase.
  from requirements through system test
  requirements only
  high-level design only
  any combination
Relaunch
Postmortem
Integration
and test
Relaunch
Implementation
Postmortem
Relaunch
High-level
design
Postmortem
Launch
Requirements
Postmortem

## Slide 13: TSP Process Structure and Flow -2
The TSP phases can and
should overlap.
The TSP development
strategy encourages
  incremental development
  iterative development
  multiple builds or cycles
  work-ahead
TSP permits whatever
process structure makes
the most business
and technical sense.
Relaunch
Postmortem
Integration
and test
Relaunch
Implementation
Postmortem
Relaunch
High-level
design
Postmortem
Launch
Requirements
Postmortem

## Slide 14: When to Launch
A launch or relaunch occurs
  at the beginning of every project phase
  when substantive changes to the plan are required
A launch may also be needed when new members are added to the team.
  familiarize them with the team processes
  integrate them into the team’s plans
  get their agreement with the goals
Notes: <number>

## Slide 15: Purpose of the TSP Launch
The purpose of the launch is to establish a common team understanding of the following project elements.
  management’s goals for the project
  team and team members’ goals
  the roles that the team members will perform
  the development work to be done
  the processes that the team will use
  the plan for doing the work
  the management and customer reporting system
  the ongoing team communication process
Notes: <number>

## Slide 16: The TSP Launch Workshop
The TSP launch is a four-day workshop used to kick off each project phase.
During the launch workshop, the team produces a comprehensive plan for their work.
The team leader and all team members participate.
The launch workshop is considered to be part of the project work (it is planned and tracked).
Notes: <number>

## Slide 17: The Launch Process Meetings
Day 1
1. Establish
product and
business
goals
2. Assign roles
and define
team goals
Day 2
4. Build top-
down and
next-phase
plans
5. Develop
the quality
plan
6. Build bottom-
up and
consolidated
plans
Day 3
7. Conduct
risk
assessment
8. Prepare
management
briefing and
launch report
Launch
postmortem
Day 4
9. Hold
management
review
New teams:
TSP process
review
3. Produce
development
strategy

## Slide 18: Launch Meeting 1
The launch begins with a meeting between the entire team and representatives from management (executives and/or marketing specialists).
The management representatives explain the
  need for the product
  business goals fulfilled by the product
  available resources for producing the product
  desired functionality of the product
  schedule and budget constraints
The team has a chance to ask questions and get clarification of any issues that concern them.

## Slide 19: Launch Meeting 2
The team discusses the management goals outlined in meeting 1 and uses these as a basis for defining their own goals for this project that mesh to the
  stated management goals
  implied goals derived from stated goals
The team members also choose roles, as discussed on the following slides.
Notes: <number>

## Slide 20: Team Member Roles -1
Team self-management responsibilities are shared among team members through eight defined team member roles.
  Customer Interface Manager
  Design Manager
  Implementation Manager
  Planning Manager
  Process Manager
  Quality Manager
  Support Manager
  Test Manager
The team leader acts as team coach.
Notes: <number>

## Slide 21: Team Member Roles -2
Team member roles are not time consuming.
Each team member should have a team member role in addition to their normal responsibilities.
All team roles should
  get team input on their decisions
  perform their role duties promptly and professionally
  train another team member as an alternate
All team members should
  follow disciplined personal practices
  plan, track, and manage their personal work
  support and contribute to the team
Notes: <number>

## Slide 22: The Team Leader’s Role
The team leader does not take one of the eight team roles.
The team leader’s job is to
  coach the team
  provide management support
  guide the team in doing their work
  establish and maintain high standards for the work
  make the team accountable for problem solving
  support the team-directed management concept
Notes: <number>

## Slide 23: Launch Meetings 3 and 4
The team produces a conceptual design of the product. The conceptual design is outlined only in sufficient detail for planning the work. It is not meant to be the final blueprint for the product.
The team chooses the processes that they will use for planning, measuring, and tracking their work.
Based on the conceptual design, the team decides on what work will be done during the entire project (top-down plan) and then during the next few months (next-phase plan).

## Slide 24: Launch Meeting 5
In the TSP, each team member and the team are responsible for the quality of the work and the entire team agrees on the quality goals for the product.
The team also agrees on methods for certifying high quality at individual and team levels.
Individuals certify that their products are of high quality.
  use PSP quality methods and evaluate with PSP data
  conduct personal and peer reviews
  call for team assistance as needed
The team certifies that each component is of high quality.
  inspections or walk-throughs
  reinspection as needed
  integration/system test acceptance

## Slide 25: Launch Meeting 6
The team plans the next-phase work in detail. They use the conceptual design to generate a list of tasks to produced the desired outcomes for the next phase.
Tasks are allocated to the individual team members.
Each team member makes an individual plan based on his/her task list, schedule availability, and productivity estimates.
The individual plans are consolidated into a team plan. If necessary, tasks are reallocated to ensure that the work load is balanced among the team members.

## Slide 26: Launch Meeting 7
The team identifies any risks that are likely to affect their plan. Each risk is rated as high, medium, low as to impact on the project and likelihood of occurrence.
Mitigation strategies are generated for any risk with a “high” rating.
Risks are allocated for tracking among the team members.

## Slide 27: Launch Meeting 8
The team prepares a presentation to give management an overview of their plan.
The presentation includes
  team goals and roles
  quality goals
  milestone dates for completion of major components and the project as a whole
If the team was not able to meet management’s requested schedule, they present alternative proposals.
  additional resources needed
  iterative development plans

## Slide 28: Launch Meeting 9
The team presents its plan to management.
Management asks questions about the plan (and any alternative proposals).
At the end of meeting 9, the team and management should reach agreement on one of the plans presented.

## Slide 29: Launch Postmortem
The coach and team members meet to discuss how things went during the launch.
  what worked well
  what did not work well
  suggestions for improving the launch process in future launches

## Slide 30: After the Launch
TSP projects are team-directed. Being a team-directed project means that the team manages itself.
  tracks their work against their plan
  manages the quality of their work
  works aggressively to meet team goals
The team must also show management and the customer that they are managing themselves.
  frequently report status and progress
  anticipate, plan for, and report on project risks
The weekly team meeting is the mechanism for
  reporting their status to each other
  collecting information for management and customer reports

## Slide 31: The Weekly Team Meeting
The weekly team meeting keeps the project on track by reviewing status and planned work for the team and each team member on a weekly basis.
The meeting objective is to ensure that all team members
  understand current project status
  know what tasks are next
  are aware of everyone’s status and progress
  know the status against the quality plan
  discuss actions needed to ensure high quality
  understand the key project issues and risks
  participate in key team decisions
Notes: <number>

## Slide 32: TSP Project Tracking -1
Each team member is responsible for
  gathering data on their work
  ensuring the quality of the work that they produce
  tracking status against their personal plan
  keeping the team informed on their personal status
Project tracking in the TSP is based on the principles and measures used in the PSP.

## Slide 33: TSP Project Tracking -2
Quality
summary
Schedule
status
Engineer A
Product
summary
Enter defects
by component
and phase
Enter
size by
component
Enter
week of task
completion
Enter
time by
task
Updated team and
engineer task, schedule,
and quality plans
Team task
and schedule
summary
Task status
Engineer A

## Slide 34: TSP Project Plan Elements
The detailed team and individual plans facilitate precise project tracking.
  product size (in pages or lines of code)
  time (in minutes per phase or task)
  defects injected and removed (by phase)
  schedule planning/tracking with earned value
These PSP elements will be explained in detail in the remainder of the course.

## Slide 35: Messages to Remember
The TSP was developed to help software teams to build high quality products, on time, on schedule, every time.
TSP fosters teamwork through its
  launch process
  detailed plans
  defined roles
  team-directed management approach
  weekly status tracking
The foundation of TSP is the commitment of individual team members to using the PSP methods and principles in which they were trained.
Notes: <number>