## Slide 1
Introduction to Personal Process
Module 4: Planning I - Measures
Notes: <number>

## Slide 3: Module Objectives
At the end of this module, you will
  understand the PSP planning framework
  understand the value of measures
  define a size measure for something that you do at work
Notes: <number>

## Slide 4: Module Overview
Plans
Size and effort measurements
Selecting a size measure
Notes: <number>

## Slide 5: Planning: Step 1 in Your Process
Businesses operate on commitments. They contract to provide a product or service at
  an agreed-upon price
  an agreed-upon date
To be successful, businesses must make commitments that they can meet at a profit.
To make commitments that they can meet at a profit, businesses must develop plans that accurately represent what they can do.
Notes: <number>

## Slide 6: Planning: Why it Should be Step 1
Commitments are important within an organization.
Your management and your teammates ask you to make commitments.
  what you will do
  what resources you will need
  when you will complete your work
To make commitments that you can meet, you need a plan that accurately represents what you can do.
Notes: <number>

## Slide 7: Additional Benefits of a Plan
A good plan helps you to be more efficient. It
  guides you as you do your work
  keeps you from doing things in the wrong order
  keeps you focused on the work
A good plan helps you to track your status. You can
  determine if you are on schedule, ahead of schedule, or behind schedule
  determine if you can still meet your commitments
  keep your manager and teammates informed of your status
Notes: <number>

## Slide 8: What a Plan Should Contain
Job description
Job sizing
  How big is it?
  What resources are needed?
Job structure
  How you are going to do the work?
  What you will do first, second, and so on?
Job schedule
  How many hours will it require?
  When are you able to work on it?
  When will you finish?

## Slide 9: The PSP Project Planning Framework
Define
requirements
Produce
conceptual
design
Estimate
size
Estimate
resources
Produce
schedule
Develop
product
Size, resource,
schedule
data
Process
analysis
Resources
available
Productivity
database
Size
database
Customer
need
Product
delivery
Tracking
reports
Customer
Management
Items
Tasks

## Slide 10: Size Measurement
The planning process starts with an estimate of the job size.
By estimating the size of the product that you plan to build, you can better judge the amount of work needed to build it.
Before you can estimate the product size, you need a consistent and repeatable way to describe the product’s size.
In other words, you need to select an appropriate size measure.

## Slide 11: Size Measurement Criteria
The criteria for a size measure are that it must be
  useful for planning
  precise
  directly countable/measurable
The next slides will discuss these points.

## Slide 12: Useful for Planning
A primary goal in planning is to estimate the effort for a job.
For a size measure to be useful during planning, it must help you to estimate the effort for the job.
To help you estimate the effort for the job, there must be a relationship between the size measure and the effort for the job.
If a relationship exists between a size measure and effort, then the size measure can be used for planning.
The next slide illustrates such a relationship for writing pages of text for a book.

## Slide 13: Example: Text Pages versus Effort

## Slide 14: Precision
The principal concern with precision for a size measure is the degree to which the measure is completely defined.
When two people measure the same thing, will they get the same result?
This requires a precise size measurement definition.

## Slide 15: Directly Countable
The size measure must be directly countable or measurable in the product.
Examples of directly countable measures are
  pages
  paragraphs
  diagrams
  graphs
Examples of something that is not directly countable in a document are themes or topics.

## Slide 16: Effort Measure
While the size measure depends on the job, the effort measure is always time.
The concerns with measuring time are these.
  What is included in the time measure?
  What precision is used to measure time?
The next slides will discuss these points.

## Slide 17: What is Included in the Time Measure?
Since you are looking for a relationship between size and effort, only the time spent actually working on a task (“time on task”) should be included.
Interruptions such as phone calls, rest breaks, and office conversations
  are highly variable
  are not related to the job
  must be excluded from task time in order to determine the size versus time relationship
Most engineers find that they spend less than 50% of their time on task.

## Slide 18: Time Measurement Precision
Effort on projects is often measured in person months.
While this is useful for financial accounting systems, it is not useful for tracking, analyzing, or improving personal processes.
People rarely work on one thing for more than an hour or two.
In PSP, effort is measured in minutes.
  This measure is precise enough.
  Once you decide to precisely measure time, the units do not make much difference.

## Slide 19: Selecting a Size Measure -1
Start with some historical data from past projects.
  development effort
  product characteristics (candidate size measures)
  special conditions
Rank the products by development effort.
See what characteristics distinguish those products that took the greatest effort from those that took the least.

## Slide 20: Selecting a Size Measure -2
Determine if the candidate size measure is related to effort.
  Create a graph with the candidate size measure on the horizontal axis and effort on the vertical axis.
  Plot each pair of historical data (candidate size measure, effort) as a point on the graph.
  If the points define a line, then the candidate size measure is related to effort and can be used for planning.
There may be no single best size measure. A combination of size measures could be needed.

## Slide 21: Ex: Text Pages versus Writing Time

## Slide 22: Ex: LOC versus Development Time

## Slide 23: Estimating Effort Directly
If you cannot find a good size measure, you may have to estimate development time directly.
  Collect a lot of historical data.
  Compare the new work with past work.
  Judge the likely development time.

## Slide 24: Messages to Remember
The primary purpose of planning is to help you to make commitments that you can meet.
In the PSP planning framework, effort estimates are based on estimates of the product’s size and your historical productivity.
The primary criteria for a size measurement is that it is directly related to effort, i.e., it is useful for planning.

## Slide 25: Size Measure Selection Exercise
In this exercise, you will
  learn how to test the correlation of potential size measures
  select a size measure a process that you use at work
There are two parts to this exercise.

## Slide 26: Part 1
You are given size and effort data on two candidate size measures.
Use graphs to test the data for a relationship.
Identify the best size measure.
10 minutes

## Slide 27: Part 2
List at least three potential size measures a process that you use at work.
Evaluate the potential size measures using the following criteria.
  useful for planning (directly related to effort)
  precisely defined
  directly measurable
10 minutes

## Slide 28: Exercise Feedback: Part 1
Which measure - chapters or pages - best correlates with effort?
Which measure would be best to use for planning a new book?

## Slide 29: Exercise Feedback: Part 2
Example measures may be
  pages
  paragraphs
  requirements
  diagrams
  objects