## Slide 1
Introduction to Personal Process
Module 5: Planning II - Estimating

## Slide 3: PSP Project Planning Framework
Define
requirements
Produce
conceptual
design
Estimate
size
Estimate
resources
Produce
schedule
Develop
product
Size, resource,
schedule
data
Process
analysis
Resources
available
Productivity
database
Size
database
Customer
need
Product
delivery
Tracking
reports
Customer
Management
Items
Tasks

## Slide 4: Module Objectives
At the end of this module, you will
  understand estimating principles
  understand how to estimate size and effort using the PSP planning framework

## Slide 5: Module Overview
Estimating principles
Estimating size
Estimating effort
Notes: <number>

## Slide 6: Estimating Exercise -1
Exercise instructions
  Estimate the number of M&M’s in container A.
  Write your estimate here. ________
The actual number of M&M’s in container A is _____.
1 minute
Notes: <number>

## Slide 7: Estimating Exercise -2
Now
  Estimate the number of M&M’s in container B.
  Write your estimate here _______.
The actual number of M&M’s in container B is _____.
1 minute
Notes: <number>

## Slide 8: Exercise Feedback
A little data can significantly improve your estimates.
With historical data on things that you’ve done before, you can quickly make reasonable estimates.
What is your experience with making estimates?
Notes: <number>

## Slide 9: Estimating Principles -1
Estimating is an uncertain process.
  No one knows what the final size or effort will be.
  The more data you have, the better your estimates are likely to be.
  The earlier the estimate is made, the less is known.
  Management or other pressures can bias an estimate.
Estimating is a skill that must be learned, practiced, and maintained.
  Ability improves with experience and data.
  Some people will be better at estimating than others.

## Slide 10: Estimating Principles -2
Estimating accuracy improves when you
  break a product down into parts
  estimate each part separately
  achieve a balance between over- and under-estimating on the parts
The reason that the estimates become accurate is that with a balance of over- and under-estimates, the errors tend to cancel each other out.

## Slide 11: Ex: Estimating in Detail -1
Suppose that you need to estimate the size of a design document.
Your historical data shows that
  actual sizes have been within ± 50% of your estimates
  you tend to have a balance between under- and over- estimates
First, you estimate the design document as a whole at 50 pages. Based on your estimating experience, the actual size should be somewhere between 25 and 75 pages.

## Slide 12: Ex: Estimating in Detail -2
Next, you decide to estimate the design document in parts.
You break the document into 4 parts and estimate each part separately.
  part 1 20 pages
  part 2 8 pages
  part 3 14 pages
  part 4 20 pages
This size estimate totals 62 pages.
What is the accuracy? That is, within what range around 62 do you expect the actual size to be?

## Slide 13: Ex: Estimating in Detail -3
Since your past estimating experience shows that you tend to have a balance between over- and under-estimates, you would expect that a couple of the parts are over-estimated and a couple may be under-estimated.
In that case, the errors will tend to cancel each other, and the error for the total estimate will be less than the sum of the individual errors.
Using some simple mathematics, you can calculate the range around your estimate within which the actual value should fall, based on your past estimating experience.

## Slide 14: Ex: Estimating in Detail -4
Apply your past experience of having the actual size be within ± 50% of your estimates to the estimates for the parts.
  part 1 20 pages ±10 pages
  part 2 8 pages ± 4 pages
  part 3 14 pages ± 7 pages
  part 4 20 pages ±10 pages
While the total size estimate is the sum of the individual estimates, the error range for the total is not the sum of the individual ranges.

## Slide 15: Ex: Estimating in Detail -5
The error range for the total estimate is the square root of the sum of the squares of the individual ranges.

## Slide 16: Accuracy of the Estimates

## Slide 17: Estimating Goals
The objective of estimating is to become consistent.
  understand the variability of your estimates
  achieve a balance between under- and over-estimates
To become consistent at estimating, you must
  use a defined process
  collect and use historical data
  practice

## Slide 18: An Estimating Problem -1
Suppose that you wanted to estimate how long it would take to write a report.
You have data on a couple of reports you have written recently.
  total pages
  total time
  number of chapters
  number of pages per chapter
How could you proceed in making your estimate?

## Slide 19: An Estimating Problem -2
If you had an estimate for the number of pages in the report, you could estimate the development time by using your average productivity from the earlier reports.
How can you estimate the number of pages from the report requirement?

## Slide 20: Estimating Size Directly
One way to estimate the report size would be to estimate the whole report at once.
You could
  compare the requirements for this report to previous reports
  use your historical data to guide your estimate
Recall our earlier discussion of estimate accuracy.
What accuracy are you likely to achieve?

## Slide 21: Estimating Size with Parts
Another approach would be to break the report into parts and estimate the size of the parts.
You could
  create a chapter outline
  estimate the size of each chapter
  add up the estimates for the chapters
How is the accuracy for this estimate likely to compare with the first approach?

## Slide 22: Choosing the Estimating Method
If the report is just a chapter or two, directly estimating size would probably suffice.
If the report is more than a chapter or two, breaking the report into chapters and estimating the size of each chapter would result in a more accurate estimate.
The next slides illustrate how to estimate with parts.

## Slide 23: Size Estimating Method -1
Consider the following situation. You and your spouse decide to build your dream house.
You go to a contractor to get some idea of what it will cost. The contractor tells you that they estimate cost based on the size of the house measured in square feet.
You and your spouse don’t visualize your dream house in terms of square feet, but in terms of the rooms you want.
The contractor has some data on room sizes and suggests that you use the data to estimate the size of your dream house.

## Slide 24: Contractor’s Room Size Data

## Slide 25: Size Estimating Method -2
You and your spouse list the rooms for your dream house.
For each room, you identify the type of room (e.g., bedroom) and its relative size.
Next, you go to the contractor’s room size data and find the size in square feet for each room.
Finally, you add up the estimated sizes for all of the rooms in your dream house to come up with an overall size estimate for your dream house.

## Slide 26: Dream House Size Estimate
Room Rm type Rel size Est sq ft
Master BR Bed L 350
Child BR Bed M 200
Child BR Bed M 200
Guest BR Bed S 100
Master bath Bath L 210
Children’s bath Bath M 120
Guest bath Bath M 120
Kitchen Kitchen L 265
Living Living M 300
Family Living L 400
Dining Dining M 195
Computer Den M 200
Powder Bath S 50
Total 2710

## Slide 27: PSP Estimating Technique
The steps for estimating product size are these.
  Create a conceptual design that breaks the product into parts.
  Judge the relative size of the parts.
  Use historical data to convert the relative sizes into estimates for the parts.
  Add the estimates for the parts.
The next slides elaborate on this approach.

## Slide 28: Conceptual Design
Create a conceptual design for the product.
  This is a preliminary design approach that breaks the product down into an expected set of parts, e.g., chapters for a report.
  It is produced mainly to make the size estimate; you may change it when you get into the design phase.
  For things that you understand, the conceptual design can be done quickly.
Examples
  document: chapter outline
  product: major parts/components needed for build

## Slide 29: Sizing the Parts
Judge the relative size of each part.
  Use your judgement to pick a relative size: small, medium, or large.
  The size estimate for the part is taken from the relative size table.
The relative size table is created from historical data.

## Slide 30: Creating a Relative Size Table -1
The relative size table is constructed using historical data on the size of parts that you have built in the past.
Identify the
  largest size (maximum)
  smallest size (minimum)
Compute the average size.

## Slide 31: Creating a Relative Size Table -2
The maximum, minimum, and average sizes are used to calculate size entries for the relative size table.

## Slide 32: Example: Relative Size Table
Use the following size data for 20 parts.
average = 22.25
(maximum - average)/2 = 8.875
(average - minimum)/2 = 5.125
Medium part = 22.25
Large part = 22.25 + 8.875 = 31.125
Small part = 22.25 - 5.125 = 17.125

## Slide 33: Additional Comments
If your parts must be separated into distinct size groupings
(such as rooms of a house, where baths have a much different size range than bedrooms), you may need to
  identify the separate types
  create entries in your size table for each type

## Slide 34: Estimating Time
Use your historical productivity rate to estimate time.
where

## Slide 35: Multiple Size Measures
When each process step has a unique size measure that relates to effort
  estimate the size for each step
  estimate the effort for each step
  combine the effort estimates

## Slide 36: Estimating Without Historical Data
If you don’t have historical data, you can still use these methods, but you’ll have to use guesses in place of the historical data.
Since even a little bit of data can improve your estimates, see if you can get some baseline data from someone else.
For the size table, make your best guess on the sizes of small, medium, and large parts.
Make your best guess on productivity.

## Slide 37: Messages to Remember
For all but very small products, size estimates should be done by breaking the product down into parts and then estimating the size of the parts using historical data.
Effort estimates are based on
  size estimates
  historical rates for productivity

## Slide 38: Estimating Exercise -1
You will now apply the PSP size and effort estimating methods to calculate a relative size table for writing a book.
You are given some historical data on size and time from using a scripted book-writing process.
In this exercise, you will
  calculate values for the relative size table
  calculate an overall rate to be used in estimating time

## Slide 39: Estimating Exercise -2
The instructions in the workbook will guide you through the process.
At the end of the exercise, the instructor will review the results with you.
20 minutes

## Slide 40: Exercise Feedback