## Slide 1
Introduction to Personal Process
Module 6: Planning III - Scheduling

## Slide 3: PSP Project Planning Framework
Define
requirements
Produce
conceptual
design
Estimate
size
Estimate
resources
Produce
schedule
Develop
product
Size, resource,
schedule
data
Process
analysis
Resources
available
Productivity
database
Size
database
Customer
need
Product
delivery
Tracking
reports
Customer
Management
Items
Tasks

## Slide 4: Module Objectives
At the end of this module, you will know how to
  build a schedule
  create an earned value plan
  track your progress using earned value

## Slide 5: Module Overview
Scheduling
Project tracking
Notes: <number>

## Slide 6: Why Schedule Plans are Needed -1
Management wants to know when you will complete your project.
Once you have an estimate of how much effort the project will require, you still need a projection for when the project will be completed.
To determine when you are likely to finish, you need to build a schedule which maps
  the estimated effort to your hours available for work on project tasks
  your available task hours to your master weekly calendar

## Slide 7: Why Schedule Plans are Needed -2
Schedule plans
  define your commitment
  allow others in your work group to coordinate their work with yours
  allow you to track your progress and report your status
In short, the schedule plan establishes a framework for managing your work.

## Slide 8: Creating a Schedule
To make a schedule, you need three things.
  the estimated hours per task
  the order in which the tasks will be done
  a calendar of your available task hours
Scheduling consists of spreading your available work hours across the tasks.
Starting with the first task and continuing for all of the tasks, calculate when the task
  can be started
  will be completed

## Slide 9: Task Order
An initial task order provides a basis for planning.
The initial task order should consider your development strategy.
  conceptual approach
  task completion criteria
  task interdependencies
  cost and cycle time priorities
The task order is likely to change as new information becomes available.

## Slide 10: Available Task Hours -1
Even with good effort estimates, your schedules can be seriously in error if you make incorrect assumptions about how much time you can spend working on project tasks.
Time spent on e-mail, telephone calls, meetings, rest breaks, and the like are not counted as task hours.
Typically, engineers find that 50% or less of their time at work is actually spent on project tasks.

## Slide 11: Available Task Hours -2
Unless you have data to suggest otherwise, your initial plans should use 50% of your work hours as the basis for estimating your available task hours.
Once you have gathered some data on the actual number of task hours that you achieve per day or week, you can use this data to adjust your schedule plans.

## Slide 12: A Scheduling Example -1
Jose is a member of a software project team. His commitments are
  develop a project module
  do some team planning
  review activities for other deliverables
  prepare and make a project presentation
The project must be completed in 12 days, and Jose has 4 hours per day available to work on the project.
How should he proceed?

## Slide 13: A Scheduling Example -2
Using historical data from other projects and his own PSP database, Jose
  determines the task order
  lists the tasks in order of completion on a task template
  estimates how much time each will take

## Slide 14: A Scheduling Example -3
Next, Jose generates a running total of planned time and records these figures in the Cumulative Hours column.

## Slide 15: A Scheduling Example -4
The next step is for Jose to determine how much time he will have available during the next 12 days.
Jose estimates that he can devote 4 hours each day to working on this project.
With 4 hours per day for 12 days, there are 48 hours available for project work. Since the total estimate for all tasks is 43 hours, this should be enough time to complete the project.

## Slide 16: A Scheduling Example -5
In a schedule planning template, Jose enters
  the day number and date
  task hours he plans to work each day
  a running total of the cumulative hours at the end of each day

## Slide 17: A Scheduling Example -6
Jose determines the day on which each task will finish by
  matching the cumulative task hours on the task planning template required to complete a task with the first date on the schedule planning template where the cumulative hours equals or exceeds that number
  placing the task completion date in the Plan Date column of the task planning template
Now Jose has a schedule!

## Slide 18: Jose’s Schedule

## Slide 19: Project Tracking Principles
To track a project, you need
  a plan that divides the work into a detailed set of tasks
  a way to assign a value to the amount of work required for each task
  data on tasks completed
Then, you
  determine the rate at which you are completing work
  use that rate and the remaining amount of work to estimate the project completion date

## Slide 20: A Detailed Plan
You want to plan at a level of detail that enables you to complete two to four tasks per week.
  With less than two checkpoints per week, your status and progress will be harder to determine.
  With more than four checkpoints per week, you may find that you are investing more time in tracking than is needed.
These task completions provide
  checkpoints for assessing status against your plan
  a sense of accomplishment with each task that you complete

## Slide 21: Earned Value
Earned value tracking is a way to evaluate project progress.
It establishes a relative value for every task.

## Slide 22: Assigning a Value to Each Task
The earned value for a task is the percent of the total project hours that a task is planned to take.
Example: Jose estimated that it would take 2 hours to develop his plan. The estimated time for the total project is 43 hours. Therefore, the earned value for this planning task is (2/43)*100, or 4.65.
The total earned value for project is 100.
Earned value establishes a common value for each task, regardless of the type of work, which facilitates progress tracking.

## Slide 23: Earned Value Plan
An earned value plan is a table (or a chart) that shows your planned earned value by day (or week).
It is constructed by calculating for each day (or week) on the schedule the total earned value of all tasks that are planned to be completed by that date.

## Slide 24: Jose’s Earned Value Plan -1
Jose uses the TSP support tool to generate an earned value plan.

## Slide 25: Jose’s Earned Value Plan -2
Do you see any problems with Jose’s earned value plan?

## Slide 26: Jose’s Problem
The problem with Jose’s plan is that he has an eight-day stretch (six working days), from 9/14 until 9/22, between planned task completions. His status (or progress) during that time can not be determined from this plan.
Jose needs to break the module development task down into the next level of granularity.
Jose breaks the module development task into seven smaller tasks and recalculates his task and earned value plans.

## Slide 27: Jose’s Revised Earned Value Plan -1

## Slide 28: Jose’s Revised Earned Value Plan -2

## Slide 29: Tracking Using Earned Value -1
When a task is completed, it earns the planned earned value (regardless of how many hours it actually took).
Partially completed tasks receive no earned value.
Status is determined by comparing your total value earned on completed tasks with your earned value plan.

## Slide 30: Tracking Using Earned Value -2
The order in which you do the tasks does not affect your ability to determine your status or to measure your progress.
Project completion can be estimated by dividing the earned value needed to complete the project by the rate at which value has been earned to date.

## Slide 31: Tracking Jose’s Earned Value -1
Jose enters the planned values in the schedule planning template and begins tracking his earned value.

## Slide 32: Estimating Jose’s Completion Date
At the end of three days, Jose’s earned value is 16.28.
His rate of earning value is 5.43 per day.
He has to earn 83.72 more to complete this project.
If he continues to earn value at the rate of 5.43 per day, it will take him 15.42 more days to finish.
We estimate that it will take Jose 19 days to finish, instead of the original estimate of 11 days.

## Slide 33: Tracking Jose’s Earned Value -2

## Slide 34: Messages to Remember
An earned value plan should
  be based on historical data
  contain two to four task completions per week
Earned value tracking
  provides an accurate picture of project status
  is not affected by the order in which the tasks are done
  provides a forecast of when the project will be finished

## Slide 35: Scheduling Exercise -1
In this exercise, you will create an earned value plan.
There are five major tasks (six steps) in this exercise.
  Use the book writing process script to create a task list on the task template for this job (step 1).
  Fill in the effort estimates for these tasks using the estimated time in phase data from the plan summary form (step 2) .
  Fill in the schedule template with the hours per week, as provided in step 3 of the exercise instructions.
  Compute the planned earned value for these tasks (steps 4 and 5).
  Make a chart to display your earned value plan (step 6).

## Slide 36: Scheduling Exercise -2
When you are done, review your results with an instructor.
25 minutes

## Slide 37: Exercise Feedback
Did you have any problems with the exercise?