Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Answers for
Earned Value Plan Exercise

Managing TSP Teams

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

Task Planning Template

| Student | JD Veloper | Date | 8/1 |
| --- | --- | --- | --- |
| Instructor | Humphrey | Program # | 9A |

| Task |  | Plan |  |  |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Name | Hours | Planned Value | Cumulative Hours | Cumulative Planned Value | Date Monday | Date | Earned Value | Cumulative Earned Value |
| 1 | Planning | 49 | 15.7 | 49 | 15.7 | 1 |  |  |  |
| 2 | Design | 87 | 27.8 | 136 | 43.5 | 3 |  |  |  |
| 3 | Design Review | 16 | 5.1 | 152 | 48.6 | 3 |  |  |  |
| 4 | Code | 64 | 20.4 | 216 | 69.0 | 4 |  |  |  |
| 5 | Code Review | 20 | 6.4 | 236 | 75.4 | 4 |  |  |  |
| 6 | Compile | 15 | 4.8 | 251 | 80.2 | 5 |  |  |  |
| 7 | Test | 33 | 10.5 | 284 | 90.7 | 5 |  |  |  |
| 8 | Postmortem | 29 | 9.3 | 313 | 100.0 | 6 |  |  |  |
| Totals |  | 313 |  |  |  |  |  |  |  |

Schedule Planning Template

| Student | JD Veloper | Date | 8/1 |
| --- | --- | --- | --- |
| Instructor | Humphrey | Program # | 9A |

|  |  | Plan |  |  | Actual |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Day | Date | Direct | Cumulative | Cumulative | Direct | Cumulative | Cumulative | Adjusted |
| No. | Monday | Hours | Hours | Planned Value | Hours | Hours | Earned Value | Earned Value |
| 1 |  | 60 | 60 | 15.7 |  |  |  |  |
| 2 |  | 60 | 120 | 15.7 |  |  |  |  |
| 3 |  | 60 | 180 | 48.6 |  |  |  |  |
| 4 |  | 60 | 240 | 75.4 |  |  |  |  |
| 5 |  | 60 | 300 | 90.7 |  |  |  |  |
| 6 |  | 60 | 360 | 100.0 |  |  |  |  |
| 7 |  | 60 | 420 |  |  |  |  |  |
| 8 |  | 60 | 480 |  |  |  |  |  |
| 9 |  | 60 | 540 |  |  |  |  |  |
| 10 |  | 60 | 600 |  |  |  |  |  |