Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Workbook for
Coaching PSP-trained Developers Exercise
Part 1a

Managing TSP Teams

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

Managing TSP Teams

Coaching PSP-trained Developers Exercise

Overview

| #### Exercise Overview | The exercise includes the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Exercise Objectives | 2 |
|  | Exercise Instructions | 2 |
|  | Background Information | 3 |
|  | Otto’s Revised Project Plan Summary | 4 |
|  | Otto’s Revised Cycle Summary (Plan) | 6 |
|  | Otto’s Revised Size Estimating Template | 8 |
|  | Task and Schedule Planning Templates | 9 |

| Exercise Objectives | After completing this exercise, participants will - have a better understanding of the issues involved in using PSP at work - understand how to evaluate a PSP Plan, how to check progress against a plan, and how to evaluate a completed PSP project |
| --- | --- |

| #### Exercise #### Instructions | - Review the background information and Otto’s revised PSP plans. - Did Otto address all of the issues in the original plan? |
| --- | --- |

Background

| #### Background | Based on the suggestions that you provided at the last meeting, Otto revised his project plan summary, cycle summary, and size estimating template. Estimating that he can spend two direct hours per day on this project, Otto also put together task and schedule planning templates so that the project can be tracked using the earned value method. |
| --- | --- |

PSP3 Project Plan Summary

| Engineer | Otto | Date | 11/1 |
| --- | --- | --- | --- |
| Project | 2001/XQ35 |  | revised plan |
| Component | Compact Disc | Language | C |

| Summary | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LOC/Hour | 22.80 |  |  |  |  |  |  |  |  |  |  |
| Planned Time | 1445 |  |  |  |  |  |  |  |  |  |  |
| Actual Time |  |  |  |  |  |  |  |  |  |  |  |
| CPI(Cost-Performance Index) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | (Planned/Actual) |  |  |
| % Reused | .5 |  |  |  |  |  |  |  |  |  |  |
| % New Reused | 28.2 |  |  |  |  |  |  |  |  |  |  |
| Test Defects/KLOC | 15.8 |  |  |  |  |  |  |  |  |  |  |
| Total Defects/KLOC | 106 |  |  |  |  |  |  |  |  |  |  |
| Yield | 61% |  |  |  |  |  |  |  |  |  |  |
| % Appraisal COQ | 28 |  |  |  |  |  |  |  |  |  |  |
| % Failure COQ | 14 |  |  |  |  |  |  |  |  |  |  |
| COQ A/F Ratio | 2.0 |  |  |  |  |  |  |  |  |  |  |
| Program Size (LOC) | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| Base(B) | 7000 |  |  |  |  |  |  |  |  |  |  |
|  | (Measured) |  |  |  | (Measured) |  |  |  |  |  |  |
| Deleted (D) | 0 |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |
| Modified (M) | 25 |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |
| Added (A) | 524 |  |  |  |  |  |  |  |  |  |  |
|  | (N-M) |  |  |  | (T-B+D-R) |  |  |  |  |  |  |
| Reused (R) | 40 |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |
| Total New & Changed (N) | 549 |  |  |  |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (A+M) |  |  |  |  |  |  |
| Total LOC (T) | 7564 |  |  |  |  |  |  |  |  |  |  |
|  | (N+B-M-D+R) |  |  |  | (Measured) |  |  |  |  |  |  |
| Total New Reused | 155 |  |  |  |  |  |  |  |  |  |  |
| Upper Prediction Interval (70%) | 869 |  |  |  |  |  |  |  |  |  |  |
| Lower Prediction Interval (70%) | 229 |  |  |  |  |  |  |  |  |  |  |
| Time in Phase (min.) | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| Planning | 144 |  |  |  |  |  |  |  |  |  |  |
| High-level design | 116 |  |  |  |  |  |  |  |  |  |  |
| High-level design review | 58 |  |  |  |  |  |  |  |  |  |  |
| Detailed design | 173 |  |  |  |  |  |  |  |  |  |  |
| Detailed design review | 116 |  |  |  |  |  |  |  |  |  |  |
| Code | 332 |  |  |  |  |  |  |  |  |  |  |
| Code review | 231 |  |  |  |  |  |  |  |  |  |  |
| Compile | 58 |  |  |  |  |  |  |  |  |  |  |
| Test | 145 |  |  |  |  |  |  |  |  |  |  |
| Postmortem | 72 |  |  |  |  |  |  |  |  |  |  |
| Total | 1445 |  |  |  |  |  |  |  |  |  |  |
| Total Time UPI (70%) | 1900 |  |  |  |  |  |  |  |  |  |  |
| Total Time LPI (70%) | 990 |  |  |  |  |  |  |  |  |  |  |

PSP3 Project Plan Summary (continued)

| Engineer | Otto | Date | 11/1 |
| --- | --- | --- | --- |
| Project | 2001/XQ35 |  | revised plan |
| Component | Compact Disc | Language | C |

| Defects Injected | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning | 0 |  |  |  |  |  |  |  |  |  |  |
| High-level design | 6 |  |  |  |  |  |  |  |  |  |  |
| High-level design review | 0 |  |  |  |  |  |  |  |  |  |  |
| Detailed design | 8 |  |  |  |  |  |  |  |  |  |  |
| Detailed design review | 0 |  |  |  |  |  |  |  |  |  |  |
| Code | 44 |  |  |  |  |  |  |  |  |  |  |
| Code review | 0 |  |  |  |  |  |  |  |  |  |  |
| Compile | 0 |  |  |  |  |  |  |  |  |  |  |
| Test | 0 |  |  |  |  |  |  |  |  |  |  |
| Total Development | 58 |  |  |  |  |  |  |  |  |  |  |
| Defects Removed | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| Planning | 0 |  |  |  |  |  |  |  |  |  |  |
| High-level design | 0 |  |  |  |  |  |  |  |  |  |  |
| High-level design review | 4 |  |  |  |  |  |  |  |  |  |  |
| Detailed design | 0 |  |  |  |  |  |  |  |  |  |  |
| Detailed design review | 8 |  |  |  |  |  |  |  |  |  |  |
| Code | 0 |  |  |  |  |  |  |  |  |  |  |
| Code review | 23 |  |  |  |  |  |  |  |  |  |  |
| Compile | 14 |  |  |  |  |  |  |  |  |  |  |
| Test | 9 |  |  |  |  |  |  |  |  |  |  |
| Total Development | 58 |  |  |  |  |  |  |  |  |  |  |
| After Development |  |  |  |  |  |  |  |  |  |  |  |
| Defect Removal Efficiency | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| Defects/Hour - Design review | 4.2 |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour - Code review | 6.0 |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour - Compile | 14.5 |  |  |  |  |  |  |  |  |  |  |
| Defects/Hour - Test | 3.6 |  |  |  |  |  |  |  |  |  |  |
| DRL(DLDR/UT) | 1.2 |  |  |  |  |  |  |  |  |  |  |
| DRL(CodeReview/UT) | 1.7 |  |  |  |  |  |  |  |  |  |  |
| DRL(Compile/UT) | 4.0 |  |  |  |  |  |  |  |  |  |  |

Cycle Summary

| Engineer | Otto |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  | 11/1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project | 2001 XQ35 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | revised plan |  |  |  |  |  |
| Component | Compact Disc |  |  |  |  |  |  |  |  |  |  | Language |  |  |  |  | C |  |  |  |  |  |
| Cycle |  |  | 1 |  |  |  |  | 2 |  |  |  |  |  |  | Total |  |  |  |  |  |  |  |
|  |  |  | Plan |  |  | Actual |  | Plan |  |  | Actual |  |  |  | Plan |  |  |  |  | Actual |  |  |
| Program Size (LOC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Base(B) |  | 7000 |  |  |  |  |  |  | 7290 |  |  |  |  |  |  | 7000 |  |  |  |  |  |  |
| Deleted (D) |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Modified (M) |  | 0 |  |  |  |  |  |  | 25 |  |  |  |  |  |  | 25 |  |  |  |  |  |  |
| Added (A) |  | 250 |  |  |  |  |  |  | 274 |  |  |  |  |  |  | 524 |  |  |  |  |  |  |
| Reused (R) |  | 40 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 40 |  |  |  |  |  |  |
| Total New & Changed (N) |  | 250 |  |  |  |  |  |  | 299 |  |  |  |  |  |  | 549 |  |  |  |  |  |  |
| Total LOC (T) |  | 7290 |  |  |  |  |  |  | 7564 |  |  |  |  |  |  | 7564 |  |  |  |  |  |  |
| Total New Reused |  | 155 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 155 |  |  |  |  |  |  |
| Time in Phase (min.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 116 |  |  |  |  |  |  |  |  |  |  |  |  |  | 116 |  |  |  |  |  |  |
| HLD Review |  | 58 |  |  |  |  |  |  |  |  |  |  |  |  |  | 58 |  |  |  |  |  |  |
| Design |  | 79 |  |  |  |  |  |  | 94 |  |  |  |  |  |  | 173 |  |  |  |  |  |  |
| Design Review |  | 53 |  |  |  |  |  |  | 63 |  |  |  |  |  |  | 116 |  |  |  |  |  |  |
| Code |  | 151 |  |  |  |  |  |  | 181 |  |  |  |  |  |  | 332 |  |  |  |  |  |  |
| Code Review |  | 104 |  |  |  |  |  |  | 127 |  |  |  |  |  |  | 231 |  |  |  |  |  |  |
| Compile |  | 26 |  |  |  |  |  |  | 32 |  |  |  |  |  |  | 58 |  |  |  |  |  |  |
| Test |  | 48 |  |  |  |  |  |  | 97 |  |  |  |  |  |  | 145 |  |  |  |  |  |  |
| Total |  | 635 |  |  |  |  |  |  | 594 |  |  |  |  |  |  | 1229 |  |  |  |  |  |  |
| Defects Injected |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  | 6 |  |  |  |  |  |  |
| HLD Review |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Design |  | 4 |  |  |  |  |  |  | 4 |  |  |  |  |  |  | 8 |  |  |  |  |  |  |
| Design Review |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Code |  | 20 |  |  |  |  |  |  | 24 |  |  |  |  |  |  | 44 |  |  |  |  |  |  |
| Code Review |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Compile |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Test |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Total |  | 30 |  |  |  |  |  |  | 28 |  |  |  |  |  |  | 58 |  |  |  |  |  |  |
| Defects Removed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| HLD Review |  | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  | 4 |  |  |  |  |  |  |
| Design |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Design Review |  | 4 |  |  |  |  |  |  | 4 |  |  |  |  |  |  | 8 |  |  |  |  |  |  |
| Code |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  | 0 |  |  |  |  |  |  |
| Code Review |  | 10 |  |  |  |  |  |  | 13 |  |  |  |  |  |  | 23 |  |  |  |  |  |  |
| Compile |  | 6 |  |  |  |  |  |  | 8 |  |  |  |  |  |  | 14 |  |  |  |  |  |  |
| Test |  | 3 |  |  |  |  |  |  | 6 |  |  |  |  |  |  | 9 |  |  |  |  |  |  |
| Total |  | 27 |  |  |  |  |  |  | 31 |  |  |  |  |  |  | 58 |  |  |  |  |  |  |

Size Estimating Template

| Engineer | Otto | Date | 11/1 |
| --- | --- | --- | --- |
| Project | 2001/XQ35 | Language | C |

| BASE PROGRAM LOC |  |  |  |  |  |  |  |  |  | ESTIMATE |  |  |  |  | ACTUAL |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BASE SIZE (B) => => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 7000 |  |  |  |  |
| LOC DELETED (D) => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |
| LOC MODIFIED (M) => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 25 |  |  |  |  |
| OBJECT LOC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| BASE ADDITIONS |  | TYPE1 |  |  | METHODS |  |  | REL. SIZE |  |  | LOC |  |  | LOC |  |  |
| CD Buttons |  |  | My L |  |  |  |  |  | large |  |  | 60 |  |  |  |  |
| CD Displays |  |  | My L |  |  |  |  |  | v large |  |  | 142 |  |  |  |  |
| TOTAL BASE ADDITIONS (BA) => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 202 |  |  |  |  |
| NEW OBJECTS |  | TYPE |  |  | METHODS |  |  | REL. SIZE |  |  | LOC (New Reused*) |  |  |  |  |  |
| CD Control |  |  | My I/O |  |  |  |  |  | large |  |  | 85* |  |  |  |  |
| CD Initialize |  |  | My L |  |  |  |  |  | medium |  |  | 35* |  |  |  |  |
| CD Monitor |  |  | My L |  |  |  |  |  | medium |  |  | 35* |  |  |  |  |
| TOTAL NEW OBJECTS (NO) => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 155 |  |  |  |  |
| REUSED OBJECTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Synch Serial Com |  |  |  |  |  |  |  |  |  |  |  | 40 |  |  |  |  |
| REUSED TOTAL (R) => => => => => => => => => |  |  |  |  |  |  |  |  |  |  |  | 40 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | SIZE |  |  | TIME |  |
| Estimated Object LOC (E): E = BA+NO+M |  |  |  |  |  |  |  |  |  |  |  | 382 |  |  |  |  |
| Regression Parameters: 0 Size and Time |  |  |  |  |  |  |  |  |  |  |  | 45 |  |  | 110 |  |
| Regression Parameters: 1 Size and Time |  |  |  |  |  |  |  |  |  |  |  | 1.32 |  |  | 3.495 |  |
| Estimated New and Changed LOC (N): N = 0 + 1*E |  |  |  |  |  |  |  |  |  |  |  | 549 |  |  |  |  |
| Estimated Total LOC: T = N + B - D - M + R |  |  |  |  |  |  |  |  |  |  |  | 7564 |  |  |  |  |
| Estimated Total New Reuse (sum of * LOC): |  |  |  |  |  |  |  |  |  |  |  | 155 |  |  |  |  |
| Estimated Total Development Time: Time = 0 + 1*E |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1445 |  |
| Prediction Range: Range |  |  |  |  |  |  |  |  |  |  |  | 320 |  |  | 455 |  |
| Upper Prediction Interval: UPI = N + Range |  |  |  |  |  |  |  |  |  |  |  | 869 |  |  | 1900 |  |
| Lower Prediction Interval: LPI = N - Range |  |  |  |  |  |  |  |  |  |  |  | 229 |  |  | 990 |  |
| Prediction Interval Percent: |  |  |  |  |  |  |  |  |  |  |  | 70 |  |  | 70 |  |

Table C47 Task Planning Template

| Engineer | Otto | Date | 11/1 |
| --- | --- | --- | --- |
| Project | 2001 XQ35 |  | revised plan |

| Task |  | Plan |  |  |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Name | Hours | Planned Value | Cumulative Hours | Cumulative Planned Value | Date | Date | Earned Value | Cumulative Earned Value |
| 1 | Plan | 2.40 | 10 | 2.40 | 10 | 11/5 |  |  |  |
| 2 | HLD | 1.93 | 8 | 4.33 | 18 | 6 |  |  |  |
| 3 | HLD Review | 0.97 | 4 | 5.30 | 22 | 6 |  |  |  |
| 4 | C1: Design | 1.32 | 5.5 | 6.62 | 27.5 | 7 |  |  |  |
| 5 | Design Review | 0.88 | 3.7 | 7.50 | 31.1 | 7 |  |  |  |
| 6 | Code | 2.52 | 10.4 | 10.02 | 41.6 | 11 |  |  |  |
| 7 | Code Review | 1.75 | 7.3 | 11.77 | 48.9 | 11 |  |  |  |
| 8 | Compile | 0.43 | 1.8 | 12.20 | 50.7 | 12 |  |  |  |
| 9 | Test | 0.80 | 3.3 | 13.00 | 54.0 | 12 |  |  |  |
| 10 | C2: Design | 1.57 | 6.5 | 14.57 | 60.5 | 13 |  |  |  |
| 11 | Design Review | 1.05 | 4.4 | 15.62 | 64.8 | 13 |  |  |  |
| 12 | Code | 3.02 | 12.5 | 18.63 | 77.4 | 15 |  |  |  |
| 13 | Code Review | 2.10 | 8.7 | 20.73 | 86.1 | 18 |  |  |  |
| 14 | Compile | 0.53 | 2.2 | 21.27 | 88.3 | 18 |  |  |  |
| 15 | Test | 1.62 | 6.7 | 22.88 | 95.0 | 19 |  |  |  |
| 16 | Postmortem | 1.20 | 5 | 24.08 | 100 | 20 |  |  |  |
| 17 |  |  |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |  |  |
| Totals |  |  |  |  |  |  |  |  |  |

Table C49  Schedule Planning Template

| Engineer | Otto | Date | 11/1 |
| --- | --- | --- | --- |
| Project | 2001 XQ35 |  | revised plan |

|  |  |  | Plan |  |  |  | Actual |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Day | Date |  | Direct | Cumulative | Cumulative | Direct |  | Cumulative | Cumulative | Adjusted |  |
| No. |  |  | Hours | Hours | Planned Value | Hours |  | Hours | Earned Value | Earned Value |  |
| 1 | 11/4 |  | 2 | 2 | 0 |  |  |  |  |  |  |
| 2 | 5 |  | 2 | 4 | 10 |  |  |  |  |  |  |
| 3 | 6 |  | 2 | 6 | 22 |  |  |  |  |  |  |
| 4 | 7 |  | 2 | 8 | 31.1 |  |  |  |  |  |  |
| 5 | 8 |  | 2 | 10 | 31.1 |  |  |  |  |  |  |
| 6 | 11/11 |  | 2 | 12 | 48.8 |  |  |  |  |  |  |
| 7 | 12 |  | 2 | 14 | 54.0 |  |  |  |  |  |  |
| 8 | 13 |  | 2 | 16 | 64.8 |  |  |  |  |  |  |
| 9 | 14 |  | 2 | 18 | 64.8 |  |  |  |  |  |  |
| 10 | 15 |  | 2 | 20 | 77.4 |  |  |  |  |  |  |
| 11 | 11/18 |  | 2 | 22 | 88.3 |  |  |  |  |  |  |
| 12 | 19 |  | 2 | 24 | 95.0 |  |  |  |  |  |  |
| 13 | 20 |  | 2 | 26 | 100 |  |  |  |  |  |  |
| 14 | 21 |  | 2 | 28 |  |  |  |  |  |  |  |
| 15 | 22 |  | 2 | 30 |  |  |  |  |  |  |  |
| 16 | 11/25 |  | 2 | 32 |  |  |  |  |  |  |  |
| 17 | 26 |  | 2 | 34 |  |  |  |  |  |  |  |
| 18 | 27 |  | 2 | 36 |  |  |  |  |  |  |  |
| 19 | 28 |  | 2 | 38 |  |  |  |  |  |  |  |
| 20 | 29 |  | 2 | 40 |  |  |  |  |  |  |  |
| 21 |  |  |  |  |  |  |  |  |  |  |  |
| 22 |  |  |  |  |  |  |  |  |  |  |  |
| 23 |  |  |  |  |  |  |  |  |  |  |  |
| 24 |  |  |  |  |  |  |  |  |  |  |  |
| 25 |  |  |  |  |  |  |  |  |  |  |  |
| 26 |  |  |  |  |  |  |  |  |  |  |  |
| 27 |  |  |  |  |  |  |  |  |  |  |  |
| 28 |  |  |  |  |  |  |  |  |  |  |  |
| 29 |  |  |  |  |  |  |  |  |  |  |  |
| 30 |  |  |  |  |  |  |  |  |  |  |  |
| 31 |  |  |  |  |  |  |  |  |  |  |  |
| 32 |  |  |  |  |  |  |  |  |  |  |  |
| 33 |  |  |  |  |  |  |  |  |  |  |  |

Total Base is the starting Base for Cycle 1

Total LOC is the final size for Cycle 2

1 L-Logic, I-I/O, C-Calculation, T-Text, D-Data, S-Set-up