Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Workbook for
Coaching PSP-trained Developers Exercise
Part 3

Managing TSP Teams

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

Managing TSP Teams

Coaching PSP-trained Developers Exercise

Overview

| #### Exercise Overview | The exercise includes the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Exercise Objectives | 2 |
|  | Exercise Instructions | 2 |
|  | Background Information | 3 |
|  | Otto’s completed Project Plan Summary | 4 |
|  | Otto’s completed Cycle Summary (Actual) | 6 |
|  | Otto’s completed Task and Schedule Templates | 7 |
|  | Otto’s completed Earned Value Chart | 9 |

| #### Exercise Objectives | After completing this exercise, participants will - have a better understanding of the issues involved in using PSP at work - understand how to evaluate a PSP plan, how to check progress against a plan, and how to evaluate a completed PSP project |
| --- | --- |

| #### Exercise #### Instructions | - Review the background information and Otto’s completed PSP data. - Based on his data, identify what “coaching” you would provide to Otto. - Prepare and present a short presentation (10 minutes) on your findings. |
| --- | --- |

Background

| #### Background | Otto has completed his PSP project and has asked to meet with you to review his PSP data on the project. |
| --- | --- |

PSP3 Project Plan Summary

| Engineer | Otto | Date | 11/26 |
| --- | --- | --- | --- |
| Project | 2001/XQ35 |  | completed |
| Component | Compact Disc | Language | C |

| Summary | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LOC/Hour | 22.80 |  |  |  | 17.15 |  |  |  | 17.15 |  |  |
| Planned Time | 1445 |  |  |  |  |  |  |  | 1445 |  |  |
| Actual Time |  |  |  |  | 1900 |  |  |  | 1900 |  |  |
| CPI(Cost-Performance Index) |  |  |  |  |  |  |  |  | .76 |  |  |
|  |  |  |  |  |  |  |  |  | (Planned/Actual) |  |  |
| % Reused | .5 |  |  |  | .5 |  |  |  | .5 |  |  |
| % New Reused | 28.2 |  |  |  | 35 |  |  |  | 35 |  |  |
| Test Defects/KLOC | 15.8 |  |  |  | 33.2 |  |  |  | 33.2 |  |  |
| Total Defects/KLOC | 106 |  |  |  | 125.2 |  |  |  | 125.2 |  |  |
| Yield | 61% |  |  |  | 40% |  |  |  | 40% |  |  |
| % Appraisal COQ | 28 |  |  |  | 10.4 |  |  |  | 10.4 |  |  |
| % Failure COQ | 14 |  |  |  | 29.4 |  |  |  | 29.4 |  |  |
| COQ A/F Ratio | 2.0 |  |  |  | .35 |  |  |  | .35 |  |  |
| Program Size (LOC) | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| Base(B) | 7000 |  |  |  | 7000 |  |  |  |  |  |  |
|  | (Measured) |  |  |  | (Measured) |  |  |  |  |  |  |
| Deleted (D) | 0 |  |  |  | 0 |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |
| Modified (M) | 25 |  |  |  | 38 |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |
| Added (A) | 524 |  |  |  | 505 |  |  |  |  |  |  |
|  | (N-M) |  |  |  | (T-B+D-R) |  |  |  |  |  |  |
| Reused (R) | 40 |  |  |  | 40 |  |  |  | 40 |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |  |  |  |  |
| Total New & Changed (N) | 549 |  |  |  | 543 |  |  |  | 543 |  |  |
|  | (Estimated) |  |  |  | (A+M) |  |  |  |  |  |  |
| Total LOC (T) | 7564 |  |  |  | 7545 |  |  |  | 7545 |  |  |
|  | (N+B-M-D+R) |  |  |  | (Measured) |  |  |  |  |  |  |
| Total New Reused | 155 |  |  |  | 190 |  |  |  | 190 |  |  |
| Upper Prediction Interval (70%) | 869 |  |  |  |  |  |  |  |  |  |  |
| Lower Prediction Interval (70%) | 229 |  |  |  |  |  |  |  |  |  |  |
| Time in Phase (min.) | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| Planning | 144 |  | 120 |  |  |  | 120 |  |  |  | 6.3 |
| High-level design | 116 |  | 65 |  |  |  | 65 |  |  |  | 3.4 |
| High-level design review | 58 |  | 20 |  |  |  | 20 |  |  |  | 1.1 |
| Detailed design | 173 |  | 110 |  |  |  | 110 |  |  |  | 5.8 |
| Detailed design review | 116 |  | 38 |  |  |  | 38 |  |  |  | 2.0 |
| Code | 332 |  | 763 |  |  |  | 763 |  |  |  | 40.2 |
| Code review | 231 |  | 160 |  |  |  | 160 |  |  |  | 8.4 |
| Compile | 58 |  | 127 |  |  |  | 127 |  |  |  | 6.7 |
| Test | 145 |  | 432 |  |  |  | 432 |  |  |  | 22.7 |
| Postmortem | 72 |  | 65 |  |  |  | 65 |  |  |  | 3.4 |
| Total | 1445 |  | 1900 |  |  |  | 1900 |  |  |  | 100 |
| Total Time UPI (70%) | 1900 |  |  |  |  |  |  |  |  |  |  |
| Total Time LPI (70%) | 990 |  |  |  |  |  |  |  |  |  |  |

PSP3 Project Plan Summary (continued)

| Engineer | Otto | Date | 11/26 |
| --- | --- | --- | --- |
| Project | 2001/XQ35 |  | completed |
| Component | Compact Disc | Language | C |

| Defects Injected | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning | 0 |  | 0 |  |  |  | 0 |  |  |  | 0.0 |
| High-level design | 6 |  | 2 |  |  |  | 2 |  |  |  | 2.9 |
| High-level design review | 0 |  | 0 |  |  |  | 0 |  |  |  | 0.0 |
| Detailed design | 8 |  | 15 |  |  |  | 15 |  |  |  | 22.1 |
| Detailed design review | 0 |  | 0 |  |  |  | 0 |  |  |  | 0.0 |
| Code | 44 |  | 46 |  |  |  | 46 |  |  |  | 67.7 |
| Code review | 0 |  | 0 |  |  |  | 0 |  |  |  | 0.0 |
| Compile | 0 |  | 2 |  |  |  | 2 |  |  |  | 2.9 |
| Test | 0 |  | 3 |  |  |  | 3 |  |  |  | 4.4 |
| Total Development | 58 |  | 68 |  |  |  | 68 |  |  |  | 100 |
| Defects Removed | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| Planning | 0 |  | 0 |  |  |  | 0 |  |  |  | 0.0 |
| High-level design | 0 |  | 0 |  |  |  | 0 |  |  |  | 0.0 |
| High-level design review | 4 |  | 0 |  |  |  | 0 |  |  |  | 0.0 |
| Detailed design | 0 |  | 0 |  |  |  | 0 |  |  |  | 0.0 |
| Detailed design review | 8 |  | 2 |  |  |  | 2 |  |  |  | 2.9 |
| Code | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |
| Code review | 23 |  | 23 |  |  |  | 23 |  |  |  | 33.8 |
| Compile | 14 |  | 25 |  |  |  | 25 |  |  |  | 36.8 |
| Test | 9 |  | 18 |  |  |  | 18 |  |  |  | 26.5 |
| Total Development | 58 |  | 68 |  |  |  | 68 |  |  |  | 100 |
| After Development |  |  |  |  |  |  |  |  |  |  |  |
| Defect Removal Efficiency | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| Defects/Hour - Design review | 4.2 |  |  |  | 3.2 |  |  |  | 3.2 |  |  |
| Defects/Hour - Code review | 6.0 |  |  |  | 8.6 |  |  |  | 8.6 |  |  |
| Defects/Hour - Compile | 14.5 |  |  |  | 11.8 |  |  |  | 11.8 |  |  |
| Defects/Hour - Test | 3.6 |  |  |  | 2.5 |  |  |  | 2.5 |  |  |
| DRL(DLDR/UT) | 1.2 |  |  |  | 1.3 |  |  |  | 1.3 |  |  |
| DRL(Code Review/UT) | 1.7 |  |  |  | 3.5 |  |  |  | 3.5 |  |  |
| DRL(Compile/UT) | 4.0 |  |  |  | 4.7 |  |  |  | 4.7 |  |  |

Cycle Summary

| Engineer | Otto |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  | 11/26 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project | 2001 XQ35 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | completed |  |  |  |  |  |
| Component | Compact Disc |  |  |  |  |  |  |  |  |  |  | Language |  |  |  |  | C |  |  |  |  |  |
| Cycle |  |  | 1 |  |  |  |  | 2 |  |  |  |  |  |  | Total |  |  |  |  |  |  |  |
|  |  |  | Plan |  |  | Actual |  | Plan |  |  | Actual |  |  |  | Plan |  |  |  |  | Actual |  |  |
| Program Size (LOC) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Base(B) |  | 7000 |  |  | 7000 |  |  |  | 7290 |  |  |  | 7325 |  |  | 7000 |  |  | 7000Error: Reference source not found |  |  |  |
| Deleted (D) |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |
| Modified (M) |  | 0 |  |  | 0 |  |  |  | 25 |  |  |  | 38 |  |  | 25 |  |  | 38 |  |  |  |
| Added (A) |  | 250 |  |  | 285 |  |  |  | 274 |  |  |  | 220 |  |  | 524 |  |  | 505 |  |  |  |
| Reused (R) |  | 40 |  |  | 40 |  |  |  | 0 |  |  |  | 0 |  |  | 40 |  |  | 40 |  |  |  |
| Total New & Changed (N) |  | 250 |  |  | 285 |  |  |  | 299 |  |  |  | 258 |  |  | 549 |  |  | 543 |  |  |  |
| Total LOC (T) |  | 7290 |  |  | 7325 |  |  |  | 7564 |  |  |  | 7545 |  |  | 7564 |  |  | 7545Error: Reference source not found |  |  |  |
| Total New Reused |  | 155 |  |  | 190 |  |  |  | 0 |  |  |  | 0 |  |  | 155 |  |  | 190 |  |  |  |
| Time in Phase (min.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 116 |  |  | 65 |  |  |  |  |  |  |  |  |  |  | 116 |  |  | 65 |  |  |  |
| HLD Review |  | 58 |  |  | 20 |  |  |  |  |  |  |  |  |  |  | 58 |  |  | 20 |  |  |  |
| Design |  | 79 |  |  | 40 |  |  |  | 94 |  |  |  | 70 |  |  | 173 |  |  | 110 |  |  |  |
| Design Review |  | 53 |  |  | 10 |  |  |  | 63 |  |  |  | 28 |  |  | 116 |  |  | 38 |  |  |  |
| Code |  | 151 |  |  | 483 |  |  |  | 181 |  |  |  | 280 |  |  | 332 |  |  | 763 |  |  |  |
| Code Review |  | 104 |  |  | 45 |  |  |  | 127 |  |  |  | 115 |  |  | 231 |  |  | 160 |  |  |  |
| Compile |  | 26 |  |  | 105 |  |  |  | 32 |  |  |  | 22 |  |  | 58 |  |  | 127 |  |  |  |
| Test |  | 48 |  |  | 312 |  |  |  | 97 |  |  |  | 120 |  |  | 145 |  |  | 432 |  |  |  |
| Total |  | 635 |  |  | 1080 |  |  |  | 594 |  |  |  | 635 |  |  | 1229 |  |  | 1715 |  |  |  |
| Defects Injected |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 6 |  |  | 2 |  |  |  |  |  |  |  |  |  |  | 6 |  |  | 2 |  |  |  |
| HLD Review |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  | 0 |  |  | 0 |  |  |  |
| Design |  | 4 |  |  | 5 |  |  |  | 4 |  |  |  | 10 |  |  | 8 |  |  | 15 |  |  |  |
| Design Review |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |
| Code |  | 20 |  |  | 27 |  |  |  | 24 |  |  |  | 19 |  |  | 44 |  |  | 46 |  |  |  |
| Code Review |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |
| Compile |  | 0 |  |  | 2 |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 2 |  |  |  |
| Test |  | 0 |  |  | 3 |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 3 |  |  |  |
| Total |  | 30 |  |  | 37 |  |  |  | 28 |  |  |  | 29 |  |  | 58 |  |  | 68 |  |  |  |
| Defects Removed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| High-level Design |  | 0 |  |  | 0 |  |  |  |  |  |  |  |  |  |  | 0 |  |  | 0 |  |  |  |
| HLD Review |  | 4 |  |  | 0 |  |  |  |  |  |  |  |  |  |  | 4 |  |  | 0 |  |  |  |
| Design |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |
| Design Review |  | 4 |  |  | 0 |  |  |  | 4 |  |  |  | 2 |  |  | 8 |  |  | 2 |  |  |  |
| Code |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  |
| Code Review |  | 10 |  |  | 5 |  |  |  | 13 |  |  |  | 18 |  |  | 23 |  |  | 23 |  |  |  |
| Compile |  | 6 |  |  | 19 |  |  |  | 8 |  |  |  | 6 |  |  | 14 |  |  | 25 |  |  |  |
| Test |  | 3 |  |  | 13 |  |  |  | 6 |  |  |  | 5 |  |  | 9 |  |  | 18 |  |  |  |
| Total |  | 27 |  |  | 37 |  |  |  | 31 |  |  |  | 31 |  |  | 58 |  |  | 68 |  |  |  |

Table C47 Task Planning Template

| Engineer | Otto | Date | 11/26 |
| --- | --- | --- | --- |
| Project | 2001 XQ35 |  | completed |

| Task |  | Plan |  |  |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Name | Hours | Planned Value | Cumulative Hours | Cumulative Planned Value | Date | Date | Earned Value | Cumulative Earned Value |
| 1 | Plan | 2.40 | 10 | 2.40 | 10 | 11/5 | 11/4 | 10 | 10 |
| 2 | HLD | 1.93 | 8 | 4.33 | 18 | 6 | 5 | 8 | 18 |
| 3 | HLD Review | 0.97 | 4 | 5.30 | 22 | 6 | 5 | 4 | 22 |
| 4 | C1: Design | 1.32 | 5.5 | 6.62 | 27.5 | 7 | 6 | 5.5 | 27.5 |
| 5 | Design Review | 0.88 | 3.7 | 7.50 | 31.1 | 7 | 6 | 3.7 | 31.2 |
| 6 | Code | 2.52 | 10.4 | 10.02 | 41.6 | 11 | 12 | 10.4 | 41.6 |
| 7 | Code Review | 1.75 | 7.3 | 11.77 | 48.9 | 11 | 13 | 7.3 | 48.9 |
| 8 | Compile | 0.43 | 1.8 | 12.20 | 50.7 | 12 | 14 | 1.8 | 50.7 |
| 9 | Test | 0.80 | 3.3 | 13.00 | 54.0 | 12 | 19 | 3.3 | 54 |
| 10 | C2: Design | 1.57 | 6.5 | 14.57 | 60.5 | 13 | 20 | 6.5 | 60.5 |
| 11 | Design Review | 1.05 | 4.4 | 15.62 | 64.8 | 13 | 20 | 4.4 | 64.9 |
| 12 | Code | 3.02 | 12.5 | 18.63 | 77.4 | 15 | 22 | 12.5 | 77.4 |
| 13 | Code Review | 2.10 | 8.7 | 20.73 | 86.1 | 18 | 22 | 8.7 | 86.1 |
| 14 | Compile | 0.53 | 2.2 | 21.27 | 88.3 | 18 | 25 | 2.2 | 88.3 |
| 15 | Test | 1.62 | 6.7 | 22.88 | 95.0 | 19 | 26 | 6.7 | 95 |
| 16 | Postmortem | 1.20 | 5 | 24.08 | 100 | 20 | 26 | 5 | 100 |
| 17 |  |  |  |  |  |  |  |  |  |
| 18 |  |  |  |  |  |  |  |  |  |
| Totals |  |  |  |  |  |  |  |  |  |

Table C49  Schedule Planning Template

Cycle 1

Cycle 2

| Engineer | Otto | Date | 11/26 |
| --- | --- | --- | --- |
| Project | 2001 XQ35 |  | completed |

|  |  |  | Plan |  |  |  | Actual |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Day | Date |  | Direct | Cumulative | Cumulative | Direct |  | Cumulative | Cumulative | Adjusted |  |
| No. |  |  | Hours | Hours | Planned Value | Hours |  | Hours | Earned Value | Earned Value |  |
| 1 | 11/4 |  | 2 | 2 | 0 | 2 |  | 2 | 10 |  |  |
| 2 | 5 |  | 2 | 4 | 10 | 1.41 |  | 3.41 | 22 |  |  |
| 3 | 6 |  | 2 | 6 | 22 | 1.33 |  | 4.74 | 31.2 |  |  |
| 4 | 7 |  | 2 | 8 | 31.1 | 2 |  | 6.74 | 31.2 |  |  |
| 5 | 8 |  | 2 | 10 | 31.1 | 2 |  | 8.74 | 31.2 |  |  |
| 6 | 11/11 |  | 2 | 12 | 48.8 | 2 |  | 10.74 | 31.2 |  |  |
| 7 | 12 |  | 2 | 14 | 54.0 | 1.57 |  | 12.31 | 41.6 |  |  |
| 8 | 13 |  | 2 | 16 | 64.8 | .75 |  | 13.06 | 48.9 |  |  |
| 9 | 14 |  | 2 | 18 | 64.8 | 2.25 |  | 15.31 | 50.7 |  |  |
| 10 | 15 |  | 2 | 20 | 77.4 | 2.33 |  | 17.64 | 50.7 |  |  |
| 11 | 11/18 |  | 2 | 22 | 88.3 | 1.13 |  | 18.77 | 50.7 |  |  |
| 12 | 19 |  | 2 | 24 | 95.0 | 2 |  | 20.77 | 54 |  |  |
| 13 | 20 |  | 2 | 26 | 100 | 2 |  | 22.77 | 64.9 |  |  |
| 14 | 21 |  | 2 | 28 |  | 3 |  | 25.77 | 64.9 |  |  |
| 15 | 22 |  | 2 | 30 |  | 2.7 |  | 28.47 | 86.1 |  |  |
| 16 | 11/25 |  | 2 | 32 |  | 2 |  | 30.47 | 88.3 |  |  |
| 17 | 26 |  | 2 | 34 |  | 1.2 |  | 31.67 | 100 |  |  |
| 18 | 27 |  | 2 | 36 |  |  |  |  |  |  |  |
| 19 | 28 |  | 2 | 38 |  |  |  |  |  |  |  |
| 20 | 29 |  | 2 | 40 |  |  |  |  |  |  |  |
| 21 |  |  |  |  |  |  |  |  |  |  |  |
| 22 |  |  |  |  |  |  |  |  |  |  |  |
| 23 |  |  |  |  |  |  |  |  |  |  |  |
| 24 |  |  |  |  |  |  |  |  |  |  |  |
| 25 |  |  |  |  |  |  |  |  |  |  |  |
| 26 |  |  |  |  |  |  |  |  |  |  |  |
| 27 |  |  |  |  |  |  |  |  |  |  |  |
| 28 |  |  |  |  |  |  |  |  |  |  |  |
| 29 |  |  |  |  |  |  |  |  |  |  |  |
| 30 |  |  |  |  |  |  |  |  |  |  |  |
| 31 |  |  |  |  |  |  |  |  |  |  |  |
| 32 |  |  |  |  |  |  |  |  |  |  |  |
| 33 |  |  |  |  |  |  |  |  |  |  |  |

Cycle 2

Cycle 1

Total Base is the starting Base for Cycle 1

Total LOC is the final size for Cycle 2