Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Workbook for
PROBE Part I Exercise

Managing TSP Teams

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

Managing TSP Teams

PROBE  Part I Exercise

Overview

| #### Exercise Overview | The workshop includes the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Exercise Instructions | 2 |
|  | JD’s PROBE Data | 3 |
|  | Size Estimating Template and Instructions | 5 |

| #### Exercise Objectives | After completing this exercise, participants will - understand the first three steps of the PROBE method - conceptual design - identify and size objects - estimate other LOC - have completed the top portion of JD’s size estimating template |
| --- | --- |

| #### Exercise #### Instructions | You have been provided with JD’s data for the first three steps of the PROBE method. - program requirements - JD’s conceptual design - identified objects and relative sizes - JD’s other LOC estimate - JD’s relative size table Using this data, complete all except the ACTUAL column of the top portion of JD’s size estimating template. - base program LOC - object LOC - reused objects |
| --- | --- |

### JD’s Data for the First Three Steps of PROBE

| #### Program 9A Requirements | Program 9A requirements: - Calculate the mean and standard deviation of a series of n real numbers. - Input the numbers from the keyboard or a file. - Store the numbers in a linked list. - Print the results. |
| --- | --- |

| #### Mean and #### Standard #### Deviation #### Equations | The mean is the average of n numbers. xavg=i=1nxin The standard deviation is calculated as follows.  is the symbol for standard deviation  is the symbol for summation i is an index to the n numbers Xavg is the average value of the n numbers. |
| --- | --- |

| #### JD’s Conceptual Design | . |
| --- | --- |

Continued on next page

### JD’s Data for the First Three Steps of PROBE, continued

| #### JD’s Identified Objects |  |
| --- | --- |

| Object | Source | Type | Methods | Relative size |
| --- | --- | --- | --- | --- |
| Main() | Existing base |  |  |  |
| Input_data | New | I/O | 1 | M |
| Linked_list | New | data | 5 | M |
| Calc_mean | New | Calc | 1 | M |
| Calc_sd | New | Calc | 1 | L |
| Print_result | New | I/O | 1 | M |

| #### JD’s Other #### LOC Estimates |  |
| --- | --- |

| Item | Estimated size |
| --- | --- |
| Base | 224 |
| Base deleted | 0 |
| Base modified | 20 |
| Base Additions | 9 |
| Reused | 0 |

| #### JD’s LOC/Method Table |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | C++ Object Size in LOC per Method |  |  |  |  |  |  |  |  |
|  | Object Type | Very Small | Small | Medium | Large | Very Large |  |  |  |
|  | Calculation | 2.34 | 5.13 | 11.25 | 24.66 | 54.04 |  |  |  |
|  | Data | 2.60 | 4.79 | 8.84 | 16.31 | 30.09 |  |  |  |
|  | I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93 |  |  |  |
|  | Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83 |  |  |  |
|  | Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09 |  |  |  |
|  | Text | 3.75 | 8.00 | 17.07 | 36.41 | 77.66 |  |  |  |

Size Estimating Template

1 L-Logic, I-I/O, C-Calculation, T-Text, D-Data, S-Set-up

Size Estimating Template Instructions

| Purpose | This template is used to guide the size estimating process and to hold the estimate data. |
| --- | --- |
| Header | Enter the following: - your name - today's date - the instructor's name - the number of the program If you need additional space in any category, use separate sheets and include the totals on this form. |
| Base Program LOC | If this development is a modification or enhancement of an existing program, - count and enter the base program size at B - enter the estimated base LOC to be deleted at D - enter the estimated base LOC to be modified at M After development, enter the actual LOC for B, D, and M. |
| Object LOC - Base Additions | If you plan to add LOC to the base program enter the added LOC at BA. If the added LOC is a method, use the procedure for new objects. After development, enter the actual LOC for B, D, and M. |
| Object LOC – New Objects | - Identify and name the objects needed for this design. - Judge the number of methods in each object. - Determine the type category for each object (L - Logic, I - I/O, C - Calculation, T - Text, D - Data, S - Set-up). - Estimate the relative size of the object's methods (VS - very small, S - small, M – medium, L - large, VL - very large). - Find the LOC per method from the object database. - Calculate the estimated object size as: number of methods times LOC per method. - Note with an * in the LOC (New Reused*) – ESTIMATED column those objects that will be put in the reuse library. - After development, enter the actual LOC for each new object. |
| Reused Objects | - Enter the name of each unmodified reused object. - Enter the estimated LOC of each unmodified reused object. - Sum these LOC and enter as REUSED TOTAL at R. - After development, enter the actual reused object LOC. - If any reused objects are to be modified or enhanced, include the object LOC with the base program data along with any deletions and modifications. Include their additions with base additions. - Modified objects are treated as base LOC and not as reused objects. |