## Slide 1
Managing TSP Teams
Module 10: PSP Planning - PROBE Part II
Notes: The course name line should be placed so that the bottom of the letters in the title are sitting on the horizontal guideline setting 1.24. Module number and title should be placed so that the bottom of the text letters are sitting on the horizontal guideline setting 0.00 (horizontal center of slide). If the module number/title line is so long that is wraps to two lines, nudge the text upward so that the bottom of the letters in the FIRST line of the module title is sitting on horizontal guideline setting 0.30.
2. The left margin is at vertical guideline 3.91 (left of center). The left edge of the text should touch this guideline.
3. Font setting for “Course Name” line is Arial Narrow, 32 points, bold. Font for the “Module” line is Arial Narrow, 45 points, bold. This information is on the slide body. The “distribution limited” and sponsorship statements are on the master slide. The font convention for these elements is Ariel, 16 points, bold. The footer information is Ariel, 10 points, bold.
4. Always change the month and year information in the footer (title master, slide master) if changes are made to the course material. This includes minor modifications such as correcting typos. Use the month and year in which the changes were made. Change the footers ONLY on modules that were actually changed. If necessary, change the copyright dates (title master, slide master) to the current year’s date.

## Slide 3: Module Overview
Completing the size estimating template
  estimating program size
  estimating resources
  prediction intervals
Starting the project plan

## Slide 4: Completing the Estimate
These steps have been completed.
  conceptual design
  object identification
  estimating other LOC
We are now ready to
  estimate program size
  estimate resources
  calculate prediction intervals

## Slide 5: The PROBE Estimating Method
Conceptual
design
Identify and size objects
Number of
methods
Object
type
Relative
size
Reuse
categories
Estimate other LOC
Estimate
program size
Calculate
prediction interval
Size estimate
Estimate
resources
Calculate
prediction interval
Resource estimate
Step

## Slide 6: Estimating Program Size -1
Estimated object LOC (E) is the sum of
  modified base (M)
  base additions (BA)
  new objects (NO)

## Slide 7: Estimating Program Size -2
Applying linear regression to historical data, the slope (1) and intercept (0) of a “best fit” straight line is determined.
  estimated object LOC is the x axis
  actual N&C LOC is the y axis
The estimated N&C LOC is as follows.
Est. N&C = 0 + 1  (estimated object LOC)
Note: the linear regression parameters 0 and 1 are computed using a spreadsheet and data from prior PSP projects.

## Slide 8: Correlation
In order for regression to give meaningful results, the two data sets must correlate to each other; that is, they must have a good “straight-line” fit.
The degree to which two data sets correlate is given by the the correlation coefficient rxy.

## Slide 9: Using Correlation -1
The correlation rxy can range from +1 to -1.
  Near +1 implies a strong positive relationship: when x increases, so does y.
  Near -1 implies a strong negative relationship: when x increases, y decreases.
  Near 0 implies no relationship.

## Slide 10: Using Correlation -2
Correlation is used in the PSP to judge the quality of the linear relation of various historical process data that are used for planning.
For this purpose we use the value of the relation rxy squared, or r 2.
If r 2 is
0.9 r 2
0.7 r 2 <0.9
r 2 < 0.5
the relationship is
predictive; use it with high confidence
strong and can be used for planning
adequate for planning, but with caution
not reliable for planning purposes
0.5 r 2 <0.7

## Slide 11
Y = 0.83x + 29.34
R2 = 0.8147

## Slide 12: Estimating Judgment -1
At least three pairs of x and y data are necessary to use linear regression.
To be suitable for planning, the correlation coefficient, r, should satisfy the condition r 2  0.5.
0 is a measure of the estimating bias. If 0 is close to or larger than the data being estimated, linear regression may not give a good estimate.

## Slide 13: Estimating Judgment -2
1 represents the percentage that must added to the estimated object LOC to get the total amount of new and changed LOC. For example, a 1 of 1.25 means that the estimate must be increased by 25%.
When 1 is not close to 1.0 (e.g., smaller than 0.5 or larger than 2.0), linear regression may not give a good estimate.
In any situation where linear regression parameters appear unreasonable, historical averages should be used to make estimates.

## Slide 14: The PROBE Estimating Method
Conceptual
design
Identify and size objects
Number of
methods
Object
type
Relative
size
Reuse
categories
Estimate other LOC
Estimate
program size
Calculate
prediction interval
Size estimate
Estimate
resources
Calculate
prediction interval
Resource estimate
Step

## Slide 15: Estimating Resources
Y = 1.71x + 71.91
R2 = 0.6869
To estimate resources, PROBE uses the historical relationship between estimated object LOC and actual resources.

## Slide 16: The PROBE Estimating Method
Conceptual
design
Identify and size objects
Number of
methods
Object
type
Relative
size
Reuse
categories
Estimate other LOC
Estimate
program size
Calculate
prediction interval
Size estimate
Estimate
resources
Calculate
prediction interval
Resource estimate
Step

## Slide 17: Prediction Interval
The prediction interval (PI) is the range around the estimate within which the actual result is likely to fall.
  It assumes that the variation in the estimate is similar to prior estimates.
  It is calculated from the same data used to calculate the regression parameters.
The PI is computed using a 70% likelihood (probability).
The PI helps in understanding the quality of the estimate.
Estimated Object LOC vs. Actual Minutes
y = 1.4507x + 109.8
R2
= 0.6869
0
100
200
300
400
500
600
0
50
100
150
200
250
Estimated Object LOC
Actual Minutes

## Slide 18: Completing the Size Estimate
The steps to completing the size estimating template are as follows.
  Compute the estimated object LOC (E).
  Determine the betas for size and time from historical data (use a spreadsheet.)
  Compute estimated N&C LOC using size betas.
  Compute estimated total (T) LOC.
  Compute estimated total development time using time betas.
  Determine prediction ranges for size and time estimates (use a spreadsheet.)
  Compute upper and lower prediction intervals.

## Slide 19: Starting the Project Plan
The size and time data from the size estimating template are transferred to the plan column of the project plan summary.
  All program size numbers come directly from the template, except the added LOC, which must be computed.
  For time in phase data, only the total, UPI, and LPI come from the template.
  Individual phase times are computed using the “To date %” from the last project.

## Slide 20: Messages to Remember
PROBE uses historical data of the engineers’ work. It allows engineers to
  predict the accuracy of their estimate
  improve their estimating accuracy