## Slide 1
Managing TSP Teams
Module 12: PSP Planning -Schedule
Notes: The course name line should be placed so that the bottom of the letters in the title are sitting on the horizontal guideline setting 1.24. Module number and title should be placed so that the bottom of the text letters are sitting on the horizontal guideline setting 0.00 (horizontal center of slide). If the module number/title line is so long that is wraps to two lines, nudge the text upward so that the bottom of the letters in the FIRST line of the module title is sitting on horizontal guideline setting 0.30.
2. The left margin is at vertical guideline 3.91 (left of center). The left edge of the text should touch this guideline.
3. Font setting for “Course Name” line is Arial Narrow, 32 points, bold. Font for the “Module” line is Arial Narrow, 45 points, bold. This information is on the slide body. The “distribution limited” and sponsorship statements are on the master slide. The font convention for these elements is Ariel, 16 points, bold. The footer information is Ariel, 10 points, bold.
4. Always change the month and year information in the footer (title master, slide master) if changes are made to the course material. This includes minor modifications such as correcting typos. Use the month and year in which the changes were made. Change the footers ONLY on modules that were actually changed. If necessary, change the copyright dates (title master, slide master) to the current year’s date.

## Slide 3: Module Overview
Planning framework
Creating a schedule
Project tracking

## Slide 4: The PSP Planning Framework
PROBE method
Define
requirements
Produce
conceptual
design
Estimate
size
Estimate
resources
Produce
schedule
Develop
product
Size, resource
schedule
data
Process
analysis
Resources
available
Productivity
database
Size
database
Customer
need
Product
delivery
Tracking
reports
Customer
Management
Items
Tasks
Notes: 14

## Slide 5: PSP Planning Steps

## Slide 6: The Scheduling Process
Determine tasks and
estimate task effort
Determine available
project hours for each week
Determine task sequence
and completion dates
Calculate
planned values
Schedule and task plans
Planned total time
Notes: 19

## Slide 7: Schedule Estimating
To make a schedule, three things are needed.
  the estimated hours per task
  a calendar of available direct hours
  the order in which the tasks will be done
Then, scheduling consists of
  spreading the available hours across the tasks
  determining when each task should be started
  determining when each task is likely to finish

## Slide 8: Project Tracking -1
To track a project, you need
  a detailed plan
  data on tasks completed
  a way to measure the value of each task
Then, you
  determine the historical rate of task completion
  use that rate to estimate the project completion date

## Slide 9: Project Tracking -2
With a detailed plan, you
  have two or three checkpoints per week
  can accurately determine status
  can accurately estimate job completion
However, since tasks vary, you need a common way to assign value to task completion.
Earned value is a way to do this.

## Slide 10: Earned Value Tracking -1
The planned value for a task is the percent of the total project hours that a task is planned to take.
Planned value establishes a common value for each task, regardless of the type of work, which facilitates progress tracking.
When a task is completed, it is assigned an earned value (EV) that is equal to the planned value for that task (regardless of how many hours it actually took).
Partially completed tasks receive no earned value.

## Slide 11: Earned Value Tracking -2
As each task is completed, it earns the planned value.
  Enter the earned value (EV) for the task.
  Enter the date of task completion.
  Add the EV to date in the cumulative EV column.
Enter the cumulative EV for each week as it is completed.
Track the earned value versus planned value by week.

## Slide 12: A Scheduling Example -1
Suppose an engineer shows you this plan.
Do you see any problems with it?
Notes: 43

## Slide 13: A Scheduling Example -2
Here’s the schedule after six weeks.
Notes: 44

## Slide 14: Management Considerations
Schedule planning and status tracking which are based on earned value is one of the most powerful management aspects of PSP.
An earned value plan based on historical data, and with two or three milestones per week, gives a very accurate picture of project status and a forecast of when the project will be finished.
You should require your engineers to produce an earned value plan before they start their work, and you should track their progress each week against that plan.

## Slide 15: Messages to Remember
The PSP shows engineers how to estimate and plan their work.
As engineers gain experience, they learn to make better estimates and plans.
The keys to making better estimates and plans are to use
  relevant historical data
  statistically sound methods
  a defined estimating and planning process
  sound judgement
Notes: 49