## Slide 1
Managing TSP Teams
Module 15: Tracking and Maintaining the TSP Plan
Notes: This module is designed to be very discussion oriented.
Most slides have notes to indicate how the slide should be delivered.

## Slide 3: Module Overview
Collecting and tracking data
The weekly team meeting
Maintaining the team’s schedule

## Slide 4: From the Launch
The team has
  completed the TSP launch and planned their work
  made a commitment and obtained management approval to proceed
  begun to carry out their plan
The team will not get the intended benefits of TSP if they do not follow the process, which includes collecting and tracking data.
Notes: These first few slides are just background context, move through them briskly.

## Slide 5: The TSP Launch Artifacts
Team goals
Conceptual design
Planned products
Size estimates
Task hour plan
Schedule plan
Earned-value plan
What if?
How well?
Who?
When?
How?
What?
Team strategy
Team process
Team roles
Task plans
Detailed plans
Quality plan
Risk evaluation
Alternative plans
Business needs
Management goals
Product requirements
. 2004 by Carnegie Mellon University
July 2004
Managing TSP Teams - Module 15 - <number>

## Slide 6: TSP Project Tracking
Project tracking in TSP is based on
  the team’s plan
  task hour and task completion data
  plan and earned value
Individual plans facilitate precise project tracking.
Team members are each responsible for
  gathering data on their work
  tracking status against their personal plans
  the quality of the work that they produce
  keeping the team informed of their progress
Individual team member data are consolidated each week so that the team can assess progress against goals.

## Slide 7: The Weekly Team Meeting
The weekly team meeting is the forum that the team uses to
  track progress against the plan
  track the status on the project's issues and risks
  communicate with each other
TSP Week Summary - Form WEEK
Name
Date
2/7/2000
Team
Status for Week
5
Cycle
Week Date
1/31/2000
Plan/
Weekly Data
Plan
Actual
Actual
Project hours for this week
80.0
69.0
1.16
Project hours this cycle to date
400.0
344.8
1.16
Earned value for this week
10.3
3.1
3.37
Earned value this cycle to date
40.2
30.0
1.34
To-date hours for tasks completed
293.0
303.8
0.96
Plan
Actual
Earned
Planned
Plan Hrs./
Assembly
Phase
Tasks Completed
Resource
Hours
Hours
Value
Week
Actual Hrs.
SYSTEM
REQ
Write SRS general sections
tmc
14.0
12.0
1.4
4
1.17
SYSTEM
REQ
Weekly requirements analysis meeting 5
tma
4.0
4.0
0.4
5
1.00
SYSTEM
REQ
Weekly requirements analysis meeting 5
tmb
4.0
4.0
0.4
5
1.00
SYSTEM
REQ
Weekly requirements analysis meeting 5
tmc
4.0
4.0
0.4
5
1.00
SYSTEM
REQ
Weekly requirements analysis meeting 5
tmd
4.0
4.0
0.4
5
1.00
TASKS DUE THROUGH WEEK 7
SYSTEM
REQ
Review SRS general sections
tmc
5.0
0.0
4
SYSTEM
STP
Complete Validation Test Plan
tmd
8.0
8.5
0.0
4
0.94
Consolidated Team Plan
Security System Upgrade
Notes: Contrast this with a typical team meeting (I.e., non-TSP).

## Slide 8: Maintaining the Team’s Schedule
The team manages its commitments by using the data it collects.
The team determines how it is doing against its plan.
If the team is falling behind, it determines
  what is the likely cause
  what the team can do to maintain its commitment
The team informs management if the commitment cannot be maintained or if management help is needed.
Notes: note – need to bring in idea about the launch resulted in a commitment by the team, the plan was the teams way of assuring themselves they could meet the commitment. Now that the team has started work, the plan is the team’s tool to see where they stand on meeting that commitment.
The plan is not “cast-in-concrete” not to be changed. The plan is dynamic and the team needs to continual change it to make sure it reflects what they know now. And the team uses it to guide them in meeting their commitment to management.

## Slide 9: Determining Status Against Plan
TSP Week Summary - Form WEEK
Name
Date
2/7/2000
Team
Status for Week
5
Cycle
Week Date
1/31/2000
Plan/
Weekly Data
Plan
Actual
Actual
Project hours for this week
80.0
69.0
1.16
Project hours this cycle to date
400.0
344.8
1.16
Earned value for this week
10.3
3.1
3.37
Earned value this cycle to date
40.2
30.0
1.34
To-date hours for tasks completed
293.0
303.8
0.96
Consolidated Team Plan
Security System Upgrade
Two things are important here.
  the team’s current project status
  the team’s projected completion date
Current status is determined using data on the WEEK form.
Notes: Note, this slide has animation on the arrows. As you explain the formula on the bottom, use the mouse click to show where each item comes from on the Week form.
A remote mouse clicker is very helpful.

## Slide 10: Determining Status Against Plan (continued)
Projected completion date can be determined using data on the WEEK form and the original planned weeks.
TSP Week Summary - Form WEEK
Name
Date
2/7/2000
Team
Status for Week
5
Cycle
Week Date
1/31/2000
Plan/
Weekly Data
Plan
Actual
Actual
Project hours for this week
80.0
69.0
1.16
Project hours this cycle to date
400.0
344.8
1.16
Earned value for this week
10.3
3.1
3.37
Earned value this cycle to date
40.2
30.0
1.34
To-date hours for tasks completed
293.0
303.8
0.96
Consolidated Team Plan
Millenium Upgrade
Notes: Note, this slide has animation. Walk through the first formula, using the mouse click to show where each item comes from on the Week form. Then use the mouse click to show the second formula and explain it.
These 2 indicators tell us the magnitude of the problem, now we want to look into why the team is behind and then what the team can do.

## Slide 11: Possible Causes of Plan Deviation
The estimates used to produce the plan may be inaccurate.
  not based on historical data
  poor size estimate and/or productivity rates
Team members may not be getting the task time as planned.
  frequent interruptions
  unplanned work
The team may not have a suitable plan. The next slides discuss possible problems with the plan.
Notes: Make sure you understand the flow that follows this slide. How to determine if inaccurate estimates or not getting enough task hours are the cause of not being on plan will be addressed starting on slide 14.
But first we examine the problem of not having a suitable plan because you really can’t track status until you have a suitable plan.

## Slide 12: Possible Problems with the Plan
The plan does not reflect the work that the team needs to do.
  The tasks on individual plans are not what the individual needs to do.
How is this likely to affect the team’s status?
What should the team do about this?
Notes: Explain this point to the class.
  Think about why this happened, mostly inexperience at making plans. The team should improve its ability to make plans over time.
Then ask the class how this will affect the team’s status.
  the team will not be able to record task hours since what they are working on is not a task in their plan
  their earned value will be low, possibly very low
What should the team do?
  replan!

## Slide 13: Possible Problems with the Plan (continued)
The tasks are structured badly.
  Most tasks are not complete until the work is complete.
  Tasks are like time buckets, i.e. project management.
How is this likely to affect the team’s status?
What should the team do about this?
B
start
done
A
C
D
B
start
done
A
C
D
instead
of
Notes: Explain the point, then ask the class the questions.
  the team will be achieving task hours but not earned value
  redo the plan so they can track the work

## Slide 14: Possible Problems with the Plan (continued)
Tasks are too large.
  Effort estimates for single tasks are much larger than 10 hours.
  Actual time for completed single tasks is much larger than 10 hours.
How is this likely to affect the team’s status?
What should the team do about this?
B
start
done
A
B
start
done
A
C
D
instead
of
Notes: Explain the point and ask the class the questions.
  team will achieve task hours but earned value will come in BIG chunks, won’t have accurate status
  break the tasks down to smaller increments

## Slide 15: Identifying Estimating Problems
The cost performance index (CPI) shows how the team is performing with respect to the effort estimates in the plan.
The CPI is available on the WEEK form.
TSP Week Summary - Form WEEK
Name
Date
2/7/2000
Team
Status for Week
5
Cycle
Week Date
1/31/2000
Plan/
Weekly Data
Plan
Actual
Actual
Project hours for this week
80.0
69.0
1.16
Project hours this cycle to date
400.0
344.8
1.16
Earned value for this week
10.3
3.1
3.37
Earned value this cycle to date
40.2
30.0
1.34
To-date hours for tasks completed
293.0
303.8
0.96
Consolidated Team Plan
Security System Upgrade
Notes: This is the first of the slides explaining how to identify if estimating or task hours is a problem.
This one and the next 2 slides cover estimating accuracy and how it affects the plan/schedule.

## Slide 16: Interpreting the CPI
A CPI of 1 means
What does this imply about the accuracy of the individual estimates?
Assuming the team is achieving the planned task hours, what does this imply about schedule performance?
What does a CPI of 0.5 imply about
  effort estimates?
  schedule performance (assuming the team is achieving the planned task hours)?
=
sum of the effort estimates
for the completed tasks
sum of the actual effort
for the completed tasks
Notes: This is a class discussion slide.
Ask each question and then discuss with the class what the answer is.
CPI of 1 implies that the task estimates are balance around 0 error, or on balance the team is doing very good on the task estimates.
If the team members are achieving their planned hours, the team should finish on schedule.
A CPI of 0.5 implies that on balance, the team’s estimates were low by 100% or it took twice as long to do the work as estimated.
A CPI of 0.5 implies it will take twice as long as the team estimated, assuming the team is achieving it’s planned task hours each week.

## Slide 17: Interpreting the CPI (continued)
What does a CPI of 2 imply about
  effort estimates?
  schedule performance (assuming that the team is achieving the planned task hours)?
What general characterization can be made about schedule performance based on the CPI?
Schedule growth (due to effort estimates) = 1/CPI
Projected schedule = Original plan weeks/CPI
Notes: Note, this slide has animation. The last two lines do not show until the next mouse click.
CPI of 2 implies that on balance, the work is taking half the effort estimated and that the team will finish in half the original planned time (assuming the effort distribution is constant).

## Slide 18: Interpreting Task Hour Data
The task hour data is in the form WEEK and can be interpreted similar to the effort for completed tasks data.
If (Plan hours to date)/(Actual hours to date) = 2
  What does it mean?
  What is the effect on schedule performance?
TSP Week Summary - Form WEEK
Name
Date
2/7/2000
Team
Status for Week
5
Cycle
Week Date
1/31/2000
Plan/
Weekly Data
Plan
Actual
Actual
Project hours for this week
138.0
69.0
2.00
Project hours this cycle to date
689.6
344.8
2.00
Earned value for this week
10.3
3.1
3.37
Earned value this cycle to date
80.4
30.0
2.68
To-date hours for tasks completed
293.0
303.8
0.96
Consolidated Team Plan
Security System Upgrade
Notes: Ask the class what this means and what it’ impact is on the team’s schedule (assuming the team’s CPI is 1).
  the team has half the planned hours
  the work will take twice as long as planned

## Slide 19: Interpreting Task Hour Data (continued)
If (Plan hours to date)/(Actual hours to date) = 0.5
  What does it mean?
  What is the effect on schedule performance?
What general characterization can be made about schedule performance based on the plan/actual task hours?
Schedule growth (due to task hours) = plan/actual
Projected schedule = Original plan weeks * (plan/actual)
Notes: This slide is a continuation from the last slide.
What does plan/actual hours of 0.5 mean?
  team has work twice as many hours as planned
  team will finish in half the scheduled time (assuming they continue at this pace)

## Slide 20: Combined Effect
The combined effect on schedule performance is
schedule growth =
Note: schedule growth computed this way is usually less than that indicated with earned value.
  What could cause that?
  Is it a problem?
plan/actual project task hours
plan/actual hours for completed tasks
TSP Week Summary - Form WEEK
Name
Date
2/7/2000
Team
Status for Week
5
Cycle
Week Date
1/31/2000
Plan/
Weekly Data
Plan
Actual
Actual
Project hours for this week
138.0
69.0
2.00
Project hours this cycle to date
689.6
344.8
2.00
Earned value for this week
10.3
3.1
3.37
Earned value this cycle to date
80.4
30.0
2.68
To-date hours for tasks completed
293.0
303.8
0.96
Consolidated Team Plan
Security System Upgrade
Notes: Schedule growth computed with this way is less than the earned value projection because of the uncompleted task hours. EV gives the team no credit for work started but not completed. Both projections would be the same if the uncompleted task hour were zero.

## Slide 21: Maintaining the Plan Exercise
Form groups of 3 to 5 people and take 20 minutes to decide how to answer these questions.
  How badly exposed is the project’s schedule?
  What is the cause of the schedule problem?
  What should be done about the problem?
Be prepared to give a 5-minute summary to present your conclusions and why you decided as you did.
Notes: This exercise is a direct application of the lecture concepts and the exercise data was shown on some of the earlier slides. So this should be a very straightforward exercise for the class.

## Slide 22: Messages to Remember
Managing with data requires that individuals follow the process and collect the required data.
In the weekly team meeting, the team uses its data to determine
  how it is doing against its plan
  how it can maintain its commitment to management