## Slide 1
Managing TSP Teams
Module 4: Building Self-directed Teams

## Slide 3: Module Overview
Software teams
Self-directed teams
The TSP process
TSP results

## Slide 4: A Software Product is a Team Effort
Software products are made from software modules or components.
These modules are designed, built, integrated, and tested by a team of software developers.
The team’s skills, spirit, discipline, and commitment govern the results.

## Slide 5: Successful Team Practices
When development teams work well, they generally have successful projects.
To be successful, teams need
  clear goals
  established roles
  defined processes
  agreed-upon plans
Teams also must be motivated and personally committed.
Without these, teams will rarely be successful.

## Slide 6: Self-directed Teams -1
Traditional team
The leader plans, directs,
and tracks the team’s
work.
Self-directed team
The team members participate
in planning, managing, and
tracking their own work.

## Slide 7: Self-directed Teams -2
Self-directed teams
  are attacking important problems
  have aggressive but realistic goals
  work to defined plans and processes
The team members
  are skilled and trained for the job
  know their roles and responsibilities
  are personally committed to the work
Because the team members are in control of their own work, they are motivated to do a superior job.
The TSP builds self-directed teams.

## Slide 8: Building Self-directed Teams
Self-directed teams must be built.
This requires a team-building process.
Team
Member
Skills
Team
Building
Team
Management
Process discipline
Performance measures
Estimating & planning skills
Quality management skills
Goal setting
Role assignment
Tailored team process
Detailed and balanced plans
Team communication
Team coordination
Project tracking
Risk analysis
PSP
TSP

## Slide 9: The TSP Launch
In the four-day TSP team-building process, teams
  establish their own goals and roles
  define their own strategies and processes
  produce their product development plans
  defend their plans to management
TSP teams
  own their own processes and plans
  understand why their goals are important
  have voluntarily committed to their goals
  believe that their commitments are achievable
All team members participate in the launch.

## Slide 10: TSP Process Structure
TSP projects can start on any phase or cycle.
Each phase or cycle starts with a launch or re-launch.
The strategy is to
  develop in increments
  use multiple cycles
  work-ahead
TSP permits whatever process structure makes the most business and technical sense.
Phase or cycle
Postmortem
Development
phase
or cycle
Launch
Re-launch
Project
Postmortem

## Slide 11: The TSP Launch Process
Day 1
1. Establish
product and
business
goals
2. Assign roles
and define
team goals
Day 2
4. Build overall
and
near-term
plans
5. Develop
the quality
plan
6. Build individual
and
consolidated
plans
Day 3
7. Conduct
risk
assessment
8. Prepare
management
briefing and
launch report
Launch
postmortem
Day 4
9. Hold
management
review
3. Produce
development
strategy
and process
A qualified TSP team coach guides the team through a defined process to develop its plan and to negotiate that plan with management.

## Slide 12: TSP Launch Meeting 1
In launch meeting 1, management
  describes what they want done
  explains why the job is important
  answers the team member’s questions
The objectives of meeting 1 are to
  motivate the team members to do this job
  ensure that the team understands management’s criteria for success

## Slide 13: TSP Launch Meetings 2 through 8
During the TSP launch, the team members
  define a process and strategy for doing the job
  produce detailed team and personal plans
  assess the risks of their plans
  present their plans to management
Because the team and team leader have a great deal to do during the launch, they
  are guided by a trained TSP coach to help them focus on building the plan
  work without observers

## Slide 14: TSP Launch Meeting 9
In launch meeting 9, the team presents its plan.
  This will be the best plan that the team knows how to make.
  If the members do not see how to meet management’s objectives, they present alternative plans.
Management’s responsibilities in meeting 9 are to
  probe the team’s plan
  assess the plan’s accuracy and completeness
  approve the plan if it is suitable

## Slide 15: TSP Launch Meeting 9 (cont.)
Team plans rarely meet all of management’s objectives.
When this occurs, managers must
  identify the most suitable alternate plan
  suggest other choices if no suitable plan is available
At the meeting’s conclusion, management
  decides how to proceed
  tells the team its decision
  explains why they made the decision
  thanks the team members for their work

## Slide 16: TSP Team Operation
Following the launch, the team does the job.
  follows its plans
  tracks the work
  regularly assesses project risks
  reports to management on status and progress
For longer jobs, TSP teams periodically relaunch their projects.

## Slide 17: The TSP Relaunch
Teams can make detailed plans only for about three to six months.
Longer-range plans are rarely accurate enough to guide development work.
A relaunch is needed to
  update the plan based on new knowledge
  make new detailed plans
The relaunch is similar to the launch process.

## Slide 18: TSP Users
The TSP is used by a growing number of organizations, such as
ABB
AIS
Bechtel
Boeing
Census Bureau
Comnet
EDS
Ericsson
Honeywell
IBM Japan
Intuit
Kaiser
Litton
Microsoft
NASA Langley
SAIC
SDRC
Teradyne
Trilogy
United Defense
USAF: Hill AFB
USN: China Lake
USN: NAVOCEANO
Xerox

## Slide 19: TSP Performance Summary -1
Performance Category | TSP Impact Study (2003)* | Typical Industry Performance (Standish Group)**
Schedule error average | 6% | 
Schedule error range | -20% to +27% | 
* From a study of 20 projects in 13 organizations conducted in 2003
** Of the unsuccessful projects, average schedule error was 222%

## Slide 20: TSP Performance Summary -2
Performance Category | TSP Impact Study (2003)* | Typical Industry Performance
System test defects per thousand instructions | 0.4 avg. 0.0 to 0.9 | 2 to 14
Released defects per thousand instructions | 0.06 avg. 0.0 to 0.2 | 1 to 7
System test effort (% of total effort) | 4% avg. 2% to 7% | 40%
* From a study of 20 projects in 13 organizations conducted in 2003

## Slide 21: TSP Performance Comparison*
*From a study of 18 TSP projects in four organizations conducted in 2000

## Slide 22: Process Improvement Pays Off

## Slide 23: Predictable Schedules
CMM introduced
TSP introduced
[Source: AIS]

## Slide 24: A TSP Industrial Project
Plan Actual
Size estimate 110,000 LOC 89,995 LOC
Effort estimate 16,000 hours 14,711 hours
Schedule 77 weeks 71 weeks
Product quality (Defects/KLOC removed in phase)
  Integration 1.0 0.2
  System test 0.1 0.4
  Field trial 0.0 0.02
Benefits
  Quality levels improved 20 times over prior projects.
  Actual effort and schedule were within 8% of plan (early).

## Slide 25: Team-Member Comments
With proper support, TSP developers can produce extraordinary results.
Developers like to use the TSP:
“This really feels like a tight team.”
“The TSP forces you to design, to think the whole thing out.”
“Design time is way up but code time decreased to compensate.”
“Tracking your time is an eye opener.”
“Really good teamwork on this project - no duplication of effort.”
“I’m more productive.”
“Gives you incredible insight into project performance.”
“Wonderful to have team members assigned specific roles.”
“Team really came together to make the plan.”
“I feel included and empowered.”

## Slide 26: Messages to Remember
To be successful, teams need
  clear goals and roles
  agreed-upon processes and plans
On self-directed teams, the members
  own their own processes and plans
  understand their goals and roles
  voluntarily commit to their goals
  believe their commitments are achievable
The TSP launch builds self-directed teams.
Notes: Go around the room and have everyone explain who they are and what their objectives are. Record the objectives on flip charts.