## Slide 1
Managing TSP Teams
Module 5: Managing with Facts and Data

## Slide 3: Module Overview
Managing self-directed teams
Rational management
  set challenging goals
  get the facts
  use facts and data
  anticipate and address problems
Process discipline
Rewarding quality work

## Slide 4: Managing Self-directed Teams
Team
Member
Skills
Team
Building
Team
Management
Process discipline
Performance measures
Estimating & planning skills
Quality management skills
Goal setting
Role assignment
Tailored team process
Detailed balanced plans
Team communication
Team coordination
Project tracking
Risk analysis
Team Performance
PSP
TSP
Senior
Management
Team support
Team discipline
Program visibility
Capitalizing on
team potential
is management’s
responsibility.

## Slide 5: Management Direction
Teams are very responsive.
  They will try to do whatever you want.
  Without guidance, they will do what they think you want.
  That may not be what you really want.
If you stress schedule above everything else, teams will
  strive to meet aggressive dates
  shortchange the process
  take more time than following the process
Doing the job the right way is, in the end, always the fastest and cheapest way.

## Slide 6: Rational Management
Rational management is the most effective way to manage TSP teams.
Rational management has four elements.
  setting aggressive but realistic goals
  getting the facts
  using facts and data to make decisions
  monitoring team performance to anticipate and address problems

## Slide 7: Aggressive but Realistic Goals
Everyone knows what an aggressive goal is, but what is a realistic goal?
A realistic goal is one that the team members see how to meet.
  They have made a plan to meet the goal.
  They are willing to commit to this plan.
To ensure that the goal is realistic, probe the team’s plan to ensure that it
  is detailed and complete
  is based on historical data
  considers the key risks

## Slide 8: Negotiating Realistic Schedules
When teams say that they cannot meet a date, that date is unrealistic.
If you insist that the team meet that date, there is little if any chance that the team will do so.
Irrational management has several consequences.
  Teams cannot make believable plans.
  They do not believe the plans that they have.
  They are not motivated to meet management’s dates.
  Their jobs take longer than they would with a realistic plan.

## Slide 9: Getting the Facts
The TSP provides many kinds of data.
A full assessment of project status must include schedule and quality data.
With the task hour and earned value (EV) measures, teams can precisely determine schedule status.
They can also estimate when they will likely finish the job.

## Slide 10: Task Hours
Task hours are the hours that the team spends on planned tasks.
Task hours do not include many unplanned but necessary tasks.
  meetings
  courses
  task coordination
  advice and assistance
  handling mail, supplies, expenses, etc.
Teams can estimate task hours, but planning the other activities is guesswork.
When measured, tracked, and managed, task hours can often be improved.

## Slide 11: Improving Task Hours
Average task hours per developer per week were improved from
9.6 hours to 15.1 hours through quiet time, process documentation, more efficient meetings, etc.
+57%
Source: Allied Signal

## Slide 12: Managing Task Hours
Task hours can only be improved by the developers.
To do so, they need management support.
Improving weekly task hours directly improves team productivity.
Task hour improvement costs little or nothing.

## Slide 13: Earned Value
A task’s earned value (EV) is the percentage of the total estimated project hours that the task is planned to take.
  EV values each task, regardless of type.
  EV is earned when the task is completed.
  There is no partial credit.
  The EV credit is the same, regardless of the time the task actually takes.
EV provides a precise way to
  measure project status
  estimate project completion dates

## Slide 14: Earned Value Example -1
A 10-person team estimates that the first development cycle of a job will take 1,000 task hours.
The team’s top-down plan breaks the work into 5 phases.
The task hour estimates for these first-cycle phases are as follows.
  requirements development: 165 hours
  high-level design (HLD): 150 hours
  detailed design (DLD): 220 hours
  implementation: 250 hours
  testing: 215 hours

## Slide 15: Earned Value Example -2
The planned value (PV) is the value in the plan.
This value is earned (EV) only on task completion.
The Cycle 1 Task Plan
Task Cycle 1 Task Cumulative PV Cumulative
No. Tasks Hours Task Hours PV
1 Requirements 165 165 16.5 16.5
2 HLD 150 315 15.0 31.5
3 DLD 220 535 22.0 53.5
4 Implementation 250 785 25.0 78.5
5 Testing 215 1,000 21.5 100.0

## Slide 16: Earned Value Example -3
The Cycle 1 Schedule Plan
Week Plan Cumulative PV Cumulative
No. Hours Plan Hours PV
1 160 160 0.0 0.0
2 160 320 31.5 31.5
3 160 480 0.0 31.5
4 160 640 22.0 53.5
5 160 800 25.0 78.5
6 160 960 0.0 78.5
7 160 1,120 21.5 100.0
8 160 1,280 0.0 100.0

## Slide 17: Project Tracking Example -1
After four weeks, the work has taken longer than expected.
  The team finished the requirements in 218 hours instead of the planned 165 hours.
  High-level design took 186 hours instead of 150.
  The detailed design is partially completed.
  The team members are confident they will finish it in a day or two.
What is the estimate for project completion?

## Slide 18: Project Tracking Example -2
As tasks are completed, their EV is entered for the week earned.
When is the project likely to finish?
Schedule Planning Template
Week Plan Actual Cumulative Cumulative Cumulative
No. Hours Hours Actual Hours PV EV
1 160 126 126 0.0 0.0
2 160 148 274 31.5 16.5
3 160 156 430 31.5 31.5
4 160 163 593 53.5 31.5
5 160 78.5
6 160 78.5
7 160 100.0
8 160 100.0

## Slide 19: Project Tracking Example -3
The team gets no credit for partially completed work.
The developers have earned 31.5 EV in 4 weeks, or 7.875 EV per week.
There are 100-31.5 = 68.5 EV to go.
At 7.8754 per week, that is 8.7 more weeks.
Added to the 4 weeks spent so far, that is 12.7 weeks.
At the current rate of progress, the team will be 5.7 weeks late.

## Slide 20: Project Tracking Considerations
With more detailed plans, status can be more precisely measured.
With more precise status information, completion projections are more accurate.
More accurate completion projections will help you manage the business.

## Slide 21: Business Implications
With PSP training, developers know how to plan, schedule, and track their work.
TSP teams use these PSP-learned methods to make detailed plans.
  Tasks are no more than 10 task hours each.
  Task time is recorded daily.
  EV is measured weekly.
You can tell project status to within 10 task hours.
TSP teams regularly report their status.

## Slide 22: Using Facts and Data
Project schedules slip a day at a time.
If you cannot precisely measure project status, you will not know where projects stand.
Without such knowledge, you cannot address schedule problems in time to fix them.
With the TSP, you can
  closely monitor team performance
  address problems in time
  consistently meet schedules

## Slide 23: Gathering Data
For precise project management, teams need precise project data.
These data must be gathered by the developers.
To do so, they must be
  properly trained
  suitably led
A qualified TSP coach can help teams and team leaders gather and use their TSP data.

## Slide 24: Data Sensitivity
Personal data are sensitive.
  Productivity varies among individuals.
  People have off days.
  Mistakes are always embarrassing.
If the developers feel that their personal data could be used against them, they will not gather that data.
Only use aggregate team data to manage TSP projects.
If management respects the developers’ data, data privacy will not be an issue.

## Slide 25: Hold Regular Project Reviews
Periodic project reviews help you to
  understand project status
  identify impending problems
  expose poor work
  recognize superior work
Regular reviews also help teams by
  showing continued management interest
  reinforcing your desire for quality work
  maintaining the team’s motivation
  identifying areas where the team needs help

## Slide 26: Reward Quality Work
When organizations reward the firefighters, they have lots of fires.
Unless management recognizes and rewards quality work, the developers and teams who quietly do such work will
  soon become invisible
  be passed over in promotions
  get discouraged and leave
Search for and reward those who do the highest quality work.

## Slide 27: Messages to Remember
To get the best performance, teams must
  make detailed plans
  follow their processes and plans
  gather and use data
  manage quality
To consistently do this, they must be rationally managed.
For your teams to perform at their best
  require that the teams gather and use their data
  use only team-level data
  regularly review the work
  reward quality work
Notes: Go around the room and have everyone explain who they are and what their objectives are. Record the objectives on flip charts.