## Slide 1
Managing TSP Teams
Module 8: Leading and Coaching TSP Teams
Notes: The course name line should be placed so that the bottom of the letters in the title are sitting on the horizontal guideline setting 1.24. Module number and title should be placed so that the bottom of the text letters are sitting on the horizontal guideline setting 0.00 (horizontal center of slide). If the module number/title line is so long that is wraps to two lines, nudge the text upward so that the bottom of the letters in the FIRST line of the module title is sitting on horizontal guideline setting 0.30.
2. The left margin is at vertical guideline 3.91 (left of center). The left edge of the text should touch this guideline.
3. Font setting for “Course Name” line is Arial Narrow, 32 points, bold. Font for the “Module” line is Arial Narrow, 45 points, bold. This information is on the slide body. The “distribution limited” and sponsorship statements are on the master slide. The font convention for these elements is Ariel, 16 points, bold. The footer information is Ariel, 10 points, bold.
4. Always change the month and year information in the footer (title master, slide master) if changes are made to the course material. This includes minor modifications such as correcting typos. Use the month and year in which the changes were made. Change the footers ONLY on modules that were actually changed. If necessary, change the copyright dates (title master, slide master) to the current year’s date.

## Slide 3: Objectives: Days Two and Three
To recognize how to lead and coach individuals using the PSP
  the PSP process framework
  the PSP planning framework
  conceptual design and PROBE
  size and time estimating
  scheduling and earned value
To recognize how to lead and coach TSP teams
  maintaining the team
  maintaining plans
  maintaining quality

## Slide 4: Module Overview
Team leader responsibilities
Building self-directed teams

## Slide 5: The Team Leader Role
The team leader’s primary responsibility is to get the project done.
  The product must be delivered on schedule for its planned costs.
  The product must meet its stated and implied requirements.
Team leaders direct the work, rather than doing it.
The team’s performance governs the quality of the final product.
The team leader’s performance governs the environment in which the team functions.
Notes: I use this slide to make the point that the team leader cannot do the job themselves, but must motivate and encourage a team to do the job. This is hard for most team leader’s because they have been promoted because of their ability to get things done. Now they must focus on a new skill of getting others to get the job done.

## Slide 6: Self-Directed Teams
TSP team leaders create a cohesive and cooperative environment by building and maintaining self-directed teams.
Self-directive teams have the following characteristics.
  sense of membership and belonging
  commitment to a common team goal
  ownership of the process and plan
  the skill to make a plan and the discipline to use it
  dedication to excellence

## Slide 7: The TSP Launch
The TSP launch is the mechanism for establishing the conditions for a self-directed team.
  The launch workshop accelerates team-building.
  The team establishes a common understanding of the work and the approach it will use.
  The team makes a plan to which it can commit and obtains management support for that plan.
All team members are trained in the PSP prior to the launch.
Notes: This set of slides on the launch is here because by this time in the course, team leaders have lots of questions about the launch and the instructors need to go into more detail than is provided in day 1 for the team leaders.
Pt – put the team under stress, creates a sense of belonging through roles, etc.

## Slide 8: The Launch Process Meetings
Day 1
1. Establish
product and
business
goals
2. Assign roles
and define
team goals
Day 2
4. Build top-
down and
next-phase
plans
5. Develop
the quality
plan
6. Build bottom-
up and
consolidated
plans
Day 3
7. Conduct
risk
assessment
8. Prepare
management
briefing and
launch report
Launch
postmortem
Day 4
9. Hold
management
review
3. Produce
development
strategy
and process

## Slide 9: Establish Product and Business Goals
The first step in the launch is for the team to understand what they are being asked to do.
In meeting 1, management and marketing meet with the team to tell the team
  what they want the team to develop
    essential features
    nice-to-have features
  when the product is needed
  what resources the team has
  what flexibility the team has
  why this job is important
  how management will measure success

## Slide 10: Establish Team Goals
In launch meeting 2, the team sets its goals and organizes itself.
The team starts with the goals defined by management.
  reviews and refines management’s goals
  adds team-specific goals

## Slide 11: Organize the Team -1
Self-directed teams manage their own work.
This responsibility must be shared.
Traditional project management responsibilities are distributed among eight team roles.
  customer interface manager
  design manager
  implementation manager
  test manager
  planning manager
  quality manager
  process manager
  support manager

## Slide 12: Organize the Team -2
Each team member assumes the responsibility for at least one team management role.
Defined roles
  ensure that key areas are covered
  give each team member a responsibility in running the team
  build a sense of membership and ownership among the team members
  free the team leader to focus on the role of coaching and leading the team

## Slide 13: Define the Work and the Approach
In meeting 3, the team accomplishes three important prerequisites to building the team plan.
  identifies all of the “work” the team needs to do
  identifies the “build strategy” the team will use to develop the software
  identifies or defines the “processes” the team will follow to do the work
Project strategy
Process, support
List of products
Cyclic strategy
Conceptual
design

## Slide 14: Build the Overall Plan
In launch meeting 4, the team creates the overall plan.
  the estimated sizes of the products to be produced (how big is the job)
  the tasks needed to do the work (with effort estimates)
    next-phase tasks, detailed to the work step level
    later phases at a high level
  the estimated team hours available each week for the work
  an initial schedule for the project
The team may consider alternative plans if management goals are not met.
Overall plan
Available time
Estimate resources
Define tasks
Estimate size

## Slide 15: Build a Quality Plan
In launch meeting 5, the team builds a quality plan that estimates the
  number of defects that will be injected in each phase
  number of defects that will be removed in each phase
  quality (defect density) of the final product
  quality (process quality index) of the development process
The team ensures that the plan meets the quality goals.
Quality plan
Quality goals
Defects injected
Defects removed

## Slide 16: Build Individual Work Plans
In launch meeting 6, the team allocates tasks to the team members, who build individual work plans for their tasks for the next phase.
In building their plans, the engineers
  refine size and effort estimates using their own data and processes
  break tasks to the granularity of around 10 task hours per task or less
  estimate their own available task hours for each week
  create an earned-value plan
The team reviews individual plans and balances workloads across all team members.
Balanced
plan
Allocate tasks
Individual plans
Balance workload

## Slide 17: Build a Consolidated Team Plan
The individual team-member plans for the next project phase are consolidated into a single team plan that contains a
  task list of all individual tasks with
    estimated hours
    planned date
    planned value
  schedule with
    planned team hours per week
    planned team earned value per week
The team uses this plan to guide and track its work during the next project phase.

## Slide 18: Identify Risks and Mitigation Strategies
In launch meeting 7, the team identifies and assesses risks to the team meeting its plan.
The risks are documented in the team’s plan.
Risks are assigned to team members to track during the project.
The team identifies mitigation and recovery strategies for high-priority risks.

## Slide 19: The TSP Launch Products
What?
How?
When?
Who?
How well?
What if?
Business needs Management goals Product requirements
Team goals
Conceptual design
Planned products
Size estimates
Team strategy
Team defined process
Team roles
Task plans
Earned-value Plan
Task plan
Schedule Plan
Earned-value Plan
Quality plan
Risk evaluation
Alternate plans

## Slide 20: Prepare Management Briefing
In launch meeting 8, the team prepares a presentation on the plan for management.
If the team’s plan does not meet management’s goals, the team generates alternate plans to come closer to or meet management’s goals by
  adding more resources
  delivering a reduced-functionality initial version, followed later by a full-functionality version(s)

## Slide 21: Management Review of the Plan
In launch meeting 9, the team presents its plan (and alternatives, if any) to management and answers questions.
Management determines whether
  the plan is based on sound estimates, historical data, and a quality process
  the team believes in their plan
  the plan or an alternative meets the business need
Management
  approves the plan or an alternative
  asks the team to look at a different alternative

## Slide 22: The Team Leader’s Role in Planning
The team leader acts as a facilitator. He or she
  takes the time to reach full consensus on all important issues
  ensures that adequate resources are available
  elevates issues and concerns up the management chain, as needed
  coaches the team, as needed
  does not monopolize the planning meetings
  allows the team to do the planning
  encourages all team members to participate
  looks for signs of resistance and tries to bring issues to the surface
Notes: On the first, bullet. The team leader must also agree with the plan. If the team leader thinks the team is making a bad decision, the team leader should make the team convince them that the team is right.

## Slide 23: Team Management
The TSP launch process will help you to build
  a committed team
  a plan that the team owns
Next, you must motivate the team to work that plan and to use the process to do their jobs the best way that they can.
Team leaders must now focus on the following areas.
  coaching individual team members (modules 8-13)
  maintaining the team (module 14)
  managing to the plan (module 15)
  maintaining a quality focus (module 16)

## Slide 24: Coaching Individuals
The performance of the team
depends on the performance
of the individual members.
The remainder of today
will focus on the PSP
and individual coaching.
Tomorrow will we
cover coaching
Teams.
Team
Member
Skills
Team
Building
Team
Management
Process discipline
Performance measures
Estimating & planning skills
Quality management skills
Goal setting
Role assignment
Tailored team process
Detailed and balanced plans
Team communication
Team coordination
Project tracking
Risk analysis
PSP
TSP

## Slide 25: Messages to Remember
The TSP achieves high performance by building and maintaining self-directed teams.
The team leader’s focus is on creating and maintaining a cooperative and cohesive team environment.