## Slide 1
Managing TSP Teams
Module 9: PSP Planning - PROBE Part I
Notes: The course name line should be placed so that the bottom of the letters in the title are sitting on the horizontal guideline setting 1.24. Module number and title should be placed so that the bottom of the text letters are sitting on the horizontal guideline setting 0.00 (horizontal center of slide). If the module number/title line is so long that is wraps to two lines, nudge the text upward so that the bottom of the letters in the FIRST line of the module title is sitting on horizontal guideline setting 0.30.
2. The left margin is at vertical guideline 3.91 (left of center). The left edge of the text should touch this guideline.
3. Font setting for “Course Name” line is Arial Narrow, 32 points, bold. Font for the “Module” line is Arial Narrow, 45 points, bold. This information is on the slide body. The “distribution limited” and sponsorship statements are on the master slide. The font convention for these elements is Ariel, 16 points, bold. The footer information is Ariel, 10 points, bold.
4. Always change the month and year information in the footer (title master, slide master) if changes are made to the course material. This includes minor modifications such as correcting typos. Use the month and year in which the changes were made. Change the footers ONLY on modules that were actually changed. If necessary, change the copyright dates (title master, slide master) to the current year’s date.

## Slide 3: Module Overview
Plans
Planning framework
PSP estimating method

## Slide 4: The PSP Process Flow
Requirements
Process
scripts
Project
plan
summary
Finished product
Project and process
data summary report
Time
and
defect
logs
PSP Process
Development
Planning
Design
Code
Compile
Test
Design review
Code review
Postmortem
guide
Notes: 27
Make a plan, with an estimate of development time and size, and record on the project plan summary
Develop the product using current methods
Complete the project plan summary by entering the time spent, the defects injected per phase, and the defects found per phase
Development includes these steps:
  design the program
  implement the design
  compile the program until it is defect free
  test the program and fix all defects
During the process, record all defects found in the defect log and the time spent per phase in the time recording log

## Slide 5: Planning Phase
Historical size,
time, and defect data
Requirements
Planning
Project plan summary
Updated
defect and
time logs
Size estimate
Task and
schedule

## Slide 6: The PSP Planning Framework
Define
requirements
Produce
conceptual
design
Estimate
size
Estimate
resources
Produce
schedule
Develop
product
Size, resource
schedule
data
Process
analysis
Resources
available
Productivity
database
Size
database
Customer
need
Product
delivery
Tracking
reports
Customer
Management
Items
Tasks
Notes: 14

## Slide 7: The PROBE Estimating Method
Conceptual
design
Identify and size objects
Number of
methods
Object
type
Relative
size
Reuse
categories
Estimate other LOC
Estimate
program size
Calculate
prediction interval
Size estimate
Estimate
resources
Calculate
prediction interval
Resource estimate
Step

## Slide 8: Size Estimating Template
The PROBE estimate is recorded on the size estimating template.
This form holds estimates for
  base LOC
  new objects
  reused objects
  program size estimate
  total development time

## Slide 9: Conceptual Design -1
The conceptual design
  relates the requirements to the product
  defines the product elements that will produce the desired functions
  is needed to estimate the size of what will be built
The engineer uses judgement to identify the product elements.
Requirements:
Write a program to calculate mean and standard deviation.

## Slide 10: Conceptual Design -2
The conceptual design is not detailed.
In essence, an engineer says, “If I had the following objects, I would know how to build this.”
For understood designs, conceptual designs can be done quickly.
If engineers do not understand the design, they do not know enough to make an estimate.
Requirements:
Write a program to calculate mean and standard deviation.
main()
Input data
Linked list
Calc. mean
Calc. SD
Print result

## Slide 11: Identify and Size Objects -1
To estimate the new objects’ sizes, engineers relate the objects in the conceptual design to previously-built objects, using a relative size table.
The relative size table was constructed earlier, using a size database of previously-built objects, divided into types (calculation, data, I/O, logic, set-up, and text) and broken into relative sizes.

## Slide 12: Identify and Size Objects -2
Engineers review their conceptual designs, identifying the types and relative sizes for each object, and record this on the size estimating template in the new object or the base additions section.
Object Type Size LOC
Input_Data I/O M
Calc_Mean Calc M
Calc_SD Calc L
Print_Result I/O M
Linked_List Data M
main()
Input data
Linked list
Calc. mean
Calc. SD
Print result

## Slide 13: Identify and Size Objects -3
Next, engineers determine the LOC estimate for each object in the conceptual design by referring to their relative size table and selecting for each object the LOC that corresponds to its type and relative size.
Note: if an object has more than one method, the LOC in the table must be multiplied by the number of methods to get the object LOC estimate.
Object Type Size LOC
Input_Data I/O M 16
Calc_Mean Calc M 11
Calc_SD Calc L 25
Print_Result I/O M 16
Linked_List Data M 44
main()
Input data
Linked list
Calc. mean
Calc. SD
Print result

## Slide 14: Estimating Other LOC
After identifying and sizing new objects, the other LOC are estimated.
  base code used from an earlier program
  deletions and modifications to the base code
  additions to the base code
    code additions to existing base objects/methods
    methods added to existing base objects
  reused code

## Slide 15: Messages to Remember
The PSP shows engineers how to estimate and plan their work.
The keys to making good estimates and plans are to use
  relevant historical data
  statistically sound methods
PROBE is a statistically sound method for estimating project size and resources.