## Slide 1: Personal Software ProcessSM for Engineers: Part I Resource and Schedule Planning
Notes: <number>

## Slide 3: Lecture Topics
Resource and schedule planning overview
The planning process
Resource estimating
Combining estimates
Schedule estimating
Earned value tracking
Notes: <number>

## Slide 4: The Need for Resource and Schedule Plans
Plans provide a business basis for doing the work. They
  establish the price
  set the schedule
  permit agreement on the work
Plans establish a management framework. They
  define commitments
  help groups to coordinate their work
  allow status tracking
Notes: <number>

## Slide 5: Estimating Accuracy
Planning is a skill that must be developed.
  The PSP helps to build planning skill.
  Even simple plans are subject to error.
    unforeseen events
    unexpected complications
    just plain mistakes
The best strategy is to plan in detail.
  Identify the recognized tasks.
  Make estimates based on similar experience.
  Make judgments on the rest.
Notes: <number>

## Slide 6: An Estimating Error Example
When estimating in parts, the total error is less than the sum of the part errors.
  Errors tend to balance out.
  This assumes no common bias.
For a 1000-hour job with estimating accuracy of ± 50%, the estimate range is from 500 to 1500 hours.
In 25 parts, each with 50% error, the
  total would be 1000 hours, as before
  estimate range is from 900 to 1100 hours
Notes: <number>

## Slide 7: Combining Individual Errors
To combine individual estimates
  Combine the estimated values.
  Add the estimate variances.
With 25 estimates
  Each estimate averages 40 hours.
  The standard deviation is 50%, or 20 hours.
  The variance for each is 400.
  The variances total 10,000.
  The combined standard deviation is the square root of the variance, or 100.
  The estimate range is 900 to 1100 hours.
Notes: <number>

## Slide 8
Size Estimating Error Range
-100
0
100
200
300
400
500
1
2
3
4
5
6
7
8
9
10
Program Number
% Error
Max
Class
Min
Notes: <number>

## Slide 9
Time Estimating Accuracy - %
Error
-100
0
100
200
300
400
500
1
2
3
4
5
6
7
8
9
10
Program Number
% Estimate Error
Max
Class
Min
Notes: <number>

## Slide 10: The Project Planning Framework
Product
delivery
Tracking
reports
Define
requirements
Produce
conceptual
design
Estimate
size
Estimate
resources
Produce
schedule
Develop
product
Size, resource,
schedule
data
Process
analysis
Resources
available
Size
database
Productivity
database
Notes: <number>

## Slide 11: Planning Development Time with PROBE
Do
you have
historical data?
(2)
Are there
sufficient estimated
object data?
(3)
No
Yes
Object LOC estimate (1)
Are there sufficient
data for regression?
(4)
Do the regression
calculation on estimated
new and changed LOC
and actual hours. (9).
Calculate the
time required.
(10)
Calculate the
prediction interval.
(11)
Time estimate
(12)
Calculate historical
productivity in LOC
per hour. (5)
Calculate the
hours required.
(6)
Estimate the shortest
and longest likely times.
(7)
Do the regression
calculation on estimated
object LOC and
actual hours. (13)
Calculate the
time required.
(14)
Calculate the
prediction interval.
(15)
Yes
No
No
Yes
Estimating
choice C
Estimating
choice B
Estimating
choice A
Estimating
choice D
judgment
Time estimate
(8)
Time estimate
(16)
Notes: <number>

## Slide 12: The Resource Planning Process
Start with a size estimate.
Identify the available data.
Use regression when you have three or more sets of data that correlate.
Use data for estimated LOC to actual hours, when available.
Calculate the prediction interval.
Notes: <number>

## Slide 13: Combining Resource Estimates
To combine multiple estimates from the same data
  Combine the parts; i.e., if three LOC estimates were made, combine their object LOC as input to one resource estimate.
  Do the same for the prediction interval.
Notes: <number>

## Slide 14: Example of Combining Resource Estimates
Start with three estimates.
  A = 45 hours, + or - 10
  B = 18 hours, + or - 5
  C = 85 hours, + or - 25
The combined estimate is
  total = 45 + 18 + 85 = 148 hours
  variance = 100 + 25 + 625 = 750
  range = square root of variance = 27.4 hours
  estimate = 121 to 175 hours
Notes: <number>

## Slide 15: Using Multiple Proxies
With size/hour data for several proxies
  Estimate each as before.
  Combine the total estimates and prediction intervals as just described.
Use multiple regression if
  there is a correlation between development time and each proxy
  the proxies do not have separate size/hour data
Multiple regression is covered later.
Notes: <number>

## Slide 16: Schedule Estimating
To make a schedule, you need three things.
  the estimated direct project hours
  a calendar of available direct hours
  the order in which the tasks will be done
Then, you need to
  estimate the hours needed for each task
  spread these hours over the calendar of available hours
Notes: <number>

## Slide 17: Available Direct Hours
Staffing schedule
  New projects are not instantly staffed.
  You need a committed staffing plan.
Produce a calendar spread of available hours.
  at 52 weeks a year and 40 hour weeks, one year = 2080 hours
  with 3 weeks vacation and 10 holidays, one year = 1880 hours (90%)
  with 10% for meetings, 5% for mail, interrupts, one year  1000 to 1400 hours (50 to 65%)
Notes: <number>

## Slide 18: The Task Order
The task order must be driven by the development strategy.
  You need a conceptual approach.
  Each task needs completion criteria.
  You must consider task interdependencies.
  Also consider cost and cycle time priorities.
Determine the planned task order.
  The task order will change with new knowledge.
  The initial task order provides a basis for planning.
Notes: <number>

## Slide 19: Produce the Schedule
Estimate the hours that each task will take.
  What portion of total hours have such tasks historically taken?
  Will anything unusual affect this project?
  To ensure that tasks are not omitted, spread the task time for the entire project.
Spread the task hours over the calendar.
  Identify key project checkpoints.
  Use a standard format.
Notes: <number>

## Slide 20: Task Planning Template
The PSP task planning template is in table C47 (page 693).
To fill out this template
  List the tasks in their expected order of completion.
  Enter the hours that each task is expected to take.
  Add the hours in the cumulative hours column.
At this point, start to prepare the schedule planning template.
Notes: <number>

## Slide 21: Schedule Planning Template
The PSP schedule template is in table C49 (page 695).
To start filling out this template
  List the calendar dates in the left column.
  Use days or weeks, depending on project scale.
    For days, list every date.
    For weeks, use a standard day (say, Monday).
  List the planned direct project hours available each week.
  Add the hours in the cumulative hours column.
  Complete the task and schedule templates together.
Notes: <number>

## Slide 22: Completing the Plan
For each task
  Find the cumulative hours needed to complete that task on the task template.
  Find the week on the schedule template when those hours have first been exceeded.
  Enter the week’s date in the Date column for that task on the task template.
You now have the task schedule.
Notes: <number>

## Slide 23: Schedule Planning Example -1
Using table C47, start with an estimate of the hours per task.
Task Hours Cum. Hrs.
A 2 2
B 5 7
C 4 11
D 7 18
E 3 21
F 5 26
G 6 32
H 3 35
I 2 37
Notes: <number>

## Slide 24: Schedule Planning Example -2
Using table C49, estimate the direct hours available per day.
Day Hours Cum. Hrs.
1 3 3
2 5 8
3 5 13
4 5 18
5 4 22
6 6 28
7 5 33
8 5 38
Notes: <number>

## Slide 25: Schedule Planning Example - 3
Enter in the task schedule the day on which the cumulative hours for each task is reached.
Task Hours Cum. Hrs. Day
  A 2 2 1
  B 5 7 2
  C 4 11 3
  D 7 18 4
E 3 21 5
F 5 26 6
G 6 32 7
H 3 35 8
I 2 37 8
Notes: <number>

## Slide 26: Earned Value
The purpose of earned value is to
  establish a value for each task
  permit progress tracking against the plan
  facilitate tracking, even with plan changes
Principles behind earned value
  It provides a common value for each task.
  This value is the percentage of the total project hours that this task is planned to take.
  No value is given for partial task completion.
  Major plan changes require new plans.
Notes: <number>

## Slide 27: Establish the Planned Value
On the task template
  Add the number of project hours.
  Calculate the percentage that each task is of the total hours.
  Enter this percentage as the planned value (PV) for that task.
  Calculate the cumulative PV for each task.
On the schedule template, enter the cumulative planned value for the tasks to be completed each week.
Notes: <number>

## Slide 28: Earned Value Example -1
Next, produce the PV, or the percentage of the total job that each task represents.
Task | Hours | Cum. Hrs. | Day | PV | Cum. PV
A | 2 | 2 | 1 | 5.4 | 5.4
B | 5 | 7 | 2 | 13.5 | 18.9
C | 4 | 11 | 3 | 10.8 | 29.7
D | 7 | 18 | 4 | 18.9 | 48.6
E | 3 | 21 | 5 | 8.1 | 56.7
F | 5 | 26 | 6 | 13.5 | 70.2
G | 6 | 32 | 7 | 16.3 | 86.5
H | 3 | 35 | 8 | 8.1 | 94.6
I | 2 | 37 | 8 | 5.4 | 100.0
Notes: <number>

## Slide 29: Earned Value Example -2
Enter the cumulative planned value for each day.
Day Hours Cum. Hrs. Cum. PV
1 3 3 5.4
2 5 8 18.9
3 5 13 29.7
4 5 18 48.6
5 4 22 56.7
6 6 28 70.2
7 5 33 86.5
8 5 38 100.0
Notes: <number>

## Slide 30: Tracking the Plan
As each task is completed, it earns the planned value.
  Enter the earned value (EV) for that task.
  Enter the date of task completion.
  Add the EV to date in the cumulative EV column.
In the schedule template, enter the cumulative EV for each week as it is completed.
Track earned value versus planned value by week.
Notes: <number>

## Slide 31: Tracking the Plan Example -1
During the project, enter on the task planning template the day each task is completed.
Task | Hours | Cum. Hrs. | Day | PV | Cum. PV | Done
A | 2 | 2 | 1 | 5.4 | 5.4 | 1
B | 5 | 7 | 2 | 13.5 | 18.9 | 2
C | 4 | 11 | 3 | 10.8 | 29.7 | 4
D | 7 | 18 | 4 | 18.9 | 48.6 | 5
E | 3 | 21 | 5 | 8.1 | 56.7 | 
F | 5 | 26 | 6 | 13.5 | 70.2 | 
G | 6 | 32 | 7 | 16.3 | 86.5 | 
H | 3 | 35 | 8 | 8.1 | 94.6 | 
I | 2 | 37 | 8 | 5.4 | 100.0 | 
Notes: <number>

## Slide 32: Tracking the Plan Example -2
Also enter on the schedule template the earned value (EV) for each day.
Day Hours Cum. Hrs. Cum. PV EV
1 3 3 5.4 5.4
2 5 8 18.9 18.9
3 5 13 29.7 18.9
4 5 18 48.6 29.7
5 4 22 56.7 48.6
6 6 28 70.2
7 5 33 86.5
8 5 38 100.0
Notes: <number>

## Slide 33: Projecting Project Completion
Assume that the project will continue to earn value at the rate it has in the past.
Extrapolate to project completion by linearly extending the EV line until it reaches 100%.
This is the likely project completion date, unless
  the rate of progress can be accelerated
  work for the remaining tasks can be reduced below the original plan
Notes: <number>

## Slide 34: Projecting Project Completion Example -1
What is the actual EV per day?
Day Hours Cum. Hrs. Cum. PV EV Proj. EV
1 3 3 5.4 5.4 5.4
2 5 8 18.9 18.9 18.9
3 5 13 29.7 18.9 18.9
4 5 18 48.6 29.7 29.7
5 4 22 56.7 48.6 48.6
6 6 28 70.2
7 5 33 86.5
8 5 38 100.0
9
10
11
12
13
When should you expect to finish?
Notes: <number>

## Slide 35: Projecting Project Completion Example -2
Using the actual EV earned per day of 9.72, enter the EV by day to project completion.
Day Hours Cum. Hrs. Cum. PV EV Proj. EV
1 3 3 5.4 5.4 5.4
2 5 8 18.9 18.9 18.9
3 5 13 29.7 18.9 18.9
4 5 18 48.6 29.7 29.7
5 4 22 56.7 48.6 48.6
6 6 28 70.2 58.3
7 5 33 86.5 68.0
8 5 38 100.0 77.8
9 87.5
10 97.2
11 100.0
Notes: <number>

## Slide 36: Changing the Plan
The plan is still tracked against the original planned value schedule.
  By adding a task, the value of all the completed and planned tasks is reduced.
  When tasks are deleted, the value of all the completed and planned tasks is increased.
For major plan changes, you must produce a new plan.
Notes: <number>

## Slide 37: Messages to Remember
You can use the PROBE method to estimate development hours.
This method also gives you the likely hourly range within which the project will be completed.
With an accurate estimate, you can make an accurate schedule.
The earned value method helps you to track progress and project job completion.
Notes: <number>