## Slide 1: Personal Software ProcessSM for Engineers: Part I Tutorial: Using PROBE with the Student Workbook
Notes: <number>

## Slide 3: Objective
After this tutorial, you will know how to use the size estimate and PROBE worksheets to prepare estimates of program size and development time.
Notes: <number>

## Slide 4: Steps in the PROBE Method
Conceptual
design
Identify and size objects
Number of
methods
Object
type
Relative
size
Reuse
categories
Estimate other LOC
Estimate
program size
Calculate
prediction interval
Size estimate
Estimate
resources
Calculate
prediction interval
Resource estimate
1.
2.
3.
4.
5.
6.
7.
Start
Notes: <number>

## Slide 5: Estimating Worksheets
The student workbook includes two worksheets for estimating.
  size estimate: a PSP size-estimating template
  PROBE: an estimating tool based on the PROBE method
Open your student workbook and select the size estimate worksheet.

## Slide 6: Size Estimate Worksheet
The Size Estimate worksheet automates the preparation of size estimating templates.
Size estimating templates are included for exercises 4A through 10A.
Question marks and/or shaded fields indicate student-supplied data; other cells are locked.

## Slide 7: Size Estimate Controls -1
Use the project drop-down control to select a project.
Shortcut menus (right mouse click) provide context sensitive input for the type and rel. size fields.
The size and time estimates are transferred from the PROBE worksheet.
Notes: <number>

## Slide 8: Size Estimate Controls -2
A continuation page is provided for
  base additions
  new objects
  reused objects
Subtotals on this page are included in page one totals.
Each page includes the default C++ LOC per method table from the textbook.

## Slide 9: Example Problem
We will use the following problem to illustrate the PROBE method.
Problem statement: Develop a simple event-driven system.
Notes: <number>

## Slide 10: Requirements
Your system should contain an event manager that can register, unregister, and dispatch events. The event manager maps events to event handlers.
Your system should contain one event handler, systime, that will output the system time.
Notes: <number>

## Slide 11: Conceptual Design -1
One possible conceptual design
Event manager
systime
PrintTime
Control-P
Notes: <number>

## Slide 12: Conceptual Design -2
There are two objects in the conceptual design.
Let’s assume that we have a list object in our library. We’ll come back to this.
The next step is to identify and classify each new object.
In this example, the new objects are the event manager and the event handler.
Notes: <number>

## Slide 13: Object Identification
We begin with the event manager.
We’ll select the logic (L) type category for this object.
We estimate the relative size of the object. We’ll use large for this object.
Next, we need to get the historical LOC/method for this type and size of object.
Notes: <number>

## Slide 14: Object Size Estimating
We determine that there are three methods.
  register_event
  unregister_event
  dispatch_event
Using the table from
the Size Estimate
worksheet, we
estimate that this
object will contain
70 LOC. Why?
Notes: <number>

## Slide 15: Entering the Data
The estimate for the event manager is entered on the size estimating template. Enter these data now.
Notes: <number>

## Slide 16: Object Identification
Turning to the event handler, we determine that there are are also three methods.
  register_systime
  get_time
  print_time
Once again using
our historical
database, we
estimate that this
object will contain
48 LOC.
Notes: <number>

## Slide 17: Total New Object LOC
The estimate for the event handler object is entered on the size estimating template.
The estimated total new object LOC is calculated.
Enter these data now.
Notes: <number>

## Slide 18: Estimating Base Code
list
We would like to maintain a list of registered event handlers and the events to which they respond.
We have existing code that does everything we need, except that it was written for integers.
Notes: <number>

## Slide 19: Estimating Base Code -1
We determine the following.
  base size = 48 (measured)
  base deleted = 0 (estimated)
  base modified = 12 (estimated)
We also want to add a method to search for an existing event handler.
Using the object
database, we
estimate this to
be 5 LOC.
Notes: <number>

## Slide 20: Estimating Base Code -2
We record our estimate of base code here.
The base addition is recorded here.
We also determine that we will not use any objects from our reuse library.
Enter these data now.
Notes: <number>

## Slide 21: Estimating New and Changed LOC
We are now ready to estimate new and changed LOC.
Estimated object LOC = 135. Why?
How do we determine the regression parameters 0 and 1?
Notes: <number>

## Slide 22: PROBE Worksheet -1
The PROBE worksheet simplifies the size-estimating process.
It helps students to select the best estimating method.
  : Estimated object LOC
  : Estimated new and changed
  : Averaging
  : Engineering judgement
The worksheet calculates
  size and time estimates
  regression parameters
  R2
  prediction intervals
Calculations are based on historical data from the project plan summary.
Notes: <number>

## Slide 23: PROBE Worksheet -2
Method
selector
Regression
line plots
Historical data with outlier selector
Project
selector
PROBE calculations
Transfer
control

## Slide 24: Historical Data Table
The historical data table contains the data for the PROBE method.
  estimated new and changed LOC
  actual new and changed LOC
  actual minutes
  estimated object LOC
These data come from the summary worksheet.

## Slide 25: PROBE Method Calculations
The calculation table contains parameters generated for each of the methods A, B, C, and D.
  correlation (R-squared)
  intercept (Beta 0)
  slope (Beta 1)
  prediction range
  UPI
  LPI
  variance
  standard deviation
Check these parameters to determine which method to use.

## Slide 26: Regression Line Plots
Regression line plots graphically depict the correlation between estimated size and
  actual size
  actual time
These plots will help you to select the method that provides the best correlation and will help with the identification of outliers in your historical data.
Plots are based on the method selected.

## Slide 27: Outlier Control
As a process evolves, some early data may need to be discarded.
Your data may also contain outliers that represent extreme or unusual circumstances.
These data may be removed by selecting the project number in the outlier control.
Outlier control
Project 3 is an outlier

## Slide 28: Project and Method Selectors -1
The project drop-down control selects the project.
Method selectors are provided for both size and time.
Method Description
A Estimated object LOC
B Estimated new and
changed LOC
C Averaging method using
estimated new and
changed LOC
D Judgement is used in
to estimate new and
changed LOC

## Slide 29: Project and Method Selectors -2
Size method selection criteria
A: Use method A if R^2 is > .5, and B1 is between .5 and 2.0, and B0 is small relative to the estimated LOC.
B: Use method B if R^2 is > .5, and B1 is between .5 and 2.0, and B0 is small relative to the estimated LOC.
C: Use method C when you have data but method A and B cannot be used.
D: Use method D when you have no reliable historical data.

## Slide 30: Project and Method Selectors -3
Time method selection criteria
A: Use method A if R^2 is > .5, and B1 is near your min./LOC, and B0 is small relative to the estimated time.
B: Use method B if R^2 is > .5, and B1 is near your min./LOC, and B0 is small relative to the estimated time.
C: Use method C when you have data but method A and B cannot be used.
D: Use method D when you have no reliable historical data.
Notes: <number>

## Slide 31: Estimate Transfer Control
The estimate transfer control moves the estimate from the PROBE worksheet to the size estimate worksheet.
The estimate is transferred to the size estimating template for the project selected by the project selector.
Make certain that you select the correct project before you transfer the estimate!
Notes: <number>

## Slide 32: Producing the Size and Time Estimate
To produce size and time estimates, follow these steps.
  Select the size estimate worksheet.
  Select the project.
  Enter the base, modified, and deleted LOC.
  Enter the base additions, new objects, and reuse LOC.
  Select the PROBE worksheet.
  Check the calculation table to determine which estimating method to use for size and time.
  Select the method for size.
  Select the method for time.
  Click the transfer button to move your estimate back to the size estimating template.

## Slide 33: Exercise Step 2
Select project 4 and method C for both size and time on the PROBE worksheet.
  What is the predicted size?
  How does this compare with the estimate?
  What is the LOC/minute rate?
Transfer the estimate to the size estimating template and recheck the estimate there.
Look at the plan summary. What do you see?
Now, select the size estimate worksheet and delete all of the data that you entered.

## Slide 34: Messages to Remember
The PROBE worksheet will help you to select the appropriate estimating method for program size and development time.
The PROBE worksheet generates
  regression parameters
  prediction intervals
  R2
  estimates
Notes: <number>