Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Student Workbook for
PSP0.1 Exercise

Personal Software Process for Engineers: Part I

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

This page intentionally left blank.

Personal Software Process for Engineers: Part I

PSP0.1 Exercise

Overview

| #### Exercise Overview | The exercise includes the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Exercise Objectives | 3 |
|  | Exercise Instructions | 3 |
|  | JD’s LOC Size Data | 4 |
|  | PSP0.1 Plan Summary Form | 5 |
|  | PSP0.1 Project Plan Summary Instructions | 6 |

| Prerequisites and References | Prerequisite reading • Preface • Chapters 1 through 4 References • Appendix C1 • Lecture 2 • PSP0.1 Exercise slides |
| --- | --- |

| Exercise Objectives | After completing this exercise, you will • understand the PSP LOC accounting process • understand how to fill in the Program Size (LOC) portion of the PSP0.1 plan summary • be prepared to use PSP0.1 for assignments 2A and 3A |
| --- | --- |

| #### PSP0 Exercise Instructions | Review the PSP0.1 plan summary instructions for program size (LOC). Read JD’s scenario for assignment 3A. Use the data from JD’s 3A scenario to complete the program size (LOC) portion of JD’s PSP0.1 plan summary. |
| --- | --- |

Overview, Continued

| #### Size Data for JD’s Programs 1A, 2A, and 3A | JD’s program 1A was 105 total LOC, all newly developed. Of the 105 LOC, JD identified 65 LOC as reusable in future assignments: 48 LOC implementing a linked list structure and routines to manipulate the linked list, and 17 LOC implementing a file open routine. On program 2A, JD reused the file open routine from program 1A (17 LOC). The total LOC for JD’s program 2A was 87 LOC. In the planning phase for program 3A, JD decided to start with program 2A and estimated that he would add and/or modify 150 LOC to create program 3A. During the development phase for program 3A, JD deleted 12 LOC and modified 7 LOC of the program 2A code that he started with. He also decided to reuse the linked list object from program 1A (48 LOC), in addition to the file open routine already in the program 2A code that JD started with. In the postmortem phase, JD used program 2A to measure the total LOC in program 3A as 248 LOC. |
| --- | --- |

Table C25 PSP0.1 Project Plan Summary

| Student |  | Date |  |
| --- | --- | --- | --- |
| Program |  | Program # |  |
| Instructor |  | Language |  |

| Program Size (LOC) | Plan |  |  |  | Actual |  |  |  | To Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Base(B) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | (Measured) |  |  |  |  |  |  |
| Deleted (D) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | (Counted) |  |  |  |  |  |  |
| Modified (M) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | (Counted) |  |  |  |  |  |  |
| Added (A) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | (T-B+D-R) |  |  |  |  |  |  |
| Reused (R) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | (Counted) |  |  |  |  |  |  |
| Total New & Changed (N) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | (A+M) |  |  |  |  |  |  |
| Total LOC (T) |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | (Measured) |  |  |  |  |  |  |
| Total New Reused |  |  |  |  |  |  |  |  |  |  |  |
| Time in Phase (min.) | Plan |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| Planning |  |  |  |  |  |  |  |  |  |  |  |
| Design |  |  |  |  |  |  |  |  |  |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |
| Compile |  |  |  |  |  |  |  |  |  |  |  |
| Test |  |  |  |  |  |  |  |  |  |  |  |
| Postmortem |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |
| Defects Injected |  |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| Planning |  |  |  |  |  |  |  |  |  |  |  |
| Design |  |  |  |  |  |  |  |  |  |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |
| Compile |  |  |  |  |  |  |  |  |  |  |  |
| Test |  |  |  |  |  |  |  |  |  |  |  |
| Total Development |  |  |  |  |  |  |  |  |  |  |  |
| Defects Removed |  |  | Actual |  |  |  | To Date |  |  |  | To Date % |
| Planning |  |  |  |  |  |  |  |  |  |  |  |
| Design |  |  |  |  |  |  |  |  |  |  |  |
| Code |  |  |  |  |  |  |  |  |  |  |  |
| Compile |  |  |  |  |  |  |  |  |  |  |  |
| Test |  |  |  |  |  |  |  |  |  |  |  |
| Total Development |  |  |  |  |  |  |  |  |  |  |  |
| After Development |  |  |  |  |  |  |  |  |  |  |  |

Table C26 PSP0.1 Project Plan Summary Instructions

| Purpose | To hold the estimated and actual project data in a convenient and readily retrievable form |
| --- | --- |
| Header | Enter the following: • Your name and today’s date • The program name and number • The instructor’s name • The language you will use to write the program |
| Program Size (LOC) | Prior to Development: • If you are modifying or enhancing an existing program, count that program’s LOC and enter it under BaseActual. • Using your best judgment, estimate the new and changed LOC you expect to develop. After Development: • If the base LOC (B) has changed, enter the new value. • Measure the total program size and enter it under Total LOC (T)Actual. • Review your source code and, with the help of program 3A, determine the actual LOC that were deleted (D), modified (M), or reused (R). • Calculate the LOC of added code as A = T  B+ D  R. • Calculate the total new and changed LOC as N = A + M. |
| Time in Phase | • Under Plan, enter your original estimate of the total development time and the time required by phase. • Under Actual, enter the actual time in minutes spent in each development phase. • Under To Date, enter the sum of the actual time and the To Date time from your most recently developed program. • Under To Date %, enter the percentage of To Date time in each phase. |
| Defects Injected | • Under Actual, enter the number of defects injected in each phase. • Under To Date, enter the sum of the actual number of defects injected in each phase and the To Date values from the most recently developed program. • Under To Date %, enter the percentage of the To Date defects injected by phase. |
| Defects Removed | • Under Actual, enter the number of defects removed in each phase. • Under To Date, enter the sum of the actual number of defects removed in each phase and the To Date values from the most recently developed program. • Under To Date %, enter the percentage of the To Date defects removed by phase. • After development, record any defects later found during program use, reuse, or modification. |