Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Student Workbook for
Assignment Workshop 2A

Personal Software Process for Engineers: Part I

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution limited by the Software Engineering Institute to attendees.

Personal Software Process for Engineers: Part I

Assignment Workshop 2A

Overview

| #### Workshop Overview | The workshop will cover the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Workshop Objectives | 3 |
|  | Program Requirements for Assignment 2A | 3 |
|  | Assignment Instructions | 4 |
|  | Guidelines and Evaluation Criteria | 9 |
|  | Assignment Package | A1 |

| Prerequisites and References | Prerequisites • Read chapters 3 and 4 • Complete rportsR1 and R2 References • Appendix C2 • Appendix D3 • Chapter 4 |
| --- | --- |

### Program Requirements for Assignment 2A

| Workshop Objectives | After this workshop, you will • understand program 2A requirements • have completed program 2A planning -program requirements -resource estimate -size estimate |
| --- | --- |

| Program 2A Requirements | Use PSP0.1 to write a program to count the total logical LOC in a program, omitting comments and blank lines. Use your counting standard (R1) and coding standard (R2) to place one logical line on each physical line and count physical lines. Produce a single count for the entire program source file. Thoroughly test the program. As one test, count the LOC in programs 1A and 2A. |
| --- | --- |

### Assignment Instructions

| #### Instructions for Assignment 2A | Before beginning this assignment, review the top-level PSP0.1 process script below to ensure that you understand the “big picture” before you begin. Also, ensure that you have all of the inputs required before starting the planning phase. |
| --- | --- |

Table C21  PSP0.1 Process Script

| Phase Number | Purpose | To guide you in developing module-level programs |
| --- | --- | --- |
|  | Entry Criteria | • Problem description • PSP0.1 Project Plan Summary form • Time and Defect Recording Logs • Defect Type Standard • Stop watch (optional) |
| 1 | Planning | • Produce or obtain a requirements statement. • Estimate the total new and changed LOC required. • Estimate the required development time. • Enter the plan data on the Project Plan Summary form. • Complete the Time Recording Log. |
| 2 | Development | • Design the program. • Implement the design. • Compile the program and fix and log all defects found. • Test the program and fix and log all defects found. • Complete the Time Recording Log. |
| 3 | Postmortem | Complete the Project Plan Summary form with actual time, defect, and size data. |
|  | Exit Criteria | • A thoroughly tested program • Completed Project Plan Summary form with estimated and actual data • Completed PIP forms • Completed Defect and Time Recording Logs |

Continued on next page

Assignment Instructions, Continued

| #### Planning Phase | Plan assignment 2A following the PSP0.1 planning phase script. |
| --- | --- |

Table C22  PSP0.1 Planning Script

| Phase Number | Purpose | To guide the PSP planning process |
| --- | --- | --- |
|  | Entry Criteria | • Problem description • PSP0.1 Project Plan Summary form • Time Recording Log |
| 1 | Program Requirements | • Produce or obtain a requirements statement for the program. • Ensure the requirements statement is clear and unambiguous. • Resolve any questions. |
| 2 | Size Estimate | Make your best estimate of the total new and changed LOC required to develop this program. |
| 3 | Resource Estimate | • Make your best estimate of the time required to develop this program. • Using the To Date % from the most recently developed program as a guide, distribute the development time over the planned project phases. |
|  | Exit Criteria | • Documented requirements statement • Project Plan Summary form with estimated program size and development time data • Completed Time Log |

|  | Verify that you have met all of the exit criteria for the planning phase, then have an instructor review your plan. After your plan has been reviewed, proceed to the development phase. |
| --- | --- |

Continued on next page

Assignment Instructions, Continued

| #### Development Phase | Develop the program following the PSP0 development phase script. |
| --- | --- |

Table C23  PSP0.1 Development Script

| Phase Number | Purpose | To guide the development of small programs |
| --- | --- | --- |
|  | Entry Criteria | • Requirements statement • Project Plan Summary form with estimated program size and development time • Time and Defect Recording Logs • Defect Type Standard and Coding Standard |
| 1 | Design | • Review the requirements and produce a design to meet them. • Record time in Time Recording Log. |
| 2 | Code | • Implement the design following the Coding Standard. • Record in the Defect Recording Log any requirements or design defects found. • Record time in Time Recording Log. |
| 3 | Compile | • Compile the program until error-free. • Fix all defects found. • Record defects in Defect Recording Log. • Record time in Time Recording Log. |
| 4 | Test | • Test until all tests run without error. • Fix all defects found. • Record defects in Defect Recording Log. • Record time in Time Recording Log. |
|  | Exit Criteria | • A thoroughly tested program that conforms to the Coding Standard • Completed Defect and Time Recording Logs |

Verify that you have met all of the exit criteria for the development phase, then proceed to the postmortem phase.

Continued on next page

Assignment Instructions, Continued

| #### Postmortem #### Phase | Conduct the postmortem following the PSP0.1 postmortem script. |
| --- | --- |

Table C24  PSP0.1 Postmortem Script

| Phase Number | Purpose | To guide the PSP postmortem process |
| --- | --- | --- |
|  | Entry Criteria | • Problem description and requirements statement • Project Plan Summary form with planned program size and development time • Completed Time Recording Log • Completed Defect Recording Log • A tested and running program that conforms to the Coding Standard |
| 1 | Defects Injected | • Determine from the Defect Recording Log the number of defects injected in each PSP0.1 phase. • Enter this number under Defects Injected–Actual on the Project Plan Summary form. |
| 2 | Defects Removed | • Determine from the Defect Recording Log the number of defects removed in each PSP0.1 phase. • Enter this number under Defects Removed–Actual on the Project Plan Summary form. |
| 3 | Size | • Count the LOC in the completed program. • Determine the base, reused, deleted, modified, added, total, total new and changed, and new reused LOC. • Enter these data on the Project Plan Summary form. |
| 4 | Time | • Review the completed Time Recording Log. • Enter the total time spent in each PSP0.1 phase in the Actual column of the Project Plan Summary form. |
|  | Exit Criteria | • A fully tested program that conforms to the Coding Standard • Completed Project Plan Summary form • Completed PIP forms describing process problems, improvement suggestions, and lessons learned • Completed Defect and Time Recording Logs |

Verify that you have met all of the exit criteria for the PSP0.1 postmortem phase, then submit your assignment.

Continued on next page

Assignment Instructions, Continued

| #### Submitting Your Assignment | When you’ve completed the postmortem phase, submit your assignment package, source code, and test results to the instructor. The order for the assignment package is • PSP0.1 project plan summary (from the student workbook) • PIP form • time recording log • defect recording log • source program listing • R1 LOC counting standard • R2 coding standard • test results • assignment 1A project plan summary (from the student workbook) • student survey |
| --- | --- |

### Guidelines and Evaluation Criteria

| #### PSP0.1 Evaluation Criteria | Your PIP form must show that you’re thinking about the process and how it works for you. |  |
| --- | --- | --- |
|  | Your process report must be | Your process data must be |
|  | • complete | • accurate |
|  | • legible | • precise |
|  | • in the specified order | • self-consistent |
|  | Remember, test results, not code, are evaluated! |  |

| #### Suggestions | Remember, you should complete this assignment today. Keep your programs simple. You will learn as much from small programs as from large ones. Keep your reports and standards simple and short. Do not hesitate to copy or build on the PSP materials. Do it right the first time. If you are not sure, find out. Software is not a solo business, so you do not have to work alone. You must, however, produce your own estimates, designs, and code. You may have others review your work, and you may change it as a result. You should note any in your process report. Include the review time that you and your associates spend, and log the defects found. |
| --- | --- |