Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Student Workbook for
Assignment Workshop 5A

Personal Software Process for Engineers: Part I

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution limited by the Software Engineering Institute to attendees.

Personal Software Process for Engineers: Part I

Assignment Workshop 5A

Overview

| #### Workshop Overview | The workshop will cover the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Workshop Objectives | 3 |
|  | Program Requirements for Assignment 5A | 3 |
|  | Numerical Integration | 4 |
|  | Assignment Instructions | 6 |
|  | Guidelines and Evaluation Criteria | 13 |
|  | Assignment Package | A1 |

| Prerequisites and References | Prerequisites • Read chapter 6 • Complete program 4A References • Section A5 • Section C4 • Section D3 |
| --- | --- |

### Program Requirements for Assignment 5A

| Workshop Objectives | After this workshop, you will • understand program 5A requirements • have completed program 5A planning - conceptual design - size estimate - resource estimate |
| --- | --- |

| Program 5A Requirements | Use PSP1.1 to write a program to numerically integrate a function using Simpson’s rule and write the function for the normal distribution. The program should be designed to integrate using various supplied functions. You will need this program to calculate the values of the various statistical distributions used in later program assignments. Thoroughly test the program. At a minimum, use this program to calculate the values of the normal distribution integral for three values. Test Expected Value • -¥ to 2.5 0.9938 • -¥ to 0.2 0.5793 • -¥ to -1.1 0.1357 |
| --- | --- |

Numerical Integration

| Numerical Integration | In principle, numerical integration treats a function as being composed of multiple rectangular areas. It then adds these areas to produce the integral value. The trick is to sum these areas so as to minimize the error. |  |
| --- | --- | --- |

| #### Integration Limits | To determine the integration limits • most statistical functions are integrated from -¥ to some value • all statistical functions have a total area of 1.0 when integrated from -¥ to +¥ |
| --- | --- |

| Symmetric Functions | With symmetric functions (the normal and t distributions), the procedure is this. |  |  |
| --- | --- | --- | --- |
|  | If the value of X is | then integrate from | and |
|  | positive | 0 to X | add 0.5 to the results |
|  | negative | 0 to abs(X) | subtract the result from 0.5 |

| Simpson’s Rule | Simpson’s rule for calculating the integral is xlowxhighF(u)du=W3F(xlow)+4F(xlow+W)+2F(xlow+2W)+4F(xlow+3W)… where • W is the width of the segments • F is the value of the function for each x value Simpson’s rule in another form* xlowxhighFudu=W3Fxlow+i=1,3,5...N−14Fxlow+iW+i=2,4,6...N−22Fxlow+iW+Fxhigh where N is the number of segments * Note: The above equation for simpson is a simplified form of equation A5 in the book, page 518. |
| --- | --- |

Continued on next page

Numerical Integration, Continued

| Normal Distribution | The formula for the normal distribution is F(x)=-¥x1(2p)e−u22du (A6) Page 518 contains formulas for the 2 and t distributions. |
| --- | --- |

| Hints—Read Appendix A! | Refer to page 517 in Appendix A for an algorithm to evaluate the integral using Simpson’s rule. Start with N = 20 and an acceptable error (E) of 1E-07. If you are using C or C++, consider designing Simpson’s rule to accept a pointer to a function. (This makes reuse very easy.) For other languages, separate Simpson’s rule calculation from the normal distribution. |
| --- | --- |

### Assignment Instructions

| #### Instructions for Assignment 5A | Before starting assignment 5A, review the top-level PSP1.1 process script below to ensure that you understand the “big picture” before you begin. Also, ensure that you have all of the inputs required before you begin the planning phase. |
| --- | --- |

Table C41  PSP1.1 Process Script

| Phase Number | Purpose | To guide you in developing module-level programs |
| --- | --- | --- |
|  | Entry Criteria | • Problem description • PSP1.1 Project Plan Summary form • Size Estimating Template • Historical estimate and actual size and time data • Time and Defect Recording Logs • Defect Type Standard • Stop watch (optional) |
| 1 | Planning | • Produce or obtain a requirements statement. • Use the PROBE method to estimate the total new and changed LOC required. • Complete the Size Estimating Template. • Use the PROBE method to estimate the required development time. • Complete a Task Planning Template. • Complete a Schedule Planning Template. • Enter the plan data in the Project Plan Summary form. • Complete the Time Recording Log. |
| 2 | Development | • Design the program. • Implement the design. • Compile the program and fix and log all defects found. • Test the program and fix and log all defects found. • Complete the Time Recording Log. |
| 3 | Postmortem | Complete the Project Plan Summary form with actual time, defect, and size data. |
|  | Exit Criteria | • A thoroughly tested program • Completed Project Plan Summary form with estimated and actual data • Completed estimating and planning templates • Completed Test Report Template • Completed PIP forms • Completed Defect and Time Recording Logs |

Continued on next page

Assignment Instructions, Continued

| #### Planning Phase | Plan assignment 5A following the PSP1.1 planning phase and the PROBE estimating scripts. |
| --- | --- |

Table C42  PSP1.1 Planning Script

| Phase Number | Purpose | To guide the PSP planning process |
| --- | --- | --- |
|  | Entry Criteria | • Problem description • PSP1.1 Project Plan Summary form • Size Estimating, Task Planning, and Schedule Planning Templates • Historical estimated and actual size and time data • Time Recording Log |
| 1 | Program Requirements | • Produce or obtain a requirements statement for the program. • Ensure that the requirements statement is clear and unambiguous. • Resolve any questions. |
| 2 | Size Estimate | • Produce a program conceptual design. • Use the PROBE method to estimate the new and changed LOC required to develop this program. • Estimate the base, added, deleted, modified, and reused LOC. • Complete the Size Estimating Template and Project Plan Summary form. |
| 3 | Estimate Resources | • Use the PROBE method to estimate the time required to develop this program. • Using the To Date % from the most recently developed program as a guide, distribute the development time over the planned project phases. |
| 4 | Task and Schedule Planning | For projects requiring several days or more of work, complete the Task Planning and Schedule Planning Templates. |
|  | Exit Criteria | • Documented requirements statement • The program conceptual design • Completed Size Estimating Template • For projects of several days duration, completed Task Planning and Schedule Planning Templates • Completed Project Plan Summary form with estimated program size and development time data • Completed Time Recording Log |

Continued on next page

### Assignment Instructions, Continued

|  | Use the PROBE method for size and resource estimating. |
| --- | --- |

Table C36  PROBE Estimating Script

|  | Purpose | To guide the PROBE estimation process |
| --- | --- | --- |
|  | Entry Criteria | • Requirements statement • Size Estimating Template and instructions • LOC per method data for object types • Time Recording Log • Historical size and time data |
| 1 | Conceptual Design | Review the requirements and produce a conceptual design. |
| 2 | Estimate Objects | Follow the Size Estimating Template instructions to estimate the new object LOC and new reused LOC. |
| 3 | Other Program LOC | Follow the Size Estimating Template instructions to estimate base, deleted, modified, added, and reused LOC. |
| 4 | The Size Estimating Procedure | A  If you have sufficient estimated object LOC and actual new and changed LOC (three or more points that correlate), use procedure 4A. B  If you do not have sufficient estimated object LOC data but have sufficient estimated new and changed LOC data (three or more points that correlate), use procedure 4B. C  If you have insufficient data or they do not correlate, use procedure 4C. D  If you have no historical data, use procedure 4D. |
| 4A | The Size Estimating Procedure 4A | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated object LOC and actual new and changed LOC. - If is not near 0 (substantially smaller than the expected size of the new program), or is not near 1.0 (between about 0.5 and 2.0), use procedure 4B. |
| 4B | The Size Estimating Procedure 4B | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated new and change LOC and actual new and changed LOC. - If is not near 0 (substantially smaller than the expected size of the new program), or is not reasonably near 1.0 (between about 0.5 and 2.0), use procedure 4C. |
| 4C | The Size Estimating Procedure 4C | If you have any data on estimated object LOC and actual new and changed LOC, set = 0 and = (total new and changed LOC to date/total estimated object LOC to date). |
| 4D | The Size Estimating Procedure 4D | If you have no historical data, use your judgment to estimate the new and changed LOC from the estimated object LOC. |

Continued on next page

### Assignment Instructions, Continued

Table C36  PROBE Estimating Script (Continued)

| 5 | The Time Estimating Procedure | A  If you have sufficient estimated object LOC and actual development time data (three or more points that correlate), use procedure 5A. B  If you do not have sufficient estimated object LOC data, but have sufficient estimated new and changed LOC data (three or more points that correlate), use procedure 5B. C1  If you have some estimated object LOC data and they are insufficient or do not correlate, use procedure 5C1. C2  If you have some estimated new and changed LOC data and they are insufficient or do not correlate, use procedure 5C2. C3  If you only have actual data on new and changed LOC, use procedure 5C3. D  If you have no historical data, use procedure 5D. |
| --- | --- | --- |
| 5A | The Time Estimating Procedure 5A | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated object LOC and actual total development time. - If is not substantially smaller than the expected development time for the new program, or is not near 60/(to date LOC/hour) for your latest program, use procedure 5C1. |
| 5B | The Time Estimating Procedure 5B | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated new and change LOC and actual total development time. - If is not substantially smaller than the expected development time for the new program, or is not near 60/(to date LOC/hour) for your latest program, use procedure 5C2. |
| 5C1 | The Time Estimating Procedure 5C1 | If you have any data on estimated object LOC and actual development time, set = 0 and = (total development time to date/total estimated object LOC to date). |
| 5C2 | The Time Estimating Procedure 5C2 | If you have data on estimated new and changed LOC and actual development time, set = 0 and = (development time to date/estimated new and changed LOC to date). |
| 5C3 | The Time Estimating Procedure 5C3 | If you only have actual time and size data, set = 0 and = (development time to date/new and changed LOC to date). |
| 5D | The Time Estimating Procedure 5D | If you have no historical data, use your judgment to estimate the development time from the estimated object LOC. |
| 6 | Time and Size Prediction Intervals | - If you used the regression method, calculate the prediction interval as described in Table A29 (page 550). - If you did not use the regression method, estimate the maximum and minimum development times from your maximum and minimum productivity for prior programs. |

|  | Verify that you have met all of the exit criteria for the planning phase, then have an instructor review your plan. After your plan has been reviewed, proceed to the development phase. |
| --- | --- |

Continued on next page

### Assignment Instructions, Continued

| #### Development Phase | Develop the program following the PSP1.1 development phase script. |
| --- | --- |

Table C43  PSP1.1 Development Script

| Phase Number | Purpose | To guide the development of small programs |
| --- | --- | --- |
|  | Entry Criteria | • Requirements statement • Project Plan Summary form with estimated program size and development time • For projects of several days duration, completed Task Planning and Schedule Planning Templates • Time and Defect Recording Logs • Defect Type Standard and Coding Standard |
| 1 | Design | • Review the requirements and produce a design to meet them. • Record time in Time Recording Log. |
| 2 | Code | • Implement the design following the Coding Standard. • Record in the Defect Recording Log Record any requirements or design defects found. • Record time in Time Recording Log. |
| 3 | Compile | • Compile the program until error-free. • Fix all defects found. • Record defects in Defect Recording Log. • Record time in Time Recording Log. |
| 4 | Test | • Test until all tests run without error. • Fix all defects found. • Record defects in Defect Recording Log. • Record time in Time Recording Log. • Complete a Test Report Template on the tests conducted and the results obtained. |
|  | Exit Criteria | • A thoroughly tested program that conforms to the Coding Standard • Completed Test Report Template • Completed Defect and Time Recording Logs |

Verify that you have met all of the exit criteria for the development phase, then proceed to the postmortem phase.

Continued on next page

Assignment Instructions, Continued

| #### Postmortem #### Phase | Conduct the postmortem following the PSP1.1 postmortem script. |
| --- | --- |

Table C44  PSP1.1 Postmortem Script

| Phase Number | Purpose | To guide the PSP postmortem process |
| --- | --- | --- |
|  | Entry Criteria | • Problem description and requirements statement • Project Plan Summary form with program size and development time data • For projects of several days duration, completed Task Planning and Schedule Planning Templates • Completed Test Report Template • Completed Time Recording Log • Completed Defect Recording Log • A tested and running program that conforms to the Coding Standard |
| 1 | Defects Injected | • Determine from the Defect Recording Log the number of defects injected in each PSP1.1 phase. • Enter this number under Defects Injected–Actual on the Project Plan Summary form. |
| 2 | Defects Removed | • Determine from the Defect Recording Log the number of defects removed in each PSP1.1 phase. • Enter this number under Defects Removed–Actual on the Project Plan Summary form. |
| 3 | Size | • Count the LOC in the completed program. • Determine the base, reused, deleted, modified, added, total, total new and changed, and new reused LOC. • Enter these data on the Project Plan Summary form. |
| 4 | Time | • Review the completed Time Recording Log. • Enter the total time spent in each PSP1.1 phase in the Actual column of the Project Plan Summary form. |
|  | Exit Criteria | • A fully tested program that conforms to the Coding Standard • Completed Test Report Template • Completed Project Plan Summary form • Completed PIP forms describing process problems, improvement suggestions, and lessons learned • Completed Defect and Time Recording Logs |

Verify that you have met all of the exit criteria for the PSP1.1 postmortem phase, then submit your assignment.

Continued on next page

Assignment Instructions, Continued

| #### Submitting Your Assignment | When you’ve completed the postmortem phase, submit your assignment package, source code, and test results to the instructor. The order for the assignment package is • PSP1.1 Project Plan Summary • test report • PIP form • size estimating template • PROBE worksheet • time recording log • defect recording log • source program listing • test results |
| --- | --- |

### Guidelines and Evaluation Criteria for Assignment 5A

| #### Evaluation Criteria | Your process report must be • complete • legible • in the specified order | Your process data must be • accurate • precise • self-consistent |
| --- | --- | --- |
|  | Also, test results, not code, are evaluated! |  |

| #### Suggestions | Remember, you should complete this assignment today. Keep your programs simple. You will learn as much from small programs as from large ones. Keep your reports and standards simple and short. Do not hesitate to copy or build on the PSP materials. Do it right the first time. If you are not sure, find out. Software is not a solo business, so you do not have to work alone. You must, however, produce your own estimates, designs, and code. You may have others review your work, and you may change it as a result. You should note any help in your process report. Include the review time that you and your associates spend, and log the defects found. |
| --- | --- |