Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

Table C36  PROBE Estimating Script

|  | Purpose | To guide the PROBE estimation process |
| --- | --- | --- |
|  | Entry Criteria | • Requirements statement • Size Estimating Template and instructions • LOC per method data for object types • Time Recording Log • Historical size and time data |
| 1 | Conceptual Design | Review the requirements and produce a conceptual design. |
| 2 | Estimate Objects | Follow the Size Estimating Template instructions to estimate the new object LOC and new reused LOC. |
| 3 | Other Program LOC | Follow the Size Estimating Template instructions to estimate base, deleted, modified, added, and reused LOC. |
| 4 | The Size Estimating Procedure | A  If you have sufficient estimated object LOC and actual new and changed LOC (three or more points that correlate), use procedure 4A. B  If you do not have sufficient estimated object LOC data but have sufficient estimated new and changed LOC data (three or more points that correlate), use procedure 4B. C  If you have insufficient data or they do not correlate, use procedure 4C. D  If you have no historical data, use procedure 4D. |
| 4A | The Size Estimating Procedure 4A | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated object LOC and actual new and changed LOC. - If is not near 0 (substantially smaller than the expected size of the new program), or is not near 1.0 (between about 0.5 and 2.0), use procedure 4B. |
| 4B | The Size Estimating Procedure 4B | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated new and change LOC and actual new and changed LOC. - If is not near 0 (substantially smaller than the expected size of the new program), or is not reasonably near 1.0 (between about 0.5 and 2.0), use procedure 4C. |
| 4C | The Size Estimating Procedure 4C | If you have any data on estimated object LOC and actual new and changed LOC, set = 0 and = (total new and changed LOC to date/total estimated object LOC to date). |
| 4D | The Size Estimating Procedure 4D | If you have no historical data, use your judgment to estimate the new and changed LOC from the estimated object LOC. |

(Continued)

Table C36  PROBE Estimating Script (Continued)

| 5 | The Time Estimating Procedure | A  If you have sufficient estimated object LOC and actual development time data (three or more points that correlate), use procedure 5A. B  If you do not have sufficient estimated object LOC data, but have sufficient estimated new and changed LOC data (three or more points that correlate), use procedure 5B. C1  If you have some estimated object LOC data and they are insufficient or do not correlate, use procedure 5C1. C2  If you have some estimated new and changed LOC data and they are insufficient or do not correlate, use procedure 5C2. C3  If you only have actual data on new and changed LOC, use procedure 5C3. D  If you have no historical data, use procedure 5D. |
| --- | --- | --- |
| 5A | The Time Estimating Procedure 5A | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated object LOC and actual total development time. - If is not substantially smaller than the expected development time for the new program, or is not near 60/(to date LOC/hour) for your latest program, use procedure 5C1. |
| 5B | The Time Estimating Procedure 5B | - Using the procedure in Table A27 (page 545), calculate the and regression parameters from the estimated new and change LOC and actual total development time. - If is not substantially smaller than the expected development time for the new program, or is not near 60/(to date LOC/hour) for your latest program, use procedure 5C2. |
| 5C1 | The Time Estimating Procedure 5C1 | If you have any data on estimated object LOC and actual development time, set = 0 and = (total development time to date/total estimated object LOC to date). |
| 5C2 | The Time Estimating Procedure 5C2 | If you have data on estimated new and changed LOC and actual development time, set = 0 and = (development time to date/estimated new and changed LOC to date). |
| 5C3 | The Time Estimating Procedure 5C3 | If you only have actual time and size data, set = 0 and = (development time to date/new and changed LOC to date). |
| 5D | The Time Estimating Procedure 5D | If you have no historical data, use your judgment to estimate the development time from the estimated object LOC. |
| 6 | Time and Size Prediction Intervals | - If you used the regression method, calculate the prediction interval as described in Table A29 (page 550). - If you did not use the regression method, estimate the maximum and minimum development times from your maximum and minimum productivity for prior programs. |