Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

Table C46  PSP1.1 Project Plan Summary Instructions

| Purpose | To hold the estimated and actual project data in a convenient and readily retrievable form |
| --- | --- |
| Header | Enter the specified data. |
| Summary | • Enter the new and changed LOC per hour planned and actual for this program and for all programs developed to date. • Enter the planned and actual times for this program and the sums of the planned and actual times for all the exercises to date. • CPI = (To Date Planned Time) / (To Actual Date Time) • Enter the planned, actual, and To Date reuse data. |
| Program Size (LOC) | Prior to Development: • If you are modifying or enhancing an existing program, count that program’s LOC and enter it as Base–Plan. • From the Size Estimating Template, enter Estimated Object LOC (E) under Plan. • Enter the estimated new and changed LOC (N) from the Size Estimating Template. • Estimate the numbers of added (A) and modified (M) LOC so that N = A + M. • Estimate the numbers of deleted (D) and reused (R) LOC and combine with the measured base (B) LOC so that T = N + B – M – D + R. After Development: • If the base LOC (B) has changed, enter the new value. • Measure the total program size and enter it as the Total LOC (T)  Actual. • Review your source code and, with the help of program 3A, determine the actual LOC that were deleted (D), modified (M), or reused (R). • Calculate the LOC of added code as A = T  B+ D  R. • Calculate the total new and changed LOC as N = A + M. |
| Time in Phase | • Under Plan, enter estimate total time from the Size Estimating Template and time by phase. • Under Actual, enter the actual time for each phase. • Under To Date, enter the sum of the actual time and the To Date time from your most recently developed program. • Under To Date %, enter the percentage of To Date time in each phase. |

(Continued)

Table C46  PSP1.1 Project Plan Summary Instructions (Continued)

| Defects Injected | • Under Actual, enter the number of defects injected in each phase. • Under To Date, enter the sum of the actual numbers of defects injected in each phase and the To Date values from the most recently developed program. • Under To Date %, enter the percentage of the To Date defects injected by phase. |
| --- | --- |
| Defects Removed | • Under Actual, enter the numbers of defects removed in each phase. • Under To Date, enter the sum of the actual number of defects removed in each phase and the To Date value from the most recently developed program. • Under To Date %, enter the percentage of To Date defects removed by phase. • After development, record any defects later found during program use, reuse, or modification. |