Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

Table C48  Task Planning Template Instructions

| Purpose | • To estimate the development time for each project task • To compute the planned value for each project task • To estimate the planned completion date for each task • To provide a basis for tracking schedule progress even when the tasks are not completed in the planned order |
| --- | --- |
| General | • Expand this template or use multiple pages as needed. • Include every significant task. • Use task names and numbers that support the activity and are consistent with the project work breakdown structure. |
| Header | Enter the following: • Your name • Today’s date • The project number • The instructor’s name |
| Task | • Enter a task number and name. List the tasks in the order in which you expect to complete them. • Select tasks that have explicit completion criteria, for example, planning completed, program compiled and all defects corrected, testing completed and all defects corrected, and so on. |
| Plan  Hours | Enter the planned hours for each task. |
| Plan  Planned Value | • Total the planned hours for all the tasks. • For each task, calculate the percent its planned hours are of total hours. • Enter this percentage as the planned value for that task. • The total planned value should equal 100. |
| Plan  Cumulative Hours | Enter the cumulative sum of the plan hours down through each task. |
| Plan  Cumulative Value | • Sum the planned values down through each task. • Before proceeding, complete the Schedule Planning Template down through PlanCumulative Hours. • Then complete the Schedule Planning and Task Planning templates together. |
| Plan Date  Monday | • For each cumulative hours entry, find the plan cumulative hours entry on the Schedule Planning Template that equals or just exceeds it. • Enter the date from that row (of the Schedule Planning Template) as the plan date on the Task Planning Template. • If several weeks on the Schedule Planning Template have the same cumulative value, enter the earliest date. • Unless you made daily plans, pick the plan date as the Monday of the week during which completion for that task is planned. |
| Actual Date | As each task is completed, enter the completion date. |
| Earned Value | For each completed task, enter the planned value. |
| Cumulative Earned Value | As each task is completed, total all the earned value entries and enter that total beside the latest task that was completed. |