Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

Table C50  Schedule Planning Template Instructions

| Purpose | • To record the estimated and actual hours expended by calendar period • To relate the task planned value to the calendar schedule • To calculate adjusted planned and earned values when tasks change |
| --- | --- |
| General | • Expand this template or use multiple pages as needed. • Complete it in conjunction with the Task Planning Template. |
| Header | Enter the following: • Your name • Today’s date • The project number • The instructor’s name |
| Week Number | • From the project start, enter a week number, typically starting with 1. • For very small projects, it may be more convenient to use days instead of weeks. |
| Date (Monday) | • Enter the calendar date for each week. • Pick a standard day in the week, for example, Monday. |
| PlanDirect Hours | • Enter the planned number of direct project hours you expect to spend each week. • Consider non-work time such as vacations, holidays, and so on. • Consider other committed activities such as classes, meetings, and other projects. |
| Plan Cumulative Hours | Enter the cumulative planned hours through each week. |
| Plan Cumulative Planned Value | For each week, do the following: • Take the plan cumulative hours from the Schedule Planning Template. • On the Task Planning Template, find the task with nearest equal or lower plan cumulative hours and note its plan cumulative value. • Enter this cumulative value in the Schedule Planning Template for that week. • If the cumulative value for the prior week still applies, enter it again. |
| Actual | • During development, enter the actual direct hours, cumulative hours, and cumulative earned value for each week. • Determine status against plan by comparing the cumulative planned value and the actual cumulative earned value. |
| Adjusted Earned Value | Proportionately adjust the earned value up or down as tasks are added or deleted. The adjusted earned value compensates for these changes without requiring a complete new plan. |