Table C46  PSP1.1 Project Plan Summary Instructions

| Purpose | To hold the estimated and actual project data in a convenient and readily retrievable form |
| --- | --- |
| Header | Enter the specified data. |
| Summary | • Enter the new and changed LOC per hour planned and actual for this program and for all programs developed to date. • Enter the planned and actual times for this program and the sums of the planned and actual times for all the exercises to date. • CPI = (To Date Planned Time) / (To Actual Date Time) • Enter the planned, actual, and To Date reuse data. |
| Program Size (LOC) | Prior to Development: • If you are modifying or enhancing an existing program, count that program’s LOC and enter it as Base–Plan. • From the Size Estimating Template, enter Estimated Object LOC (E) under Plan. • Enter the estimated new and changed LOC (N) from the Size Estimating Template. • Estimate the numbers of added (A) and modified (M) LOC so that N = A + M. • Estimate the numbers of deleted (D) and reused (R) LOC and combine with the measured base (B) LOC so that T = N + B – M – D + R. After Development: • If the base LOC (B) has changed, enter the new value. • Measure the total program size and enter it as the Total LOC (T)  Actual. • Review your source code and, with the help of program 3A, determine the actual LOC that were deleted (D), modified (M), or reused (R). • Calculate the LOC of added code as A = T  B+ D  R. • Calculate the total new and changed LOC as N = A + M. |
| Time in Phase | • Under Plan, enter estimate total time from the Size Estimating Template and time by phase. • Under Actual, enter the actual time for each phase. • Under To Date, enter the sum of the actual time and the To Date time from your most recently developed program. • Under To Date %, enter the percentage of To Date time in each phase. |

(Continued)

Table C46  PSP1.1 Project Plan Summary Instructions (Continued)

| Defects Injected | • Under Actual, enter the number of defects injected in each phase. • Under To Date, enter the sum of the actual numbers of defects injected in each phase and the To Date values from the most recently developed program. • Under To Date %, enter the percentage of the To Date defects injected by phase. |
| --- | --- |
| Defects Removed | • Under Actual, enter the numbers of defects removed in each phase. • Under To Date, enter the sum of the actual number of defects removed in each phase and the To Date value from the most recently developed program. • Under To Date %, enter the percentage of To Date defects removed by phase. • After development, record any defects later found during program use, reuse, or modification. |