Table C51  PSP2 Process Script

| Phase Number | Purpose | To guide you in developing module-level programs |
| --- | --- | --- |
|  | Entry Criteria | • Problem description • PSP2 Project Plan Summary form • Size Estimating Template • Historical estimated and actual size and time data • Time and Defect Recording Logs • Defect Type Standard • Stop watch (optional) |
| 1 | Planning | • Produce or obtain a requirements statement. • Use the PROBE method to estimate the total new and changed LOC required and the prediction interval. • Complete the Size Estimating Template. • Use the PROBE method to estimate the development time required and the prediction interval. • Complete a Task Planning Template. • Complete a Schedule Planning Template. • Enter the plan data in the Project Plan Summary form. • Complete the Time Recording Log. |
| 2 | Development | • Design the program. • Review the design and fix and log all defects found. • Implement the design. • Review the code and fix and log all defects found. • Compile the program and fix and log all defects found. • Test the program and fix and log all defects found. • Complete the Time Recording Log. |
| 3 | Postmortem | Complete the Project Plan Summary form with actual time, defect, and size data. |
|  | Exit Criteria | • A thoroughly tested program • Completed Project Plan Summary form with estimated and actual data • Completed estimating and planning templates • Completed Design Review Checklist and Code Review Checklist • Completed Test Report Template • Completed PIP forms • Completed Defect and Time Recording Logs |