Table C64  PSP2.1 Project Plan Summary Instructions

| Purpose | To hold the estimated and actual project data in a convenient and readily retrievable form |
| --- | --- |
| Header | Enter the specified data. |
| Summary | • Enter the new and changed LOC per hour planned and actual for this program and for all programs developed to date. • Enter the planned and actual times for this program and the sums of the planned and actual times for all the exercises to date. • CPI = (To Date Planned Time)/(To Date Actual Time). • Enter the planned, actual, and To Date reuse data. • Enter the planned, actual, and To Date defect data. • Enter the planned and actual yield. |
| Cost of Quality | • Enter the % Appraisal COQ: the percentage of development time spent in design and code reviews. • Enter the % Failure COQ: the percentage of development time spent in compile and test. • Enter the A/F Ratio: the ratio of Appraisal COQ divided by Failure COQ. |
| Program Size (LOC) | Prior to development: • If you are modifying or enhancing an existing program, count that program’s LOC and enter it as BasePlan. • Enter the estimated new and changed LOC (N) from the Size Estimating Template. • Estimate the numbers of added (A) and modified (M) LOC so that N = A + M. • Estimate the numbers of deleted (D) and reused (R) LOC and combine with the measured base (B) LOC so that T = N + B  M  D + R. After Development: • If the base LOC (B) has changed, enter the new value. • Measure the total program size and enter it under Total LOC (T) Actual. • Review your source code and, with the help of program 3A, determine the actual LOC that were deleted (D), modified (M), or reused (R). • Calculate the LOC of added code as A = T  B + D  R. • Calculate the total new and changed LOC as N = A + M. |

(Continued)

Table C64  PSP2.1 Project Plan Summary Instructions (continued)

| Time in Phase | • Under Plan, enter your estimated total development time from the Size Estimating Template and the time by phase. • Under Actual, enter the actual time for each phase. • Under To Date, enter the sum of the actual time and the To Date time from your most recently developed program. • Under To Date %, enter the percentage of To Date time in each phase. |
| --- | --- |
| Defects Injected | • Under Actual, enter the number of defects injected in each phase. • Under To Date, enter the sum of the actual numbers of defects injected in each phase and the To Date values from the most recently developed program. • Under To Date %, enter the percentage of the To Date defects injected by phase. |
| Defects Removed | • Under Actual, enter the number of defects removed in each phase. • Under To Date, enter the sum of the actual number of defects removed in each phase and the To Date values from the most recently developed program. • Under To Date %, enter the percentage of the To Date defects removed by phase. • After development, record any defects later found during program use, reuse, or modification. |
| Defect Removal Efficiency | • Under Plan, enter the planned efficiencies for this project. • Under Actual, enter the actual efficiencies achieved. • Under To Date, enter the actual efficiencies for all the projects to date. |