Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Answers for
 Capstone Exercise

PSP Advanced

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

# Situation 1:  The New Project Assignment

Questions and Answers:

## What do you expect are the likely problems with this assignment?

First, there could be serious problems with the open source program: it might have a unique environment, fail to compile, have no or very limited documentation or comments, or not even provide the needed functions.

Second, even though the requirements are supposed to be firm, they could still change.

Third, the open source program could be full of defects and undocumented functions.

Fourth, with the high pressure for this job, it would likely be another late-night crisis project.

## What do you say when your manager asks you to agree to finish in three weeks?

First, concentrate on understanding what your manager wants you to do.

Second, repeat back to the manager your understanding of the job and its importance to the company.

Then, once you have reached a mutual understanding of the job, tell your manager that it sounds like a challenging opportunity but that you need a day or two to look at it before discussing the schedule. Ask if it would be OK to get back late tomorrow or first thing the following morning.

## What steps do you plan to take next?

The necessary next steps are to

- get and read the requirements

- get the open source program and make a quick assessment

- produce a strategy and conceptual design for the work

- estimate the effort required

- make a plan and a schedule

## In making a schedule commitment to your manager, what would you say?

This depends on what you find by looking at the requirements and the open source program.

If the job seems clear and there don’t appear to be serious problems with the open source program, you could commit to a schedule.

If, however, the job requirements are ill defined or the open source program appears to have serious problems, explain that you must have more time to research these problems before making a commitment. When you say this, however, have a list of the problems together with your estimate for the time required to address them.

In any event, point out the two key risks that you see: changing requirements and serious problems with the open source program.

Also, produce a document that describes your plan and the risks and give it to your manager when you make the schedule commitment.

# Situation 2:  The First Project Crisis

Questions and Answers:

## What should you do now?

Get to your manager right away and explain what you have found and the implications. Before you do, however, consider that you now know more about this issue than anybody else in the organization, so you should also make a recommendation. Remember that, if you present management with a critical problem and no proposal action plan, they will do something that you may not think is appropriate.

## What if anything should you tell your manager?

Start by reiterating the critical nature of the job and its principal objectives. Make sure that you and your manager are still in agreement about the need.

Then, assuming that you are, explain what you have found out about this job, recommend what the company should do about it, and provide a justification for that recommendation.

## What do you recommend that the company do now, and how do you support that recommendation?

Since you now know that you need ten more days to determine what needs to be done to the open source utility and since you also suspect that it would be faster to develop a new utility than to fix the open source program, you recommend that three experienced developers join you in this effort. This would accelerate the open source analysis work and allow for an early start on developing the new utility if it is needed.

In justification for this recommendation, provide the following data.

- the open source program modifications that you know are required and the work required to make them

- the additional modifications that you suspect will be needed and how long you think they will take

- a preliminary estimate of the size and development effort required to develop a new utility

# Situation 3: Joining a TSP Team

Questions and Answers:

## How do you feel about taking this assignment?

You don’t mind working on somebody else’s team as long as you feel comfortable about the team.

Your principal concerns are that Pete be somebody you are comfortable working with and that you are not treated as an outsider by the team.

## What do you tell your manager?

Assuming that you can talk reasonably freely to your manager, explain your feelings about joining Pete’s team and make sure that you could refuse the job if you didn’t feel comfortable about it.

Also, assuming that you would like to, ask your manager if you will have a job to come back to after this assignment is over.

## How do you deal with Pete?

First, get a sense for the kind of team leader Pete is. Does he seem reasonably open and friendly and is he somebody you would like to work for. If not, don’t take the job.

Second, assuming that the first answer is yes, discuss your ideas with Pete and see if he is receptive to the design approach you believe is best.

Finally, assuming that the first and second answers were yes, ask if you could meet with the team members to see what kind of group it is and if you could quickly fit in and become productive.

## What steps would you TAKE TO become a productive member of the team and to contribute to its success?

If Pete agrees, the first step would be to talk to the team members and to ask for their help in rapidly becoming a productive TSP team member.

Next, in meeting with the team, offer to hold a session to describe to them what you have learned about the job so far.

Finally, and most important, tell Pete and the team that you want to participate in the team’s next TSP launch and to take one or two key roles.

# Situation 4: Quality Problems!

Questions and Answers:

## What problems do you think Marty’s actions could cause?

There are three kinds of problems: problems for this module, problems with Marty’s subsequent work, and problems for the entire team.

For this module, the module design is needed by many people. For example, some of the people who will need design information are: the other developers, the testers, the test developers for the flagship product, and the people who will eventually maintain and enhance the utility for use in testing subsequent flagship product releases. There is also the quality exposure. Without a design, it would be difficult to analyze the behavior of this module during a code inspection and determine if it is properly performing all of its functions. That is what the design inspection is supposed to do and, without a design, it is almost impossible to identify interface issues, detect performance problems, resolve state conflicts, or identify security issues.

Regarding Marty’s other works, unless he is persuaded to produce designs in the future, he will probably develop his other modules in the same way.

As for the team, if the other members are producing designs as they had decided during the launch, they will be as concerned as you are about Marty’s work. If, instead, they decide to follow Marty’s example, you will have a real quality problem. In either case, you must do something.

## What do you do?

At this point, the first step should be to talk to Marty and explain your concerns. Then see if you can persuade him to produce designs from now on and, for this module, to produce a design document that represents the current code, review that design, and then review the code against the design. If he will, then you could agree to lead a combined team design and code inspection for the module. Explain to him that, if the module design is really simple, it should be a simple task to produce a design document. However, it is surprising how often seemingly simple designs turn out not to be so simple when you try to document them.

If Marty does not agree to do this, then discuss the issue with the team leader and coach. With their support take the issue to the team to reinforce that the entire team needs to produce the agreed detailed design material for all of the team’s modules and for the team to persuade Marty to take the corrective actions necessary.

# Situation 5: The First Test Data

Questions and Answers:

## From these data, what quality problems do you anticipate?

Before we can begin the analysis we must determine if the data is valid. It appears that everybody seems to have done a reasonable job for the size and time data as well as for the defect data for reviews, inspections, and test. However, the developers for modules A and C, did not gather compile defect data. This is clear from the fact that they spent 2.8 and 3.6 hours respectively compiling their relatively small modules. This amount of time indicates that they must have spent much of that time fixing defects.

Second, looking at the A/FR it appears that sufficient focus was not given to the appraisal phases of the process.  Module A’s appraisal cost of quality only represents 13% of the total development time compared to the planned 30%. While module C’s appraisal cost of quality is very close to the planned, the failure cost of quality fare exceeds the planned.  Both of these situations suggest that reviews and inspections are not being conducted effectively resulting is many defects escaping the reviews and inspections processes and being found in later in the process, such as unit test.  This also implies that other defects have escaped to other levels of testing or even the customer.

Third, without compile data it is hard to judge code quality and to determine what the number of unit test defects signifies. If code quality were good, excessive unit test defects would suggest design problems. The number of compile defects is the only truly objective indicator of process quality.

Forth, the review yields were low. While a 46% and 42%, modules B and C respectively, code review yield is respectable, it is not good and suggests a need to update personal review checklists or the need for help in how to conduct reviews in addition to updating checklists. The 21% code review yield for module A indicates that the review was too fast. In this case, the 424 LOC per hour rate was much too fast to find many defects. The design review yields were also low, suggesting that the designs were reviewed like code instead of analyzed. Also, too little time was spent in the design reviews.

Finally, overall quality appears to be marginal. Since the yield before compile measure is only useful when most of the developers record their compile defects, the yield before test measure is all that you have. The 90% yield for module B is respectable but below the team’s goal of 97%. The yields for modules A and C are uncomfortably low and, if replicated with the remaining module, would imply a lot of final test time and poor delivered quality. As a predictor, the large number of defects found in unit test may represent a fraction of the defects still to be found in system test.

## What do you recommend that the team do?

The things that the team should do concern compile defects, review rates, design review practices, and code review checklists.

For compile defects, point out how helpful these data could be in improving review yields and code quality but do not get into an argument about recording compile defects. Many developers view gathering compile defect data as a waste of time and will not do it, almost regardless of anything you, the coach, or the team leader say. The best approach is to gather and use the data yourself and, when other developers ask how you manage to get high code review yields, show them how you use the compile defect data to update your checklists and to check on the quality of your code review practices.

Regarding review rates, the team established a 200 LOC/hour maximum rate during the launch and they should strive to abide by that rate, even if it means doing the review in multiple steps and repeating the steps that found defects.

Design review practices are a tougher problem, and you should get the coach to help you and your team mates define and use better methods.

For the code review checklists, ask the team members how often they update them and if they need help doing so. If they do, ask the coach to help.

Finally, before going to the team with these actions, have the coach review your conclusions and discuss your plans with the team leader.

# Situation 6: What Next?

Questions and Answers:

## What are your feelings about how you handled the special assignment?

You think you did a pretty good job with the team roles and with your development work.

## What are your thoughts about how Pete has treated you?

You were surprised that Pete did not thank you for your work and are not sure if he even knew what a good job you did. Perhaps you should have made more of an effort to tell him. In thinking about this question, you realize that all you did was deliver quality products on schedule, so there was no way that he could have known what you did unless somebody told him.

## Do you arrange to talk to Pete about your thoughts and, if so, what do you plan to say?

You decide to put together a brief factual report about what you did on Pete’s team, both on the roles and with your development work. Then you will arrange to meet with him to discuss it. Assuming that he agrees that you did a good job, you will also ask him to tell your manager. Finally, you might ask if he has any suggestions on how you could do a better job on your next project.

## Do you arrange to talk to manager about your thoughts and, if so, what do you plan to say?

After talking to Pete and assuming that he was pleased with your work, arrange to tell your manager the same story you told Pete. You might also describe what a great experience it was to work on a TSP team and suggest that the TSP could be a big help on your current project. If you would like to be a TSP coach or team leader someday, you could also mention that and see if your manager would support you in preparing for such a job.