Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

# Workbook for
 Capstone Exercise

PSP Advanced

The Software Engineering Institute (SEI)

is a federally funded research and development center

sponsored by the U.S. Department of Defense and

operated by Carnegie Mellon University.

This material is approved for public release.

Distribution is limited by the Software Engineering Institute to attendees.

PSP Advanced

Capstone Exercise

Overview

| #### Exercise #### Overview | The exercise includes the following topics. |  |
| --- | --- | --- |
|  | Section | See Page |
|  | Exercise Instructions | 2 |
|  | Situation 1: The New Project Assignment | 3 |
|  | Situation 2: The First Project Crisis | 4 |
|  | Situation 3: Joining a TSP Team | 5 |
|  | Situation 4: Quality Problems! | 6 |
|  | Situation 5: First Test Data | 7 |
|  | Situation 6: What Next? | 11 |

| #### Exercise #### Instructions | - Form into groups of three to five students. - When directed to by the instructor, read a situation description - Within your group, discuss the situation and answer the questions in the situation description - Be ready to share your answers in the class discussion. |
| --- | --- |

# Situation 1:  The New Project Assignment

You have just finished a project and your manager has called you in to describe the next assignment. The company’s flagship product development group has run into a snag and needs a utility developed to help them generate custom databases for large-scale testing. They have identified an open source utility that provides almost exactly what they need but a few simple modifications are required. That is to be your job and it must be done as quickly as possible.

The required utility is on the critical path for the next release of the flagship product and they must have it within three weeks. They have defined the needed modifications and will give the requirements to you today. Your manager tells you that the job is really pretty simple and should only take an experienced programmer like you a couple of weeks.

Questions:

- What do you suspect are the likely problems with this assignment?

- What do you say when your manager asks you to agree to finish in three weeks?

- What steps do you plan to take next?

- In making the schedule commitment to your manager, what would you say?

# Situation 2:  The First Project Crisis

After much debate, your manager reluctantly agreed to your four-week plan and, as projected, you have completed analyzing the open source utility. What you have found is the following.

- First, the open source utility was designed for small commercial databases and not for the large scientific arrays used with the flagship product.

- Second, the open source utility appears to have some rather rigid constraints on field size and the number of fields that could be handled in a given database.

- Third, based on the very limited documentation available, the open source utility seems to have a rather small fixed limit on the overall database size that it could handle.

- Fourth, you have also found several defects and undocumented “features” and suspect that there are more.

You could probably fix the commercial vs. scientific and fixed field size problems in a couple of weeks. However, if, as you suspect, there really is a serious constraint on database size, it would be easier and faster to develop a new utility than to fix the open source program. Unfortunately, verifying this would take another ten days.

Questions:

- What should you do now?

- What if anything should you tell your manager?

- What do you recommend that the company do now, and how do you support that recommendation?

# Situation 3: Joining a TSP Team

Management agreed with your recommendation to form a small development team to both investigate the feasibility of modifying the open-source utility and to develop a new utility program in parallel. If, after a thorough investigation, it turns out to be practical to modify the open source utility, the entire team will concentrate on making the changes. If, however, the modifications turn out to be too time consuming, the entire team will focus on developing a new utility program.

The new utility development team was formed in the flagship development group, it is to use the TSP, and management has selected Pete to be the team leader. This is an existing TSP team that has just finished releasing a feature for the next release of the flagship product. While you feel that you should have been asked to lead a small effort to do this job, your manager has asked you to take a special assignment on Pete’s team in the flagship development group instead.

Questions:

- How do you feel about taking this assignment?

- What do you tell your manager?

- How do you deal with Pete?

- What steps would you take to become a productive member of the team and to contribute to its success?

# Situation 4:  Quality Problems!

Pete has turned out to be a great team leader and the team appears to be a nice group to work with. The team launch went well and management reluctantly agreed to the team’s ten-week schedule. In launch meeting 1, the flagship program manager put great emphasis on product quality stressing that it had an even higher priority than schedule. She said that any errors in the test databases would likely waste a great deal of time in system testing for the next product release and that would cause serious problems.

Since this is only a four-member team, each member took two roles. In launch meeting 2, you volunteered for the quality manager and design manager jobs, which you got. In meeting 3, the team agreed to produce detailed designs and to doing both personal reviews and inspections of the design and code for all the new or modified modules. They also agreed that, if they decided that modifying the open source utility was the best strategy, they would also inspect the code for all the defect-prone modules found in testing.

Now, after three weeks, the team has dropped the open source option and is developing a new utility program. Marty comes to the team’s first inspection meeting with completed code. When asked about the design and his design and code review data Marty told you that “This was a simple program, so I didn’t bother with a design or design review but I did do a code review. I found nothing and have already started unit test. It looks real good.” After Marty agreed to get you his time and defect data that afternoon, you completed the inspection, but you are worried about the quality implications of Marty’s actions.

Questions:

- What problems do you think Marty’s actions could cause?

- What do you do?

# Situation 5:  First Test Data

The team is in week 5, and the first 3 of 12 modules have completed unit testing. The process and quality data for these modules are shown in Tables 1 and 2.

Questions:

- From these data, what quality problems do you anticipate?

- What do you recommend that the team do?

Quality Term Definitions:

- Process Yield - the percentage of defects removed before the first compile or test.

- Failure Cost of Quality - is the time spent in repair and rework plus the cost of any scrap.  In TSP, it is compile and test time.

- Appraisal Cost of Quality – are the costs of inspecting for defects.  In TSP, appraisal cost is the time spent in design and code reviews, including both personal reviews and inspection.

- AF/R – is the ratio between the Appraisal COQ and the Failure COQ.

# Situation 6:  What Next?

The team has delivered the new utility program to the flagship test-development team two days ahead of schedule and product quality appears to be excellent. The test-development team has found no problems in the two weeks they have been using it.

Your special assignment to the flagship group is over and you have returned to your old job under your previous manager. Pete, the team leader has not said anything about your or the team’s performance and you wonder if he knows what a good job you did as quality and design manager.

Questions:

- What are your feelings about how you handled the special assignment?

- What are your thoughts about how Pete has treated you?

- Do you arrange to talk to Pete about your thoughts and, if so, what do you plan to say?

- Do you arrange to talk to your manager about your thoughts and, if so, what do you plan to say?