## Slide 1: PSP Advanced Planning and Tracking Commitments
Notes: In this lecture we will look at ways on how to improve process performance through advanced planning and tracking

## Slide 3: Lecture Topics
Advanced Planning
Advanced Tracking
Summary: How do I use my personal data for improved planning and tracking?
Notes: We will spend a decent amount of time getting the rationale behind the statistical concepts, Will give examples on correlation and significance to ensure a good level of understanding
Go over what regression parameters are, and what they mean for size and time, Cover in good detail what “combining estimates” means, go over multiple regression
Explain prediction intervals and how we use them, Using the student tool,
Go over other sound estimating practices as they form the foundation for the PROBE methods used within PSP

## Slide 4: Planning Review
Need plans to:
  Make commitments
  Guide & track the work
Planning involves:
  Understanding requirements
  Estimating size & effort
  Producing tasks & schedules
Types of sizes
  (B)ase, (A)dded, (M)odified, (D)eleted, (R)eused
PROBE
Notes: A review of the “Fundamental Planning Concepts” lecture from the PSP Fundamentals course

## Slide 5: Advanced Planning
The TIME it takes to build a product is directly related to its SIZE!
Higher accuracy in size estimating translates into more accurate time estimates.
Mandatory ingredient: DISCIPLINE!
  Record data as you do the work (real time recording!)
  Record all the prescribed data
  Stick with the process
  Evaluate what works and what does not!
  Use your historical data to guide planning

## Slide 6: Prediction Interval (PI)
  Prediction Interval is the range around the “projected value” that the actual result is likely to fall within.
Notes: This is a bit tricky. The prediction interval is calculated for each new estimate. The range of the prediction interval is a function of both the historical data AND the unadjusted new estimate value (the estimated proxy size), i.e. the prediction range is different for different values of the estimated proxy size.

## Slide 7: Prediction Interval Size
The Prediction Interval size depends on the
  Percent likelihood the actual result will fall within the PI (increases with %, normally use 70%)
  “variance” of the historical data around the regression line (larger as variance increases)
  “distance” of the “new proxy estimate” from the historical data (larger as distance increases)

## Slide 8: Reducing Estimating Errors: Example
When estimating in parts, the total error will be less than the sum of the part errors.
  Errors tend to balance out.
  This assumes no common bias.
For a 1000-hour job with estimating accuracy of ± 50%, the estimate range is from 500 to 1500 hours.
If the estimate is independently made in 25 parts, each with 50% error, the
  total would be 1000 hours, as before
  estimate range would be from 900 to 1100 hours

## Slide 9: Combining Individual Errors
To combine independently-made estimates
Add the estimated values.
Combine the variances (squares) of the errors.
With 25 estimates for a 1000-hour job
Each estimate averages 40 hours.
The standard deviation is 50%, or 20 hours.
The variance for each estimate is 400 hours2.
The variances add up to 10,000 hours2.
The combined standard deviation is the square root of the sum of the variances, or 100 hours.
The estimate range is 900 to 1100 hours.

## Slide 10: Class Exercise - 1
Start with three estimates.
  A = 45 hours, + or - 10
  B = 18 hours, + or - 5
  C = 85 hours, + or - 25
What is the combined estimate?

## Slide 11: Class Exercise - 2
Start with three estimates.
  A = 45 hours, + or - 10
  B = 18 hours, + or - 5
  C = 85 hours, + or - 25
What is the combined estimate?
  total = 45 + 18 + 85 = 148 hours
What is the combined estimate range?

## Slide 12: Class Exercise - 3
Start with three estimates.
  A = 45 hours, + or - 10
  B = 18 hours, + or - 5
  C = 85 hours, + or - 25
What is the combined estimate?
  total = 45 + 18 + 85 = 148 hours
What is the combined estimate range?
  variance = 100 + 25 + 625 = 750
  range = square root of variance = 27.4 hours
What is the combined UPI and LPI?

## Slide 13: Class Exercise - 4
Start with three estimates.
  A = 45 hours, + or - 10
  B = 18 hours, + or - 5
  C = 85 hours, + or - 25
What is the combined estimate?
  total = 45 + 18 + 85 = 148 hours
What is the combined estimate range?
  variance = 100 + 25 + 625 = 750
  range = square root of variance = 27.4 hours
What is the combined UPI and LPI?
  UPI = 148 + 27.4 = 175.4 hours
  LPI = 148 – 27.4 = 120.6 hours

## Slide 14: Size Estimating for Parts other than LOC - 1
  Introduce a new unit of measurement when the current one does not correlate well for the task at hand:
  Introduce:
  A new unit of measurement,
  A new size proxy

## Slide 15: Size Estimating for Parts other than LOC - 2
The new unit of measurement should be:
  Useful for planning - size and time should correlate well
  Precise - there should be a precise size measurement definition
  Automatically countable
  Adaptable to the types of work we are likely to do in the future
  Provide the means to judge the accuracy of our estimates
The proxy should be :
  Easy to visualize at the beginning of the project
  Customizable to the special needs of using organizations
  Sensitive to any implementation variations that impact development cost and effort.

## Slide 16: Size Estimating for Parts other than LOC - 3
Possible proxies:
  Objects
  Screens
  Files
  Scripts
  Document Chapters
Possible unit of measurements:
  Lines of Text within a document
  Number of controls on a screen
While size measure depends on the job, the effort
measure is always Time.

## Slide 17: Selecting a Size Measure - 1
Start with historical data from some past projects
  Development effort
  Product characteristics (candidate size measures)
  Special conditions
Rank the products by development effort.
See what characteristics distinguish those products that took the greatest effort from those that took least.

## Slide 18: Selecting a Size Measure - 2
Determine if the candidate size measure is related to effort
  Create a graph with the candidate size measure on the horizontal axis and effort on the vertical axis
  Plot each pair of historical data (candidate size measure, effort) as a point on the graph
  If the points define a line, then the candidate size measure is related to effort and can be used for planning.
There may be no single best size measure. A combination of size measures could be needed.

## Slide 19: Example: Text Pages versus Writing Time

## Slide 20: Using Multiple Proxies
With size/hour data for several proxies:
  estimate each as before
  combine the total estimates and prediction intervals as just described
Use multiple regression if:
  there is a correlation between development time and each proxy
  the proxies do not have separate size/hour data

## Slide 21: Intuitive Size Ranges
In judging size, our intuition is generally based on a normal distribution.
That is, we think of something as of average size if most such items are about that same size.
We consider something to be very large if it is larger than almost all items in its category.
When items are distributed equally around the mean, it is called a normal distribution.
With normally distributed data, the ranges should remain reasonably stable with the addition of new data points.

## Slide 22: The Distribution of Size Data - 1
With a large volume of data, you could calculate the mean and standard deviation of that data.
For the size ranges
  Medium would be the mean value.
  Large would be mean plus one standard deviation.
  Small would be mean minus one standard deviation.
  Very large would be mean plus two standard deviations.
  Very small would be mean minus two standard deviations.
This method would provide suitably intuitive size ranges if the data were normally distributed.

## Slide 23: The Distribution of Size Data - 2
Program size data are not normally distributed.
  many small values
  a few large values
  no negative values
With size data, the mean minus one or two standard deviations often gives negative size values.
The common strategy for dealing with such distributions is to treat it as a log-normal distribution.

## Slide 24: The Log-Normal Distribution
To normalize size data, do the following:
Take the natural logarithm of the data.
Determine the mean and standard deviation of the log data.
Calculate the average, large, very large, small, and very small values for the log data.
Take the inverse log of the ranges to obtain the range size values.
This procedure will generally produce useful size ranges.

## Slide 25: Other Estimating Methods
The following methods are important not only because they have each been found useful but also because their concepts form the foundation for the PROBE method used with the PSP.
  Wideband-Delphi
  Fuzzy Logic
  Standard-Component
  Agile Story Points
  Function Points

## Slide 26: Estimating Considerations in Planning
Estimating Bias
Incomplete-knowledge bias
Over-compensation
Selecting proper level of abstraction
Large jobs
Unprecedented products
Improving estimating accuracy by sub-dividing estimates into parts
Selecting a size measure that correlates with development time

## Slide 27: Summary: Advanced Planning
  Have discipline, record real time, stick to process.
  Choose a unit of measure that correlates well with development time.
  Choose intuitive proxies that are easy to visualize.
  Continuously check your estimates against prediction intervals.
  Improve estimating accuracy by subdividing estimates into parts.
  Introduce a new unit of measurement when the current one does not correlate well.
  Combine other estimating methods as found suitable.

## Slide 28: Advanced Tracking
No plan survives contact with the enemy!
[Helmuth von Moltke the Elder]
  Requirements always change.
  Tasks get cancelled or deferred.
  Some tasks are dropped, and others are added
Understanding Plan Status
Keeping the Team Owning the Commitment

## Slide 29: Understanding Schedule Status
The primary thing you want to know is this: Will the team be able to meet its committed date?
To determine this, you must look at three things.
  Does the team’s current plan meet the committed date?
  What is the team’s status against the current plan?
  Based on the current plan, what is the projected completion date?

## Slide 30: Status Against The Current Plan
To determine a project’s current status, compare the project’s current cumulative EV to the planned cumulative PV.
The project is
  ahead if the EV is greater than the PV
  behind if the EV is less than the PV
The amount ahead or behind can be estimated by dividing the PV-EV difference by the average EV earned per week.

## Slide 31: Estimating Project Completion
To estimate the project completion date with EV
  Determine the EV needed to finish.
  Determine the rate at which the team is earning EV.
  Determine how long it will take the team to earn the remaining EV.

## Slide 32: Cautions
Earned Value (EV) tracking/predictions:
  only works when the plan is realistic
  assumes the estimate errors are reasonably consistent
  assumes the project resources are planned
Notes: Bullet 1 - EV predictions are not good when the plan is not based on reality. For instance, it the plan for testing is 10% of the development effort and it really takes 40% of the development effort, the EV prediction of when testing will be complete will be way off.
Bullet 2 – Since the EV is predicting based on comparing estimates to actuals for the work completed and projecting that relationship into the future, it assumes that relationship holds for the future work. For instance, if your estimates have been 10% under on the work completed so far, the EV predictions assume that your estimates on the remaining work are also 10% under.
Bullet 3 – To make an EV prediction of when the work will be finished, you need to know the planned resources that will be available through the predicted finish date.

## Slide 33: Predicted End Date
A rough manual estimate of a balanced plan predicted end date can be achieved by:
  dividing the number of hours of work remaining by the average team hours worked per week
  taking into consideration the misestimating factor
To get a good earned value predicted end date from the TSP tool:
  Have the team balance the workload.
  Have the planning manager and coach review the individual plans for any anomalies with respect to the predicted end date.

## Slide 34: TSP Earned Value Review
PV – planned value measures each task’s % of the overall project plan.
A task’s PV is earned (becomes EV) when a task is completed (no partial credit).
Regardless of the actual time the task took, the task’s earned value is the task’s PV.
A project’s earned value (cumulative EV) is the total of the PV of all project tasks completed to date.

## Slide 35: EV Example
Based on this chart, what is this team’s status?
Notes: Discuss the team status with the class
Is the team behind?
Why is it behind? – kind of a trick answer, there is not enough information to tell.
What can cause a team to get behind schedule? – record on a flip chart

## Slide 36: Why Behind?
Team cannot get enough task hours in per week.
Estimates turn out to be low.
Change requests come in that ‘must’ be done.
Task were missed in the launch.
An external dependency does not come in on time.

## Slide 37: Possible Problems
A large number of task hours for unfinished tasks could indicate a problem. Normally, this should be less than 20 per team member. Possible problems include the following.
The plan is “bad” because:
  tasks are too large
  task breakdown is wrong
The team is “blocked” because it is:
  waiting on a dependency
  encountering a problem

## Slide 38: Tracking Status
How precisely must we track our work?
Fred Brooks: “Schedules slip a day at a time.”
If you can’t recognize a one-day slip, you only take action when the delay is obvious.
By the time the delay is obvious, it is usually too late to recover!
Fred Brooks
Notes:   As Fred Brooks said, “Schedules slip a day at a time.” To maintain schedules and costs, these one-day slips must be recovered the next day or the delays will soon compound and become completely unmanageable. With current practices, schedule slips are typically undetectable until projects are weeks or months late. The only clear indicators are code complete or test completion. Even then, these are often very fuzzy dates. The code is rarely complete when the developers say it is and testing is typically stopped when all or most of the existing test cases run, not when some quality criteria are met.

## Slide 39: Summary: Advanced Tracking
  Plans always change all the time.
  Use Planned Value and Earned Value to understand status.
  Regularly re-estimate project completion based on current Earned Value rate.
  Recognize 1-day slips.
  If behind schedule, analyze reasons.
  Re-plan as needed and have the team balance the workload.

## Slide 40: Messages to Remember
In order to properly plan and track:
  collect and record the data needed to manage the plan
  manage your personal plan
  know the status of your commitments
  proactively manage and communicate the risks and issues with your commitments
  regularly report your status to your management!