## Slide 1: PSP Advanced Tutorial: PROBE Methods A & B with Process Dashboard
Notes: This tutorial will go into the details of how PROBE Methods are evaluated for best fit based on the individual’s historical data.

## Slide 3: Lecture Topics
Using PROBE to make size and time estimates
Overview of PROBE methods A & B
Method selection criteria for “size” and “time” in methods A & B
A review of
  PROBE Size Estimating Template
  Derived measures
PROBE historical data
PROBE charts
Notes: We will provide a refresher for the class and go over the PSP Size Estimating Template in the student tool.
It may be a good idea to have the students bring up their student tool.
Engaging the class to look at their tool will also help keep the focus on the tutorial and eliminate internet surfing and email correspondence during the lecture.

## Slide 4: Using PROBE
PROBE is used to make continuously improving size and time estimates by
  collecting historical data
  calculating regression parameters on historical data
  adjusting the estimates for trends
PROBE methods A & B are introduced this week.
What differentiates methods A & B from method C, introduced in PSP Fundamentals, is that methods A & B use linear regression on your historical data to calculate the projected size and time estimates.

## Slide 5: Minimum Data for Using Regression
The regression line represents the best fit (or smallest possible distance from the regression line to the data points).
When we have only 2 data points, the regression line goes right through them for a perfect fit, but it is not meaningful.
For the regression line to act as the predictor, we need more data points (at least 3).

## Slide 6: Correlation
Correlation (r) (a.k.a. Correlation Coefficient): Degree to which two sets of data are linearly related.
Correlation squared (r2): Descriptive measure between zero and one, indicating how good one term is at predicting another.
An r2 of 1 is considered a perfect fit.
To use methods A & B, an r2 of 0.5 or higher is required.
Chart: 
| 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100
 | 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100
Chart: 
| 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100
 | 100 | 95 | 90 | 85 | 80 | 75 | 70 | 65 | 60 | 55 | 50 | 45 | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0
Negative Relationship (r = -1)
Positive Relationship (r = +1)

## Slide 7: Correlation & Significance
Significance is a measure that indicates the probability that the correlation occurred by chance.
Chart: LOC
| 51 | 66 | 77 | 88 | 103 | 105
Hours | 2 | 0.86667 | 1.25 | 4.2833 | 1 | 2.4167
Chart: LOC
| 51 | 66 | 73 | 77 | 88 | 95 | 97 | 103 | 105 | 110 | 128 | 136 | 144 | 152 | 168 | 174 | 186 | 190 | 210 | 222 | 234 | 248 | 256 | 287 | 303 | 327 | 355 | 386 | 402 | 455
Hours | 0.75 | 0.86667 | 1.4667 | 1.25 | 4.2833 | 2 | 1.8333 | 1 | 2.4167 | 3.1667 | 2.5 | 3.1167 | 3.3333 | 8.3333 | 3.8333 | 4.0667 | 2.5 | 3.6667 | 6.6667 | 5.45 | 6.3333 | 6.95 | 6.6667 | 7 | 2 | 8.3833 | 11.3333 | 13.1667 | 8.7833 | 9.3167
When the number of items in the data set grows, correlation tends to be reliable. When this is the case, pay attention to correlation.
When the number of data points is small, pay attention to significance.
Notes: Note, there is always the possibility that a high correlation was the result of chance (just a random event) and there is not a real cause and effect relationship between the two data sets. Significance is measure of that probability.
The point here is that when you have only a small number of data points in the regression and you get a good correlation, you should also check the significance measure to determine if the relation is likely due to chance and is not a true cause/effect relationship.
The students will implement the significance calculation in assignment on day 3 of this course.

## Slide 8: Adjusting Estimates with Linear Regression
In PROBE “y = mx + b” equates to:
y (adjusted estimate) = b (b0) + m (b1) * x (Estimated Proxy Size)
Projected Added and Modified Size = b0 + b1 * estimated proxy size
b0 is a constant bias in the size, e.g., overhead LOC and/or constant estimating bias
b1 is the factor for the ratio of under-estimates and over-estimates
Estimated Development Time = b0 + b1 * estimated proxy size
b0 is a constant bias in the estimated time, e.g., overhead time and/or constant estimating bias
b1 is the average additional time to develop one line of code
PROBE methods A & B calculate the trend line with linear regression:
Chart: LOC
| 51 | 66 | 73 | 77 | 88 | 95 | 97 | 103 | 105 | 110 | 128 | 136 | 144 | 152 | 168 | 174 | 186 | 190 | 210 | 222 | 234 | 248 | 256 | 287 | 303 | 327 | 355 | 386 | 402 | 455
Hours | 0.75 | 0.86667 | 1.4667 | 1.25 | 4.2833 | 2 | 1.8333 | 1 | 2.4167 | 3.1667 | 2.5 | 3.1167 | 3.3333 | 8.3333 | 3.8333 | 4.0667 | 2.5 | 3.6667 | 6.6667 | 5.45 | 6.3333 | 6.95 | 6.6667 | 7 | 2 | 8.3833 | 11.3333 | 13.1667 | 8.7833 | 9.3167
Notes: Note that beta0 is not strictly overhead (LOC or time), it also accounts for a consistent constant estimating bias.

## Slide 9: What Do Negative b0 and b1 Mean?
The y-intercept (b0) represents overhead and constant estimating bias.
While overhead can only be positive, constant estimating bias can be negative due to a strong bias towards over-estimating.
Only small, relative to the final estimate, negative values of b0 are acceptable.
Negative slope (b1) means that as the proxy size estimate increases, the size and/or effort decreases! This should not be true, thus negative values for b1 are not acceptable.
Notes: It’s important to note that negative values of beta0 are valid. They can arise due to a constant estimating bias to overestimate. The regression compensates for this tendency to overestimate by a constant amount with a negative beta0.
Note that the absolute value of B0 is used in the PROBE method selection scripts. A small negative B0 is acceptable because it will not make the estimate unreasonable. The script guidelines work well enough for planning purposes.

## Slide 10: PROBE Methods A & B Overview
PROBE method A is the most preferred method.
  Method A requires a minimum of 3 historical data points that correlate.
    estimated proxy size (E) and actual A&M for “size” estimation
    estimated proxy size (E) and actual development time for “time” estimation
  If the correlation and regression parameter values are within the selection criteria, method A is used.
PROBE method B is the next preferred method.
  Method B requires a minimum of 3 historical data points that correlate.
    plan A&M and actual A&M for “size” estimation
    plan A&M and actual development time for “time” estimation
  If the correlation and regression parameter values are within the selection criteria, Method B is used.
When PROBE methods A or B do not meet the selection criteria, use
  Method C if you have some historical data
    Method C uses averaging of historical data and does not use regression.
  Method D if you have no historical data
    Method D uses “engineer’s best guess.”

## Slide 11: Rules for Size Method Selection
First check if method A can be used.
  You have three or more data points (estimated proxy size and actual A&M) that correlate (r2 ≥ 0.5 ).
  The absolute value of b0 is less than about 25% of the expected size of the new program.
  b1 is between 0.5 and 2.
If method A cannot be used, check method B.
  You have three or more data points (plan A&M and actual A&M) that correlate (r2 ≥ 0.5 ).
  The absolute value of b0 is less than about 25% of the expected size of the new program.
  b1 is between 0.5 and 2.
If method B cannot be used and you have any data on plan A&M and actual A&M, use method C.
If you have no historical data, use method D.
Notes: Note the use of about 25% in the 2nd and 6th bullets. This comes explicitly from the PROBE Estimating script. The 25% is a guide not a hard criterion. Suggest to your students that if b0 is greater than 25% of the expected size of the program, they consult with you about using it.

## Slide 12: Rules for Time Method Selection
First check if method A can be used.
  You have three or more data points (estimated proxy size and actual time) that correlate (r2 ≥ 0.5 ).
  b0 should be near 0 (substantially smaller than the expected development time for the new program).
  b1 should be within 50% of 1/(historical productivity).
If method A cannot be used, check method B.
  You have three or more data points (plan A&M and actual time) that correlate (r2 ≥ 0.5 ).
  b0 should be near 0 (substantially smaller than the expected development time for the new program).
  b1 should be within 50% of 1/(historical productivity).
If method B cannot be used and you have historical data, use method C.
If you have no historical data, use method D.
Notes: Historical productivity is the to date productivity for the previously developed programs.

## Slide 13: Where Do the Size Guidelines Come From?
Rule for Size b0
  Having the overhead and constant bias (b0) almost as big as the finished product would not make sense. It would mean estimated proxy size has little influence on the estimate size.
  The absolute value of b0 should be less than about 25% of the expected size of the finished product.
Rule for Size b1
  Normally, the slope (b1) should be near 1.0. Values between 0.5 and 2.0 are acceptable.
  A value of less than 0.5 or greater than 2.0 indicates a large proportional-over or -under bias and should not be used unless your instructor agrees.

## Slide 14: Where Do the Time Guidelines Come From? - 1
Rule for Time b0
  Having the overhead and constant bias (b0) almost as large as the final estimated time would not make sense. It would mean the estimated proxy size has little influence on the estimated time.
  The absolute value of b0 should be significantly smaller than the estimated development time.

## Slide 15: Where Do the Time Guidelines Come From? - 2
Rule for Time b1
  “Time” b1 needs to be within 50% of (1/historical productivity).
  Example:
    How long would it take to code one LOC if historical average productivity is 30 LOC per hour?
  30 LOC 1 hr
  1 LOC x hrs
  ---------------------------
  30x = 1  x = 1/30 = 2 minutes per LOC
    For this example, if b1 is not between 1 and 3 minutes per LOC (within 50%), the applied correction is too great and should not be used.

## Slide 16: PROBE Wizard
The rules and guidelines for PROBE method selection can be complex. In the Process Dashboard, the PROBE Wizard automates the evaluation of these rules to reduce the likelihood of planning errors.
The PROBE Wizard uses estimated proxy size (E) as an input to its calculations. So before you can use the PROBE Wizard, you must produce an estimated proxy size (E).
You produce an estimated proxy size (E) by completing the upper portion of the PSP Size Estimating Template.

## Slide 17: PSP Size Estimating Template
This is the upper part of the PSP Size Estimating Template where the detailed size estimating is performed.
We are interested in
Added Size =
Base Additions + Part Additions
Estimated proxy size =
Base Additions + Part Additions
+ Modifications
No effort is spent in development on inclusion of Reused parts so they are not included in A or E.
Notes: This slide is a refresher to get everyone’s understanding on the same page.
We are interested in two derived measures: A = BA + PA and E = BA + PA + M.
It is a good idea to remove any confusion about “base” and “reused” here, if there is any!
Also remind the students that if most of the newly added parts are of medium size it is indicative of a good conceptual design, not too detailed where many parts are too small, and not too high level where many parts are too large.

## Slide 18: Follow Along …
Download the PROBE Methods A & B Sample DB for Dashboard.zip data backup file.
In your Process Dashboard, choose “C → Tools → Open Dataset.” Open the ZIP file you just downloaded.
A second Process Dashboard window will open, showing the name of the ZIP file in the title bar.
This second window is showing example data from the ZIP file. Use this second window to follow along with this tutorial.

## Slide 19: Launching the PROBE Wizard
After the conceptual design has been entered into the upper portion of the PSP Size Estimating Template, you can click the hyperlink to launch the PROBE Wizard.

## Slide 20: Verify Estimated Proxy Size
The first step of the PROBE Wizard is to review the estimated proxy size that you have produced.

## Slide 21: Review Historical Data - 1
Next, the PROBE Wizard will display a list of the historical data that will be used for the calculations.
Review this list for
  Completeness
  Known outliers

## Slide 22: Review Historical Data - 2
The PROBE Wizard will look through your past projects to create this list of historical data.
Only projects that have been marked complete will be included in the list. If a recently finished project is not on the list, open its Project Plan Summary form and make certain it has been marked complete.
Also, review the data in the Actual Size column. If data is missing or “#VALUE!”, you forgot to enter the actual size for a recently completed project. You can open the Project Plan Summary for that project to fix the problem.
If you do not resolve these problems, the missing/incomplete data will be excluded from the PROBE calculations.

## Slide 23: Review Historical Data - 3
A past project could be an outlier if something unusual occurred during its development. For example
  The requirements changed.
  The project characteristics are different than the other historical data points (e.g. new development vs legacy changes).
If you are aware of any problems such as these on past projects, you can mark individual data points as outliers.
A poor estimate is not a valid reason to mark a data point as an outlier.
Follow Along: JD knows that his instructor altered the requirements for Program 5 after he discovered a limitation in a platform library that he could not work around. Check the box to mark Program 5 as an outlier.

## Slide 24: Select PROBE Method for Size - 1
Next, the PROBE Wizard will
  Perform calculations for PROBE methods A, B, and C for size
  Eliminate methods that cannot be used because they violate the selection criteria (e.g. bad b0 or b1)
  Sort the available options, placing the most viable options at the top of the list
  Display the choices for your consideration.
Use your engineering judgment to evaluate the options, then select the one that you feel produces the most realistic estimate for the project.

## Slide 25: Select PROBE Method for Size - 2

## Slide 26: Select PROBE Method for Size - 3

## Slide 27: Viewing Charts of Historical Data
Chart thumbnails are displayed next to the various PROBE methods. Click on a thumbnail to open a larger chart.
The charts are useful for quick, visual verification of correlation and also for identification of possible outliers.
A data point may look like an outlier when there are not enough data points. Wait to accumulate enough data points to make a sound judgment call on an outlier.
If you determine that a point is an outlier, click the Back button to return to the “review historical data” step.
Notes: Note that based on an individual’s perception a visually drawn regression line may or may not be accurate!
On this example explain that when the data point circled in red is marked as an outlier we get a pretty good regression, but this would be the wrong approach as there are too few data points to make a sound judgment call!
Note: Student tool does not draw a regression line. It is best to go back to PROBE Size Estimating Template and look at the calculated correlation value and regression parameters!

## Slide 28: PROBE Glossary Terms
The PROBE Wizard includes a glossary to help with the definitions of various terms. When you see a word or phrase written in dark blue letters, you can click on the word for an explanation of its meaning.

## Slide 29: PROBE Method A Selection Criteria for Size - 1
The PROBE Wizard automatically checks the selection criteria rules on our behalf. But for this tutorial, let’s review these rules.
Size selection criteria (Step-1)
  Is the correlation (r2) equal to or greater than 0.5?
  In this example, r2 meets the requirement (0.83)
  Reminder:
  Method A uses estimated proxy size (E) and Actual A&M for “size”, and
  estimated proxy size (E) and Actual development time for “time” estimation.
Notes: Method A fits the selection criteria, so it should be selected.
A couple things to note about the prediction interval
  It is not part of the selection criteria for the method choice.
  The magnitude of the prediction interval is mainly affected by 2 items
    the variation of the historical data about the regression line
    The “distance” of the new estimated proxy size (E) from the historical data
  The larger either of these is, the larger the prediction interval is
  In this example, the variation of the historical data about the regression line is “small” – see the earlier charts. But the “distance” of the new estimated proxy size from the historical data is “large”. So although the historical data has little fluctuation, because the new estimated proxy size (e) is well outside the range of the existing data, the prediction interval is large.

## Slide 30: PROBE Method A Selection Criteria for Size - 2
Size selection criteria (Step-2)
  Absolute value of b0 should be near 0: less than about 25% of the expected size of the new program. b0 represents overhead and/or constant estimating bias, so it should not be more than about 25% of the projected A & M size (P).
  b1 represents proportional estimating bias and proportional overhead. It should be between 0.5 and 2.0.
Notes: Method A fits the selection criteria, so it should be selected.
A couple things to note about the prediction interval
  It is not part of the selection criteria for the method choice.
  The magnitude of the prediction interval is mainly affected by 2 items
    the variation of the historical data about the regression line
    The “distance” of the new estimated proxy size (E) from the historical data
  The larger either of these is, the larger the prediction interval is
  In this example, the variation of the historical data about the regression line is “small” – see the earlier charts. But the “distance” of the new estimated proxy size from the historical data is “large”. So although the historical data has little fluctuation, because the new estimated proxy size (e) is well outside the range of the existing data, the prediction interval is large.

## Slide 31: PROBE Method A Selection Criteria for Size - 3
  b0 is 25.7 compared to the Projected A&M size of 321, which satisfies the “near zero, less than about 25%” criterion.
  b1 is 1.15, which satisfies the “between 0.5 & 2.0” criterion.
  Prediction Range is +/-64.2 LOC on a Projected A&M of 321.
  The wide predication interval (128 LOC) can be indicative of variation in data (too much historical fluctuation). In this case, it is actually caused by the distance of the estimated proxy size (E) from the historical data.
  Method A for size estimating is acceptable.
  Select it and click Continue.
Notes: Method A fits the selection criteria, so it should be selected.
A couple things to note about the prediction interval
  It is not part of the selection criteria for the method choice.
  The magnitude of the prediction interval is mainly affected by 2 items
    the variation of the historical data about the regression line
    The “distance” of the new estimated proxy size (E) from the historical data
  The larger either of these is, the larger the prediction interval is
  In this example, the variation of the historical data about the regression line is “small” – see the earlier charts. But the “distance” of the new estimated proxy size from the historical data is “large”. So although the historical data has little fluctuation, because the new estimated proxy size (e) is well outside the range of the existing data, the prediction interval is large.

## Slide 32: PROBE Method A Selection for Time - 1
Next, the Wizard will present the PROBE methods for Time.
Once again, the wizard evaluates the selection criteria, eliminates unacceptable options, and sorts the most viable options first.
For this tutorial, let’s review its assessment of PROBE method A for Time.

## Slide 33: PROBE Method A Selection Criteria for Time - 2
Time selection criteria (Step-2)
  b0 should be near 0 (substantially smaller than the expected development time for the new program).
  b1 should be within 50% of .
(0.5 * ) < b1 < + (0.5* )
1
historical productivity
)
(
  Reminder:
  Method A uses estimated proxy size (E) and Actual A&M for “size”, and
  estimated proxy size (E) and actual development time for “time” estimation.
1
historical productivity
)
(
1
historical productivity
)
(
1
historical productivity
)
(
Notes: b0 and b1 should be explained here as to what they mean regarding “time”. In LOC/Size, b0, represented overhead such as declarations, setting up development environment and/or constant estimating bias.
In “time” b0 represents time spent that isn’t related to size (possibly planning and/or postmortem and/or overhead items) and constant estimating bias.
b1 should be within half of 1/”Historical Productivity”. The rational for this is that since the B0 should be substantially smaller than the expected development time and that the Projected A&M should be somewhere between ½ and 2x the estimated proxy size, b1, which is the main determinate of the time estimate, should be within 0.5 and 1.5 the reciprocal of the historical productivity expressed in minutes/LOC.
NOTE, however, this is an academic exercise in this case since b1 is negative, we can immediately conclude that method A is not usable for time!
NOTE: The historical productivity needs to be converted to minutes per LOC instead of Hours per LOC before making the comparison.

## Slide 34: PROBE Method A Selection Criteria for Time - 3
  1/b1 is -54.9 LOC/h. A negative b1 is never acceptable. We can immediately conclude that method A is not usable for time.
  b0 is 3.86 hours (compared to a hypothetical total development time of -0.8 hours), which is totally outside of acceptable parameters.
  b0 also does NOT satisfy the selection criteria.
  If b1 had been positive, how would we check its selection criterion?
Notes: Ask why a negative beta1 is never acceptable.

## Slide 35: PROBE Method A Selection Criteria for Time - 4
  If b1 was positive, you would then check if it met the criterion.
  reciprocal of productivity = (1/44.5) = 0.022 hours/LOC
  0.022 - (0.022/2) < b1 < 0.022 + (0.022/2)
  0.011 < b1 < 0.033
  29.7 < 1/b1 < 89 LOC/hour
  Because it is negative, b1 does not satisfy method A’s selection criterion for Time estimating.
  Our next option for time is method B.
Notes: Note that historical productivity is LOC/Hr, so we multiply the result by 60 to get the per minute value!

## Slide 36: PROBE Methods B and C
Method B uses
  plan A&M and actual A&M for “size” estimation
  plan A&M and actual development time for “time” estimation
Method C uses averaging of historical and does not use regression.
Other than using a different set of data, the steps in method B are identical to method A.
Let’s look at PROBE method B next and see if it provides a better fit.
Notes: We show on the slide where the data is coming from for use in Method B.
Also mention that it is discouraged to mark a data point as an outlier as fluctuation is normal and evaluation should be deferred until substantial amount of data is collected.

## Slide 37: PROBE Method B Selection Criteria for Time
  R2 of 0.91 is equal to or greater than 0.5. 
  1/β1 of 54.2 LOC/h is positive and between 29.7 and 89 LOC/h. 
  β0 of 0.72 hours is substantially smaller than the expected development time of 6.65 hours. 
  Method B for Time estimating is acceptable. Select it and Continue.
Notes: In this example, the Time selection criteria was not met by Method A, then we came into Method B and found it to be acceptable

## Slide 38: Final Consistency Check
Our PROBE-adjusted size and time estimates were made independently of each other, using different linear relationships.
As a result, it is possible to produce an overestimate for size and underestimate for time (or vice versa).
The final page of the wizard compares your newly created estimates to your historical productivity for consistency.

## Slide 39: Ending the “Follow Along” Portion of the Tutorial
If you have been following along in the Process Dashboard during this tutorial, you will currently have two Process Dashboard windows open.
  The main window, which displays “Process Dashboard” in the title bar, is displaying your actual metrics data.
  The title bar for the second window will be displaying the name of the data backup ZIP file that you created for this tutorial.
Changes in this second window will be discarded when the window is closed, so it is important not to record any real data there. To prevent an accidental situation where your metrics are recorded in the wrong window,
please close that second window now.

## Slide 40: Messages to Remember
PROBE offers four methods to arrive at size and time estimates.
  Method A is the most preferred choice.
    requires a minimum of 3 data points that correlate
    uses estimated proxy size (E) and actual A&M for “size” estimation
    uses estimated proxy size (E) and actual development time for “time” estimation
    evaluates correlation along with regression parameters
  Method B uses
    requires a minimum of 3 data points that correlate
    plan A&M and actual A&M for “size” estimation
    plan A&M and actual development time for “time” estimation
    evaluates correlation along with regression parameters
  Method C uses averaging of historical data and does not use regression.
  Method D uses “engineer’s best guess.”