## Slide 1: PSP Advanced Tutorial: PROBE Methods A & B with the Student Workbook
Notes: This tutorial will go into the details of how PROBE Methods are evaluated for best fit based on the individual’s historical data.

## Slide 3: Lecture Topics
Using PROBE to make size and time estimates
Overview of PROBE methods A & B
Method selection criteria for “size” and “time” in methods A & B
A review of
  PROBE Size Estimating Template
  Derived measures
PROBE historical data
PROBE charts
Please make a copy of your student database,
as you will be exploring the tool and experimenting with the options.
Notes: We will provide a refresher for the class and go over the PSP Size Estimating Template in the student tool.
It may be a good idea to have the students bring up their student tool.
Engaging the class to look at their tool will also help keep the focus on the tutorial and eliminate internet surfing and email correspondence during the lecture.

## Slide 4: Using PROBE
PROBE is used to make continuously improving size and time estimates by
  collecting historical data
  calculating regression parameters on historical data
  adjusting the estimates for trends
PROBE methods A & B are introduced this week.
What differentiates methods A & B from method C, introduced in PSP Fundamentals, is that methods A & B use linear regression on your historical data to calculate the projected size and time estimates.

## Slide 5: Minimum Data for Using Regression
The regression line represents the best fit (or smallest possible distance from the regression line to the data points).
When we have only 2 data points, the regression line goes right through them for a perfect fit, but it is not meaningful.
For the regression line to act as the predictor, we need more data points (at least 3).

## Slide 6: Correlation
Correlation (r) (a.k.a. Correlation Coefficient): Degree to which two sets of data are linearly related.
Correlation squared (r2): Descriptive measure between zero and one, indicating how good one term is at predicting another.
An r2 of 1 is considered a perfect fit.
To use methods A & B, an r2 of 0.5 or higher is required.
Chart: 
| 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100
 | 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100
Chart: 
| 0 | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100
 | 100 | 95 | 90 | 85 | 80 | 75 | 70 | 65 | 60 | 55 | 50 | 45 | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0
Negative Relationship (r = -1)
Positive Relationship (r = +1)

## Slide 7: Correlation & Significance
Significance is a measure that indicates the probability that the correlation occurred by chance.
Chart: LOC
| 51 | 66 | 77 | 88 | 103 | 105
Hours | 2 | 0.86667 | 1.25 | 4.2833 | 1 | 2.4167
Chart: LOC
| 51 | 66 | 73 | 77 | 88 | 95 | 97 | 103 | 105 | 110 | 128 | 136 | 144 | 152 | 168 | 174 | 186 | 190 | 210 | 222 | 234 | 248 | 256 | 287 | 303 | 327 | 355 | 386 | 402 | 455
Hours | 0.75 | 0.86667 | 1.4667 | 1.25 | 4.2833 | 2 | 1.8333 | 1 | 2.4167 | 3.1667 | 2.5 | 3.1167 | 3.3333 | 8.3333 | 3.8333 | 4.0667 | 2.5 | 3.6667 | 6.6667 | 5.45 | 6.3333 | 6.95 | 6.6667 | 7 | 2 | 8.3833 | 11.3333 | 13.1667 | 8.7833 | 9.3167
When the number of items in the data set grows, correlation tends to be reliable. When this is the case, pay attention to correlation.
When the number of data points is small, pay attention to significance.
Notes: Note, there is always the possibility that a high correlation was the result of chance (just a random event) and there is not a real cause and effect relationship between the two data sets. Significance is measure of that probability.
The point here is that when you have only a small number of data points in the regression and you get a good correlation, you should also check the significance measure to determine if the relation is likely due to chance and is not a true cause/effect relationship.
The students will implement the significance calculation in assignment on day 3 of this course.

## Slide 8: Adjusting Estimates with Linear Regression
In PROBE “y = mx + b” equates to:
y (adjusted estimate) = b (b0) + m (b1) * x (estimated proxy size)
Projected Added and Modified Size = b0 + b1 * estimated proxy size
b0 is a constant bias in the size, e.g., overhead LOC and/or constant estimating bias
b1 is the factor for the ratio of under-estimates and over-estimates
Estimated Development Time = b0 + b1 * estimated proxy size
b0 is a constant bias in the estimated time, e.g., overhead time and/or constant estimating bias
b1 is the average additional time to develop one line of code
PROBE methods A & B calculate the trend line with linear regression:
Chart: LOC
| 51 | 66 | 73 | 77 | 88 | 95 | 97 | 103 | 105 | 110 | 128 | 136 | 144 | 152 | 168 | 174 | 186 | 190 | 210 | 222 | 234 | 248 | 256 | 287 | 303 | 327 | 355 | 386 | 402 | 455
Hours | 0.75 | 0.86667 | 1.4667 | 1.25 | 4.2833 | 2 | 1.8333 | 1 | 2.4167 | 3.1667 | 2.5 | 3.1167 | 3.3333 | 8.3333 | 3.8333 | 4.0667 | 2.5 | 3.6667 | 6.6667 | 5.45 | 6.3333 | 6.95 | 6.6667 | 7 | 2 | 8.3833 | 11.3333 | 13.1667 | 8.7833 | 9.3167
Notes: Note that beta0 is not strictly overhead (LOC or time), it also accounts for a consistent constant estimating bias.

## Slide 9: What Do Negative b0 and b1 Mean?
The y-intercept (b0) represents overhead and constant estimating bias.
While overhead can only be positive, constant estimating bias can be negative due to a strong bias towards over-estimating.
Only small, relative to the final estimate, negative values of b0 are acceptable.
Negative slope (b1) means that as the proxy size estimate increases, the size and/or effort decreases! This should not be true, thus negative values for b1 are not acceptable.
Notes: It’s important to note that negative values of beta0 are valid. They can arise due to a constant estimating bias to overestimate. The regression compensates for this tendency to overestimate by a constant amount with a negative beta0.
Note that the absolute value of B0 is used in the PROBE method selection scripts. A small negative B0 is acceptable because it will not make the estimate unreasonable. The script guidelines work well enough for planning purposes.

## Slide 10: PROBE Methods A & B Overview
PROBE method A is the most preferred method.
  Method A requires a minimum of 3 historical data points that correlate.
    estimated proxy size (E) and actual A&M for “size” estimation
    estimated proxy size (E) and actual development time for “time” estimation
  If the correlation and regression parameter values are within the selection criteria, method A is used.
PROBE method B is the next preferred method.
  Method B requires a minimum of 3 historical data points that correlate.
    plan A&M and actual A&M for “size” estimation
    plan A&M and actual development time for “time” estimation
  If the correlation and regression parameter values are within the selection criteria, Method B is used.
When PROBE methods A or B do not meet the selection criteria, use
  Method C if you have some historical data
    Method C uses averaging of historical data and does not use regression.
  Method D if you have no historical data
    Method D uses “engineer’s best guess.”

## Slide 11: Rules for Size Method Selection
First check if method A can be used.
  You have three or more data points (estimated proxy size and actual A&M) that correlate (r2 ≥ 0.5 ).
  The absolute value of b0 is less than about 25% of the expected size of the new program.
  b1 is between 0.5 and 2.
If method A cannot be used, check method B.
  You have three or more data points (plan A&M and actual A&M) that correlate (r2 ≥ 0.5 ).
  The absolute value of b0 is less than about 25% of the expected size of the new program.
  b1 is between 0.5 and 2.
If method B cannot be used and you have any data on plan A&M and actual A&M, use method C.
If you have no historical data, use method D.
Notes: Note the use of about 25% in the 2nd and 6th bullets. This comes explicitly from the PROBE Estimating script. The 25% is a guide not a hard criterion. Suggest to your students that if b0 is greater than 25% of the expected size of the program, they consult with you about using it.

## Slide 12: Rules for Time Method Selection
First check if method A can be used.
  You have three or more data points (estimated proxy size and actual time) that correlate (r2 ≥ 0.5 ).
  b0 should be near 0 (substantially smaller than the expected development time for the new program).
  b1 should be within 50% of 1/(historical productivity).
If method A cannot be used, check method B.
  You have three or more data points (plan A&M and actual time) that correlate (r2 ≥ 0.5 ).
  b0 should be near 0 (substantially smaller than the expected development time for the new program).
  b1 should be within 50% of 1/(historical productivity).
If method B cannot be used and you have historical data, use method C.
If you have no historical data, use method D.
Notes: Historical productivity is the to date productivity for the previously developed programs.

## Slide 13: Where Do the Size Guidelines Come From?
Rule for Size b0
  Having the overhead and constant bias (b0) almost as big as the finished product would not make sense. It would mean estimated proxy size has little influence on the estimate size.
  The absolute value of b0 should be less than about 25% of the expected size of the finished product.
Rule for Size b1
  Normally, the slope (b1) should be near 1.0. Values between 0.5 and 2.0 are acceptable.
  A value of less than 0.5 or greater than 2.0 indicates a large proportional-over or -under bias and should not be used unless your instructor agrees.

## Slide 14: Where Do the Time Guidelines Come From? - 1
Rule for Time b0
  Having the overhead and constant bias (b0) almost as large as the final estimated time would not make sense. It would mean the estimated proxy size has little influence on the estimated time.
  The absolute value of b0 should be significantly smaller than the estimated development time.

## Slide 15: Where Do the Time Guidelines Come From? - 2
Rule for Time b1
  “Time” b1 needs to be within 50% of (1/historical productivity).
  Example:
    How long would it take to code one LOC if historical productivity is 30 LOC per hour?
  30 LOC 1 hr
  1 LOC x hrs
  ---------------------------
  30x = 1  x = 1/30 = 2 minutes per LOC
    For this example, if b1 is not between 1 and 3 minutes per LOC (within 50%), the applied correction is too great and should not be used.

## Slide 16: Follow Along …
Download the PROBE methods A and B.mdb database and import it into a copy of your PSP Student Workbook.

## Slide 17: Historical Data - PROBE Calculation Worksheet
This is the lower part of the PSP Size Estimating Template where the analysis of data and selection of the PROBE methods is performed.
This screen is reached through the PSP2.1 window’s drop down list:
Notes: We display the lower portion of the PSP Size Estimating Template first as our journey will start in the lower portion.
This slide introduces the parts of the screen with red arrows to indicate the main topics of discussion,
While we will go into the details later, it may be a good idea here to show (with the green arrows) that Method B&C’s historical data starts with Program-2 where they did estimate time for each phase for the first time, and that Method A’s historical data starts with Program-3 where they started proxy based estimating. Note the first orange arrow on Program-2 and point out that there is no “E” and then point out the second orange arrow on Program-3 where there is an “E”stimate and that with Program-3 we started building historical data on “E”stimated Proxy Size.
Since both Method A and Method B require a minimum of 3 data points, Method B has data starting from Program-2, and Method-A from Program-3.
Method A uses “E”stimated Proxy Size and Actual A&M for “size”, and “E”stimated Proxy Size and Actual development time for “time” (The double sided red arrows in PROBE Historical Data – Method A section).
Method B uses Planned program size and Actual program size for “size”, and Planned program size and Actual development time for “time” (The double sided red arrows in PROBE Historical Data – Method B and C section).
Point to blue arrows and remind that they can scroll through and view the historical data for all the programs they have developed so far.
Have the class go into their student tools and acknowledge that the entire class is now familiar with this part of the PSP Size Estimating Template.

## Slide 18: PSP Size Estimating Template
This is the upper part of the PSP Size Estimating Template where the detailed size estimating is recorded.
We are interested in
Added size =
Base Additions + Part Additions
Estimated proxy size =
Base Additions + Part Additions
+ Modifications
No effort is spent in development on inclusion of Reused parts so they are not included in A or E.
Notes: This slide is a refresher to get everyone’s understanding on the same page.
We are interested in two derived measures: A = BA + PA and E = BA + PA + M.
It is a good idea to remove any confusion about “base” and “reused” here, if there is any!
Also remind the students that if most of the newly added parts are of medium size it is indicative of a good conceptual design, not too detailed where many parts are too small, and not too high level where many parts are too large.

## Slide 19: PROBE Method A
Method A uses
  estimated proxy size (E) and actual A&M for “size” estimation
  estimated proxy size (E) and actual development time for “time” estimation
PROxy Based Estimation started with the third programming assignment.
Possible outliers are best visible on a chart.
Select the chart button (circled in red above) to view a graph of the data. If, after evaluation, the program data point is authenticated as an outlier, then mark the checkbox to eliminate the value from the PROBE calculation.
Size
Time
Notes: We show on the slide where the data is coming from for use in Method A.
Also mention that it is discouraged to mark a data point as an outlier as fluctuation is normal and evaluation should be deferred until substantial amount of data is collected.
Note that just viewing the chart does not constitute careful evaluation.
Method A’s historical data starts with Program-3 where they started proxy based estimating.

## Slide 20: PROBE Method A Size & Time Charts
The charts are useful for quick, visual verification of correlation and also for identification of possible outliers.
A data point may look like an outlier when there are not enough data points.
Wait to accumulate enough data points to make a sound judgment call on an outlier.
Notes: Note that based on an individual’s perception a visually drawn regression line may or may not be accurate!
On this example explain that when the data point circled in red is marked as an outlier we get a pretty good regression, but this would be the wrong approach as there are too few data points to make a sound judgment call!
Note: Student tool does not draw a regression line. It is best to go back to PROBE Size Estimating Template and look at the calculated correlation value and regression parameters!

## Slide 21: PROBE Method A - Outlier
In your student workbook, mark a program as an outlier and see how PROBE reacts to it with a new calculation. Review the displayed data.
Before
After
Notes: Explain that this is the “advanced” course and the students should feel pretty comfortable exploring the options on the tool and get familiar with them.
Note: Correlation changed drastically in this example!

## Slide 22: PROBE Method A Size Charts with(out) Outlier
The before chart was built based on all the data.
Before
After
Once one or more data points are marked as outliers, they no longer appear on the charts and they are also excluded from the calculations.
Notes: Tell the students that marking a data point as outlier does not delete the historical data on that program, the PROBE will be blind to that program’s data.

## Slide 23: PROBE Method A Selection Criteria for Size - 1
Size selection criteria (Step-1)
  Is the correlation (r2) equal to or greater than 0.5?
  In this example, r2 meets the requirement (0.829723).
  Reminder:
  Method A uses estimated proxy size (E) and actual A&M for “size”, and
  estimated proxy size (E) and actual development time for “time” estimation.

## Slide 24: PROBE Method A Selection Criteria for Size - 2
Size selection criteria (Step-2)
  Absolute value of b0 should be near 0: less than about 25% of the expected size of the new program. b0 represents overhead and/or constant estimating bias, so it should not be more than about 25% of the projected A & M size (P).
  b1 represents proportional estimating bias and proportional overhead. It should be between 0.5 and 2.0.
  Now we will go into PROBE Calculation Worksheet (by scrolling up from this point) to evaluate if the regression parameters satisfy the selection criteria.

## Slide 25: PROBE Method A Selection Criteria for Size - 3
  b0 is 25.69 compared to the Projected A&M size of 321.42, which satisfies the “near zero, less than about 25%” criterion.
  b1 is 1.14, which satisfies the “between 0.5 & 2.0” criterion.
  Prediction Range is +/-64 LOC on a Projected A&M of 321.42.
  The wide predication interval (128 LOC) can be indicative of variation in data (too much historical fluctuation). In this case, it is actually caused by the distance of the estimated proxy size (E) from the historical data.
  Method A for size estimating is acceptable.
Notes: Note that the “near zero, less than about 25%” criteria comes directly from the PROBE script.
Method A fits the selection criteria, so it should be selected.
A couple things to note about the prediction interval
  It is not part of the selection criteria for the method choice.
  The magnitude of the prediction interval is mainly affected by 2 items
    the variation of the historical data about the regression line
    The “distance” of the new estimated proxy size (E) from the historical data
  The larger either of these is, the larger the prediction interval is
  In this example, the variation of the historical data about the regression line is “small” – see the earlier charts. But the “distance” of the new estimated proxy size from the historical data is “large”. So although the historical data has little fluctuation, because the new estimated proxy size (e) is well outside the range of the existing data, the prediction interval is large.

## Slide 26: PROBE Method A Selection Criteria for Time - 1
Time selection criteria (Step-1)
  Is the correlation (r2) equal to or greater than 0.5?
  In this example, r2 does NOT meet the requirement (0.096).
Let’s suppose that correlation was good and check the criteria for b0 and b1.
  Reminder:
  Method A uses estimated proxy size (E) and actual A&M for “size”, and
  estimated proxy size (E) and actual development time for “time” estimation.

## Slide 27: PROBE Method A Selection Criteria for Time - 2
Time selection criteria (Step-2)
  b0 should be near 0 (substantially smaller than the expected development time for the new program).
  b1 should be within 50% of .
(0.5 *) < b1 < + (0.5 *)
  Now we will go into PROBE Calculation Worksheet (by scrolling up from this point) to evaluate if the regression parameters satisfy the selection criteria.
1
historical productivity
)
(
1
historical productivity
)
(
1
historical productivity
)
(
1
historical productivity
)
(

## Slide 28: PROBE Method A Selection Criteria for Time - 3
  b1 (-1.08) being negative, it cannot be within 50% of 1/(historical productivity). Thus, method A is not usable for time estimating.
  b0 is 230.43 (compared to an estimated total development time of -48.94), which is outside of the acceptable parameters.
  b0 also does NOT satisfy the selection criterion.
  “Time” is -48.94 minutes, which is meaningless.
  If b1 was positive, how would we check its selection criterion?

## Slide 29: PROBE Method A Selection Criteria for Time - 4
  If b1 was positive, you would then check if it met the criterion.
    1/productivity = (1/52.3) * 60 min/h = 1.14 min/LOC
  1.14 - (1.14/2) < b1 < 1.14 + (1.14/2)
  0.57 < b1 < 1.71
  (From previous slide) b1 does not satisfy method A’s selection criterion for Time estimating.
LOC/h
Notes: Note that historical productivity is LOC/Hr, so we multiply the result by 60 to get the per minute value!

## Slide 30: PROBE Method A Selection Criteria for Time - 5
  Range is 411.74 minutes compared to an estimated development time of -48.94, which is totally meaningless.
  Upper and lower prediction interval limits therefore are meaningless also.
  Our next option for time is method B.

## Slide 31: PROBE Methods B and C
Method B uses
  plan A&M and actual A&M for “size” estimation
  plan A&M and actual development time for “time” estimation
Method C uses averaging of historical data and does not use regression.
Other than using a different set of data, the steps in method B are identical to method A.
Let’s look at the PROBE Calculation Worksheet next to see if method B provides a better fit.
Time
Size
Notes: We show on the slide where the data is coming from for use in Method B.
Also mention that it is discouraged to mark a data point as an outlier as fluctuation is normal and evaluation should be deferred until substantial amount of data is collected.

## Slide 32: PROBE Method B Selection Criteria for Time
  R2 of 0.91 is equal to or greater than 0.5. 
  β1 of 1.11 is positive and between 0.57 and 1.71. 
  β0 of 43 is substantially smaller than the expected development time of 329. 
  Method B for Time estimating is acceptable.
Notes: In this example, the Time selection criteria was not met by Method A, then we came into Method B and found it to be acceptable

## Slide 33: Messages to Remember
PROBE offers four methods to arrive at size and time estimates.
  Method A is the most preferred choice.
    requires a minimum of 3 data points that correlate
    uses estimated proxy size (E) and actual A&M for “size” estimation
    uses estimated proxy size (E) and actual development time for “time” estimation
    evaluates correlation along with regression parameters
  Method B uses
    requires a minimum of 3 data points that correlate
    plan A&M and actual A&M for “size” estimation
    plan A&M and actual development time for “time” estimation
    evaluates correlation along with regression parameters
  Method C uses averaging of historical data and does not use regression.
  Method D uses “engineer’s best guess.”