## Slide 1: PSP Fundamentals Fundamental Planning Concepts

## Slide 3: Lecture Topics
The Need for Plans
The PSP Planning Framework
The Estimating Problem
The PROBE Estimating Method
Counting Size
Types of Size

## Slide 4: Question
Why are plans needed?
Notes: We begin with a class discussion of why plans are needed. Ask the class why plans are needed and write their answers on a post-it flip chart. Discuss the answers with the class and then transition to the next slide.

## Slide 5: Need for Plans
Plans are needed to
  make commitments
  guide the work
  track the work
Notes: These are the three items we concentrate on in this class.

## Slide 6: Class Discussion
What are the steps in planning?
Notes: Have another class discussion to identify the basic steps in planning. If the students do not bring up program size, prompt the class by asking what differentiates a program that takes a small effort from one that takes a lot of effort? Again, record their answers on a post-it flip chart. Discuss their answers and transition to the next slide.

## Slide 7: Basic Planning Steps
Basic steps of planning are
  understand the requirements
  estimate size of job
  estimate effort for job
  make a task list
  make a schedule
Notes: Here, we have purposefully omitted mention of creating a conceptual design. The next series of slides introduces this as the solution to the estimating problem that is framed on the next slide.
Consider putting a size versus effort chart here to make this point.

## Slide 8: The PSP Planning Framework
Product
delivery
Tracking
reports
Define
requirements
Produce
conceptual
design
Estimate
size
Estimate
resources
Produce
schedule
Develop
product
Size, resource,
schedule
data
Process
analysis
Resources
available
Size
database
Productivity
database
The Estimating Problem
Notes: Relate the PSP Planning framework to the steps in planning. You want to

## Slide 9: The Estimating Problem
Detailed size measures such as lines of code (LOC), screen controls, or data base objects are needed to make good effort estimates.
At the initial planning stage, directly estimating LOC, screen controls, or data base objects is usually difficult.
These are not the items you visualize directly from the requirements or specification.
How can this be handled?
Requirements
Lines of Code?
Notes: This slide is setting up the analogy between estimating software projects to estimating the size and cost of a house. This analogy is covered further in the next slides to introduce PROBE.

## Slide 10: Estimation Analogy: Building a House -1
Suppose you want to build a new house.
You go to a builder to get a cost estimate.
The builder tells you that the cost is directly related to the size, in square feet, of the house.
How can you come up with the needed size estimate?
Notes: This example is usually best shown on flip charts or a white board. These slide are here as backup. So, if possible, cover this as a discussion with the class using the whiteboard/flip charts, and just skip over these slides.

## Slide 11: Estimation Analogy: Building a House -2
The builder has detailed size data on actual room sizes for many houses.
The data are organized by room type such as bedroom, bath, and kitchen with the typical small, medium, and large size.
Relative Size in Square Feet |  |  | 
Room Type | small | medium | large
Bedroom | 144 | 225 | 450
Bath | 80 | 120 | 200
Kitchen | 100 | 200 | 300
Family room | 175 | 250 | 500
Notes: At this point, sketch out a conceptual design of the house in terms of the rooms, their types, and relative sizes. This is what the buyer can visualize. Next sketch out the contractor’s relative size table that is constructed from data on actual houses. Then lead the class through making an estimate.

## Slide 12: Estimation Analogy: Building a House -3
You visualize a conceptual design of your desired house by listing the rooms you want and their relative sizes; small, medium, or large.
To estimate the house size
  To estimate the square footage of each room, look up the room type and relative size in the builder’s size table.
  Total the estimated room sizes by adding the individual estimates together.
  Historical data shows that the hallways and closets add some percentage to the room size estimate. The final size estimate is calculated by adjusting the room size estimate by this historical data.
To estimate the cost, multiply the final size estimate by his cost per square foot.
Notes: At this point, sketch out a conceptual design of the house in terms of the rooms, their types, and relative sizes. This is what the buyer can visualize. Next sketch out the contractor’s relative size table that is constructed from data on actual houses. Then lead the class through making an estimate.
As you continue the example, after you sum the individual room size estimates, adjust that total by say 10% to account for closets and hallways. (This is the hook to talk about PROBE method C).
Finish the example with the cost estimate.

## Slide 13: Estimation Analogy: Relating to Software
Analogy to software
  From the requirements, visualize the “parts” needed to build the program (such as the rooms of the house), the “types” of these parts, and their relative sizes.
  Use historical data on the software parts already developed, organized into a relative size table by part “types,” to estimate “part” size.
  Estimate the program size by summing the “part” estimates and adjusting the sum by the relationship of past estimates to actual sizes.
  Estimate effort by multiplying the size estimate by historic productivity in size/hour.
Notes: Now discuss how this relates to estimating size and effort in software.
Visualizing the rooms of the house broke the house into parts; you understood these parts and could judge their relative sizes. In software, you start with the requirements or specification and visualize the parts you need for the program.

## Slide 14: The PROBE Method
The steps we just discussed make up the PROBE (Proxy Based Estimating) estimating method.
Conceptual
design
Identify and size proxies
Number of
items
Part
type
Relative
size
Reuse
categories
Estimate other
element sizes
Calculate
total projected program size
Calculate
projected program
effort

## Slide 15: Conceptual Design
A conceptual design
  relates the requirements to the product
  defines the product parts that will needed to build the product
  is used as the basis for estimating the size of the product you plan to build
Conceptual design are not the same as detailed designs.
For most projects, the conceptual design can be produced relatively quickly.
To make a conceptual design, identify the product functions and the program parts needed to produce them.
If you do not understand the product well enough to make a conceptual design, you do not know enough to make a plan.
Notes: Conceptual designs
  They are created during the planning phase for the purpose of making a size/effort estimate, not the actual design.
  They are a list of the “parts” you visualize that would be needed to build the program. A single “part is not a conceptual design. In effect, you say: “If I had the following parts, I could build this product.” Conceptual design can also be thought of as function and/or feature decomposition into program parts.
  With an understanding of the problem space, you can develop conceptual designs quickly. For the PSP exercise programs, you should be able to complete a conceptual design in under 10-20 minutes..

## Slide 16: Identify and Size the Proxies
Based on the conceptual design, categorize those parts by comparing each to types of parts historically produced.
Next, estimate the relative size of each part by comparing to the size of parts historically produced.
Finally, combine the part estimates to estimate total size of new parts.

## Slide 17: Estimate Other Element Sizes
If you will be modifying or including existing code, you will need to estimate those other parts.
Base parts are existing parts that will be changed by adding, deleting, or modifying.
Reused parts (R) are parts that will be used unmodified.

## Slide 18: Calculate Projected Total Program Size and Effort
To calculate total program size, you add up the individual pieces.
The total size may be adjusted based on your historical data to calculate a projected total program size.
The estimation of development effort is based on the projected program size.
The projected program development effort can also be adjusted based on your historical data.

## Slide 19: Size Measures
In class, we encourage you to use LOC as the size measure for the assignments; you will likely need additional size measures in practice, however.
Criteria for selecting size measures
  relates to effort
  precise
  machine countable
Notes: Discuss each of these, focusing on “precise” and “LOC.”

## Slide 20: Precise Size Measure
A size measure is precise if
  Every time you measure the same item you get the same result.
  Every person who measures the same item gets the same result.
Is LOC a precise measure?
Notes: Ask the class “Are LOC a precise measure?” They should respond “NO.”
If necessary, guide the class with examples such as reformatted code, coding style, and what is counted as an LOC. {Frame this as foreshadowing of program 2, a physical line counter}
Ask the class how LOC could be made a precise measure?
A counting standard is the answer. Briefly discuss with the class. Mention that for this class, we will provide a simple counting standard. But in the job setting they will want something more robust.

## Slide 21: Counting Standard
LOC is not a precise measure unless LOC has been defined precisely.
Defining LOC precisely in the work environment can be a significant task.
In this class, we ask you to use the following simple rules for defining a line of code.
  Count each physical line as one LOC.
  Do not count blank lines.
  Do not count lines that are only comments.
  Do not count machine generated lines.
  Be consistent about what you put on each physical line.
Notes: Note here that you may want a logical line counter in the work environment. That way, the LOC count is independent of the way the code is formatted on physical lines.

## Slide 22: Are All LOC Equal?
Recall that in PROBE, estimated development effort is based on the estimated LOC.
Assume we estimate two programs.
  Program 1 is 200 LOC of all new code.
  Program 2 is 100 LOC of new code and 100 LOC of existing code
Are these programs likely to take the same effort to develop?
Notes: Have a class discussion.
Response should be that the effort is likely to be primarily related to the LOC of new code.
Conduct a chalk talk to generalize this to all PSP types of code to be considered.
Base
  Deleted
  Modified
Added
Reused

## Slide 23: Types of LOC
The types of LOC include
  base [B] – LOC that you start with and make changes to
    deleted [D] – LOC removed from the base
    modified [M] – LOC in the base that is modified
  added [A] – LOC that is new
  reused [R] – LOC from a library that is used without changes
  added and modified [A&M] – sum of added and modified LOC
  new reusable – new LOC that is put into a reuse library
  total [T] - the LOC in the entire program
Notes: Point to note here: Base and reused are both forms of reuse.

## Slide 24: Program Size Type Relationships
Added Code
Reused Code
Modified
Base Code
Deleted
Base Code
Initial Base Code
Program Size
Initial
Base
Final
Program
Base
Changes
Notes: Use the whiteboard or flip chart to show the formulas for
T = B + A - D + R
A = T - B + D - R
Or you may want to work a numeric example like below:
Added Subtracted Base
0
0
0 0
350
350 -0 350
0
25 25
100
125 -25 450
Total Added and Modified LOC 475
Or you could draw a Venn diagram on a white board.

## Slide 25: Size Estimating Principles
Estimating is an uncertain process.
  No one knows how big the product will be.
  The earlier the estimate, the less is known.
  Estimates can be biased by business and other pressures.
Estimating is an intuitive learning process.
  Ability improves with experience and data.
  Some people will be better at estimating than others.
The objective is to become consistent.
  You will then understand the variability of your estimates.
  You seek an even balance between under- and overestimates.

## Slide 26: Messages to Remember
Product
delivery
Tracking
reports
Define
requirements
Produce
conceptual
design
Estimate
size
Estimate
resources
Produce
schedule
Develop
product
Size, resource,
schedule
data
Process
analysis
Resources
available
Size
database
Productivity
database
PROBE method
Notes: Review with the class:
Plans are necessary. Discuss the reasons why.
Conceptual design is for estimating, identifies the major parts, type and relative size.
Part size estimates come from the relative size table that is based on historical data.
Final size estimate may be adjusted to account for items not in the estimate (or estimating history).
Effort estimate is then based on size estimate.