## Slide 1: PSP Fundamentals Schedule Planning and Tracking

## Slide 3: Lecture Topics
Why do we need good plans?
Building task and schedule plans
Project tracking with earned value
Projecting project completion
Plan changes
Task and schedule planning and tracking on teams

## Slide 4: Why do we need good plans?
How do you know when your set of tasks will be complete?
What confidence do the people who will receive your product have that you will deliver when promised?
What confidence do you have that others will deliver the product to you when promised?
How do you know the effect of overrunning this week’s tasks on your ability to meet a required completion date?
What is the effect of taking on additional work?
How do you know if there is time to take an extra vacation day without compromising a delivery date?
At what point do you start working excessive overtime in order to make a delivery date?

## Slide 5: Good Plans
What are the characteristics of a good plan?
Notes: DO THIS ON THE WHITE BOARD:
A good plan:
Lists all tasks that need to be completed.
Uses estimates based on historical data.
Is based on available project hours.
Can be used to understand the impact of changes.
Is used to guide the developer’s work every day.
Allows the developer to easily evaluate how far along he or she is in the plan.
Allows the developer to easily and regularly project a completion date.

## Slide 6: Task and Schedule Plans - 1
Determine:
ordered task list
Estimate:
size of each task
effort for each task
Determine:
available project hours for each week
Calculate:
a planned completion date for each task
a completion date for the list of tasks
Requirements
Availability
Historical Data
Task and Schedule Plans

## Slide 7: Task and Schedule Plans - 2
Task No. Task Est. Hrs. Cum Est. Hrs
1 Item 1 DLD 8 8
2 Item 1 DLDR 4 12
3 Item 1 CODE 10 22
4 Item 1 CR 5 27
5 Item 1 UT 2 29
6 Item 2 DLD 9 38
7 Item 2 DLDR 4 42
8 Item 2 CODE 12 54
9 Item 2 CR 5 59
10 Item 2 UT 3 62
11 PM 1 63
ORDERED TASK LIST WITH EFFORT ESTIMATES
Week No. Plan Hrs. Cum Plan Hrs. 1 15 15
2 15 30
3 15 45
4 15 60
5 15 75
SCHEDULE AVAILABILITY
Task No. Task Est. Hrs. Cum Est. Hrs. Week No.
1 Item 1 DLD 8 8 1
2 Item 1 DLDR 4 12 1
3 Item 1 CODE 10 22 2
4 Item 1 CR 5 27 2
5 Item 1 UT 2 29 2
6 Item 2 DLD 9 38 3
7 Item 2 DLDR 4 42 3
8 Item 2 CODE 12 54 4
9 Item 2 CR 5 59 4
10 Item 2 UT 3 62 5
11 PM 1 63 5
Week No. Plan Hrs. Cum Plan Hrs. Task Nos. 1 15 15 1,2
2 15 30 3,4,5
3 15 45 6,7
4 15 60 8,9
5 15 75 10,11
SCHEDULE PLAN
TASK PLAN

## Slide 8: Project Tracking - 1
Project tracking would be simple if
  we always completed tasks in the planned order
  no tasks were added or deleted
But this never happens.
  Requirements always change.
  Tasks get cancelled or deferred.
  Some tasks are dropped, and others are added.
  Estimating errors are common.

## Slide 9: Project Tracking - 2
To track project status in a dynamic environment, you need a way to assign a value that measures the contribution of each task towards the whole project.
Then you can
  add up the value of the completed tasks
  compare this value to the value of the total job
  calculate the percentage of job completion
The PSP does this with a method called earned value (EV).

## Slide 10: Earned Value
The planned value (PV) for a task is the percent of the total project hours that is planned for that task.
Planned value establishes a common value for each task, regardless of the type of work, which facilitates progress tracking.
When a task is completed, it is assigned an earned value (EV) that is equal to the planned value for that task (regardless of how many hours it actually took).
Partially completed tasks receive no earned value.

## Slide 11: Example – Planned Value
Task Task Estimated Cumulative Week # PV Cumulative
No. Description Hrs. Est. Hrs. PV
1 Item 1 DLD 8 8 1 12.7 12.7
2 Item 1 DLDR 4 12 1 6.3 19.0
3 Item 1 CODE 10 22 2 15.9 34.9
4 Item 1 CR 5 27 2 7.9 42.9
5 Item 1 UT 2 29 2 3.2 46.0
6 Item 2 DLD 9 38 3 14.3 60.3
7 Item 2 DLDR 4 42 3 6.3 66.7
8 Item 2 CODE 12 54 4 19.0 85.7
9 Item 2 CR 5 59 4 7.9 93.7
10 Item 2 UT 3 62 5 4.8 98.4
11 PM 1 63 5 1.6 100.0
Week Plan Cumulative Task PV Cumulative No. Hours Plan Hrs. No. PV
1 15 15 1,2 19.0 19.0
2 15 30 3,4,5 27.0 46.0
3 15 45 6,7 20.6 66.7
4 15 60 8,9 27.0 93.7
5 15 75 10,11 6.3 100.0
SCHEDULE PLAN
TASK PLAN
PLANNED VALUE
PV
Week No.
100
1
2
3
4
5
10
20
30
40
70
80
50
60
90
x
x
x
x
x
x
Notes: The planned value (PV) is the value in the plan.
This value is earned (EV) only on task completion.
The plan hours are the estimated available task hours for that week.

## Slide 12: Example - Earned Value
EARNED VALUE
EV
Week No.
100
1
2
3
4
5
10
20
30
40
70
80
50
60
90
x
x
x
x
x
x
o
o
o
o
PV
EV
o
x

## Slide 13: Rules of Earned Value
Track the Plan with EV.
  Tasks earn value only when they are 100% complete. Partially completed tasks earn no value.
  EV = PV
  Assumes that the future will behave like the past.
    Predicted date is based on the rate at which value has been earned to date.
  Task order doesn’t matter.

## Slide 14: Earned Value Tracking
EV tracking
  only works for projects that have reasonably accurate plans
  assumes the rate of estimate error is reasonably consistent
  assumes the project resources will remain constant
  works best when task size is granular enough so that several tasks per week can be completed.

## Slide 15: Projecting Individual Project Completion
To estimate the project completion date with EV
  Determine the EV needed to finish.
  Determine the rate at which the individual is earning EV.
  Determine how long it will take the individual to earn the remaining EV.

## Slide 16: Projecting Project Completion - 1
After three weeks, the work has taken longer than expected, and the developer is not getting 15 task hours per week.
As tasks are completed, their EV is entered for the week earned. Partially completed work earns no value.
What is the estimated completion date?

## Slide 17: Projecting Project Completion - 2
There is no credit for partially completed work.
The team member has earned 42.8 EV in 3 weeks, or 14.3 EV per week.
There are 100 - 42.8 = 57.2 EV to go.
At 14.3 EV per week, that is 4.0 more weeks to go.
Added to the 3 weeks spent so far, that is 7.0 weeks.
At the current rate of progress, the team member will be 2.0 weeks late.
EARNED VALUE
EV
Week No.
100
1
2
3
4
5
10
20
30
40
70
80
50
60
90
x
x
x
x
x
x
o
o
o
o
PV
EV
o
x
6
7
Projected EV
v
v
v
v
v

## Slide 18: Plan Changes -1
To track job progress, you must follow the plan.
Since plans always change, you must regularly update the plan so that it represents what you currently plan to do.
Of course, you must always keep copies of the original plans.
Unless the plan differs significantly from the way that you now plan to work, merely add any new tasks and delete the cancelled ones.

## Slide 19: Plan Changes -2
Adding tasks reduces the earned value of all of the planned and completed work.
Similarly, deleting tasks increases the earned values of the planned and completed tasks remaining in the plan.
Most TSP support tools will make these EV and PV adjustments for you.
For major plan changes, you must make a new plan.

## Slide 20: Task and Schedule Planning and Tracking on Teams
Task and schedule planning works similarly for teams.
The team plan is a roll up of team members’ individual plans.
Team status is a roll up of individual team member performance.
The advantage of working on a team is that when one team member is ahead of plan and another is behind plan, the team can dynamically redistribute the work to bring the plan into balance.

## Slide 21: Example TSP Weekly Data -1
When all team members record their data consistently, TSP teams can track and manage their work precisely.
  They know the planned and actual data for each week and for the project to date.
  They can measure job status precisely and estimate how long it will take to finish the work.
Notes: Ask the students to close their laptops since the answers to the questions are on the following slides.

## Slide 22: Question 1
Is this team ahead of or behind schedule, and by how much?

## Slide 23: Answer to Question 1
Is this team ahead of or behind schedule, and by how much?
The team has earned only 22.3 EV against a plan of 28.2 EV, so it is clearly behind schedule.
At the current rate of 3.19 EV/Wk, it will take 1.85 weeks to reach the planned 28.2 EV, so the team is 1.85 weeks behind schedule.

## Slide 24: Question 2
Why is the team behind schedule?

## Slide 25: Answer to Question 2
Why is the team behind schedule?
Although the team is working more than its planned weekly hours, the work is taking 29% longer than planned.

## Slide 26: Question 3
At this rate, can the team members finish on the original plan of 25 weeks? If not, how late will they be?

## Slide 27: Answer to Question 3
At this rate, can the team members finish on the original plan of 25 weeks? If not, how late will they be?
The team has earned EV at 22.3/7 = 3.186 EV/week.
At this rate, it will take (100-22.3)/3.186 = 24.2 more weeks to finish. This is 6.2 weeks behind the 25-week plan.

## Slide 28: Question 4
Can this five-person team meet the original schedule? If not, what help would they need from management to do so?

## Slide 29: Answer to Question 4
Can this five-person team meet the original schedule? If not, what help would it need from management to do so?
To meet the schedule, it needs to do 77.7 EV of work in 18 weeks, or 4.3 EV a week.
To increase its average EV rate of 3.186 EV a week by 35%, the team must work 35% more hours, or add two team members.

## Slide 30: Conclusions
This team increased its task hours somewhat and also spent less time than planned in test.
The team also reprioritized the work and slightly reduced the total workload.
It actually finished on the exact day originally planned.
With the PSP, you will precisely know job status and will have the data to manage your own work.
With this knowledge, you will usually meet your commitments.

## Slide 31: Messages to Remember
With the PSP, you can accurately plan and track your own work.
With earned value, you can precisely judge job status and estimate the likely project completion date.
This information will permit you to make accurate and timely management reports.
When your reports indicate potential problems, you should report recommended remedial actions.
On a TSP team, you must tell management what you are doing to solve your own problems.