## Slide 1: PSP Fundamentals What’s Next? TSP Overview

## Slide 3: Lecture Topics
TSP Overview
PSP Advanced
Course Evaluation

## Slide 4: Why Teams are Not Successful
Many teams are not successful because they have
  impossible goals or schedule
  inadequate resources
  morale problems
  poor development processes and practices
The result is that the product entering the test phase is of poor quality.
  The test time is unpredictable.
  The schedule is exceeded by 25% to 50%.
  The team spends half or more of its development time in test.
Notes: The most common “impossible” goal is an impossibly short development schedule, which
  usually starts at very beginning of the project
  usually caused by the team’s inability to negotiate a rational schedule with management
  causes the team to behave illogically
Examples of inadequate resources are
  too few people
  part-time team members
  inadequate training or improper skills
When the team has an impossible schedule or is not adequately staffed, the team becomes demoralized.
  No matter what team members do, they cannot succeed.
  There is no reason to try hard.
  The project becomes a “death march.”
  Team members look for a way out.
Poor engineering practices are commonly of three kinds.
  Poorly handled requirements analysis
  superficial design methods
  undisciplined implementation
With poor development practices, teams skimp on the important front-end work, rush into coding and testing, and don’t measure and manage quality.
The result is that the code entering the test phase is of poor quality.
  The test time is unpredictable.
  The schedule is exceeded by 25% to 50%.
  The team spends half or more of its development time in test.

## Slide 5: Team Software Process
The Team Software Process is designed to provide teams and management with the ability to
  build realistic plans based on customer needs
  provide choices based on realistic plans
  provide ongoing detailed data to enable teams and management to make sound decisions
  produce high quality software products
Understand what the
customer wants
Plan for reality
Anticipate change
Provide choices
Keep tight customer
communication
Fly the plan
Provide timely
response
Perform

## Slide 6: TSP Principles
The TSP principles evolve naturally from the PSP principles.
The developers know the most about the job and can make the best plans.
When developers plan their own work, they are committed to the plan.
Precise project tracking requires detailed plans and accurate data.
Only the people doing the work can collect precise and accurate data.
To minimize cycle time, the engineers must balance their workloads.
To maximize productivity, focus on quality first.

## Slide 7: The TSP -1
The TSP uses a team-directed approach to team management.
It works best for
  integrated product teams
  teams with 3 to 15 members
It can be applied to projects that involve both new development and enhancement.
Traditional team
The leader plans, directs,
and tracks the team’s
work.
TSP teams
The team members participate
in planning, managing, and
tracking their own work.

## Slide 8: The TSP Strategy
The TSP strategy improves performance from the bottom up.
Team
Member
Skills
Team
Building
Team
Management
Process discipline
Performance measures
Estimating & planning skills
Quality management skills
Goal setting
Role assignment
Tailored team process
Detailed balanced plans
Team communication
Team coordination
Project tracking
Risk analysis
Personal Process
TSP
Notes: Create a chart or charts that show how management and developers work successfully together.
The TSP is a framework and a process structure for building and guiding development teams that develop software.
The TSP contains
  a team-building process that addresses the team goals, commitment, cohesion, and structure issues
  a team-working process that addresses engineering processes and practices used by the team
Successful self-directed teams require skilled and capable individual team members. Capable team members are critical because each instruction of a software module is crafted by an individual software engineer on the team. The engineer’s skills, discipline, and commitment govern the quality of that module and the schedule on which that module is produced. In turn, the modules come together to compose software products. Therefore, a software product is a team effort. The product’s modules are designed, built, integrated, tested, and maintained by a team of software engineers whose skills, discipline, and commitment govern the success of the project.
The objective of the PSP is to put software professionals in charge of their work and to make them feel personally responsible for the quality of the products they produce. The objectives of the TSP are to provide a team environment that supports PSP work and to build and maintain a self-directed team.

## Slide 9: TSP Measures
Measures
  TSP uses the same four basic measures as PSP.
  Individual Data is consolidated into team data.
  Data are captured on forms similar to TSP forms
Size
Schedule
Quality
Effort

## Slide 10: Team Data
Individual data are aggregated to a team view.
Individual time and defect log data are visible only to the team members and the coach.
Only aggregated team data are visible to management.

## Slide 11: The TSP Launch Process
Day 1
1. Establish
product and
business
goals
2. Assign roles
and define
team goals
Day 2
4. Build overall
and
near-term
plans
5. Develop
the quality
plan
6. Build individual
and
consolidated
plans
Day 3
7. Conduct
risk
assessment
8. Prepare
management
briefing and
launch report
Launch
postmortem
Day 4
9. Hold
management
review
3. Produce
development
strategy
and process
A qualified coach guides the team through a defined process to develop its plan and to negotiate that plan with management.
Notes: Proceed very quickly through this slide since we will spend a lot of time later in the presentation discussing overall, near-term, individual, and consolidated plans. Just make the points that the TSP launch is the mechanism for
developing the team plan
negotiating the team commitments with management
building the team
Also note that
The TSP launch is a three- to four-day workshop used to kick off each project phase.
The team leader and all team members participate.
The launch workshop is considered to be part of the project work.
The launch workshops are planned and tracked

## Slide 12: TSP Process Structure
TSP projects can start on any phase or cycle.
Each phase or cycle starts with a launch or relaunch.
The strategy is to
  develop in increments
  use multiple cycles
  work ahead
TSP supports whatever process structure makes the most business and technical sense.
Phase or cycle
Postmortem
Development
phase
or cycle
Launch
Re-launch
Project
Postmortem

## Slide 13: Cast of Characters
Team members
  follow disciplined personal practices
  plan, track, and manage their personal work
  support and contribute to the team
Team Leader
  guides the team in doing its work
  provides management support
  establishes and maintains high standards for the work
Team Coach
  TSP process expert
  independent, objective voice
  facilitator

## Slide 14: How TSP Teams Plan
The TSP planning process is very similar to the PSP planning process.
  The team starts by creating a conceptual design.
  The team estimates the size of each component of the conceptual design
  The team agrees upon a development strategy and process for building the product.
  The team builds the task plan by applying the process and development strategy to the conceptual design.
  The team builds a schedule plan by totaling each team member’s available hours per week.
  The team builds an EV plan by applying the available hours to task plan hours.
Notes: Illustrate this quickly on a white board as you explain the steps. This is the overall concept. We’ll fill in the details with the remaining slides.

## Slide 15: Planning Detail
The level of detail of the tasks in the plan depends upon how far in the future those tasks are.
Near-term tasks
  The near-term horizon generally extends to the end of the next phase or cycle, or to a phase or cycle that ends within two to four months.
  The task size should result in each person starting and ending about one to two tasks per week.
Later tasks
  Tasks for the high-level plan may be of any duration.
  The team has to have confidence that even though some tasks are less granular, they are still accurate.
Notes: You may want to talk here about why detailed planning for the whole plan doesn’t make sense. Ask the class why and talk about how much plans change and the reasons why they change: You learn more about the project; you come up with better designs; the requirements change, and so on. Emphasize that the plan detail will change but not necessarily the commitment.

## Slide 16: Types of Plan
Near-Term Plan
Near-Term Tasks
Cycle 2 Tasks
Cycle 3 Tasks …
Overall Plan
Team Member A Plan
Team Member B Plan
Team Member C Plan
Individual Plans
Consolidated Team
Near-Term Plan

## Slide 17: Project Tracking
In lecture 4, we reviewed a team’s WEEK form to understand status and predict project completion. Below is an actual WEEK form

## Slide 18: How TSP Teams Manage Quality
In PSP, individuals are responsible for quality and focus on early defect removal through personal reviews.
In TSP, the team is also responsible for quality and removes defects through team inspections.
Teams don’t produce superior products accidentally.
The team builds a quality plan to guide the team in producing a high-quality product. Teams use their data to make decisions about what to do next.
Teams can’t hit their quality goals unless every developer hits his or her quality goal.
Notes: The plan helps the team to understand when defects will be injected and removed and can help the team to understand the product’s quality status.

## Slide 19: TSP Quality Plan

## Slide 20: Team Working
TSP teams manage themselves. They
  track their work against their plans
  manage the quality of their work
  work aggressively to meet team goals
Teams must also show management and the customer that they are managing themselves. They
  report status and progress frequently
  anticipate, plan for, and report on project risks

## Slide 21: The Weekly Team Meeting
The weekly team meeting keeps the project on track by reviewing status and planned work for the team and each team member on a weekly basis.
The meeting objective is to ensure that all team members
  understand current project status
  know what tasks are next
  are aware of everyone’s status and progress
  know the status against the quality plan
  discuss actions needed to ensure high quality
  understand the key project issues and risks
  participate in key team decisions

## Slide 22: Adoption
Organizations that are using, piloting, or preparing to pilot the TSP.
ABB
ABC Informatica
Advanced Information Services
Advanced Maturity Services, Inc.
Alan S. Koch Consultants
Ambient Consulting
AMCOM*
Boeing
Centre De Investigacion En Matamaticas
Census Bureau*
CQG, Inc.
CRSIP / STSC / DRAPER
Davis Systems
DOE / Los Alamos
DOE / Naval Reactors
DPC Cirrus
Dynamics Research Corp.
EDS
Halex Associates
Heath Solutions, Inc.
Helsana*
Honeywell
IBM
Intuit*
Iomega
I.Q. Inc.
KPMG
L. G. Electronics
Lockheed Martin
LogiCare
Los Alamos National Laboratory
M/A-Com Private Radio Systems, Inc
Microsoft
Motiva
NASA Langley
NAVAIR
Naval Reactors*
NAVOCEANO*
NUWC
NCR Teradata
NCS Pearson
Northern Horizons
Northrop Grumman
NSWC / Keyport
Prodigia S.A. de C.V.
PS&J Consulting - Software Six Sigma
QuarkSoft
Respironics
Rockwell Collins
SAIC
Samsung SDS
Siberlink
STPP, Inc.
STSC
Trilogy
TYBRIN Corporation - Air Logistics
University of Alabama / Huntsville
University of Queensland
Vicarious Visions*
Xerox
*Organizations we are currently working with
Notes: Since TSP was first introduced in 1997, many TSP projects have been launched.
Project team size has ranged from 2 to over 50 team members.
Products have included embedded systems, real-time controllers, and commercial applications.
Program size has ranged from a few hundred A&M LOC to nearly half a million A&M LOC.

## Slide 23: TSP Results
TSP teams produced the highest quality products. Avg. 60 defects per millions lines of delivered code, 1/3 of the products were defect-free.3
A study of 18 TSP projects showed schedule predictability improved from a pre-TSP range of +27% to +112% to better than +/-10%2
Productivity Improvement
A telecommunications industry TSP team developed a product consisting of 89,995 new LOC in 71 weeks, a 41% improvement in productivity compared to similar systems.
A commercial TSP team producing an annual update to a large “shrink-wrap” software product delivered 47% more functionality than initially planned.
Improved Quality of Work Life
“A more disciplined process allowed me to do a better job, and allowed me to balance my job with other aspects of my life.”
“I liked the level of detail that went into initial plan, and the constant awareness of the schedule. Allowed us to make adjustments as the project went on, instead of waiting for a major milestone.”
Notes: Our research indicates that TSP has the potential to substantially reduce the journey to high maturity.
One organization, NAVAIR AV-8B
  adopted the TSP
  moved from ML1 to ML4 in 30 months
  The SEI reported average is six years.

## Slide 24: Engineers like to use the TSP
“This really feels like a tight team.”
“The TSP forces you to design, to think the whole thing out.”
“Design time is way up but code time decreased to compensate.”
“Tracking your time is an eye opener.”
“Really good teamwork on this project - no duplication of effort.”
“I’m more productive.”
“Gives you incredible insight into project performance.”
“Wonderful to have team members assigned specific roles.”
“Team really came together to make the plan.”
“I feel included and empowered.”

## Slide 25: PSP Advanced
The PSP Advanced course builds on the fundamental skills learned in the PSP fundamentals course.

## Slide 26: Evaluation
Please fill out the course evaluation forms with your comments and feedback.

## Slide 27: Course Conclusion
THANK YOU!