## Slide 1: PSP Fundamentals Tutorial: Using PSP1 with Process Dashboard

## Slide 3: Tutorial Objectives
After this tutorial, you will
  understand the process changes introduced in PSP1
  know how to use the PSP1
  be prepared to use PSP1 for program 2

## Slide 4: PSP1 Objectives
The objectives of PSP1 are to
  establish an orderly and repeatable procedure for developing software size and effort estimates
  measure the size and perform size accounting for the programs that you produce
  provide the basis for creating realistic, defensible development plans

## Slide 5: Process Changes Introduced with PSP1
PROBE added to the planning process
  size estimating template
  coding standards
Additional forms
  test report template
  process improvement proposal (PIP) form
Project Plan Summary form modified
  program size summary
  additional summary metrics
  Planned time in phase is calculated based on historical time in phase percentage.

## Slide 6: Follow Along…
We will follow along with JD as he uses PSP1 for the first time.
  Open your Process Dashboard, and choose “C → Tools → Save Data Backup.”
  Save the data backup ZIP file to a convenient location.
  Then, choose “C → Tools → Open Dataset.” Open the ZIP file you just created.
  A second Process Dashboard window will open, showing the name of the ZIP file in the title bar.
  This second window is showing a copy of your data from the ZIP file. Use this second window to follow along with JD. Changes in this second window will be discarded when the window is closed.

## Slide 7: JD’s Scenario
“JD has started his new assignment. Requirements for this program are to use PSP1 to write a program to calculate the mean and standard deviation of a series of n real numbers. Input the numbers from the keyboard or a file. Store the numbers in a linked list, one number per node. Print the results.”
JD opens the PSP1 script. He sees that the first phase is Planning. He presses the play button to start logging time in the Plan phase. JD next looks for a PSP1 Planning script.
The next step in the script asks JD to use the PROBE method to estimate the added and modified size of his program. Having forgotten how to use the PROBE method, JD asks his instructor for a refresher.

## Slide 8: Steps in the PROBE Method
Conceptual
design
Identify and size proxies
Number of
items
Part
type
Relative
size
Reuse
categories
Estimate other
element sizes
Calculate
total projected program size
Calculate
projected program
effort
Start
Notes: For each of the boxes (steps) in the PROBE process, there are three slides. The first slide describes the concept. The second slide describes how JD completed the step. The third slide shows how JD entered his data into the tool. It’s better to show the tool than to show the slide with the tool.

## Slide 9: Conceptual Design
The purpose of a conceptual design is to
  relate the requirements to the product
  define the product parts that will needed to build the product
  estimate the size of the product you plan to build
For most projects, the conceptual design can be produced relatively quickly.
To make a conceptual design, identify the product functions and the program parts needed to produce them.
Conceptual design can also be thought of as function and/or feature decomposition into program parts.
If you do not understand the product well enough to make a conceptual design, you do not know enough to make a plan.

## Slide 10: Conceptual Design
JD first develops a conceptual design of his program.
JD has a program that he can start with but it will have to be modified.
He determines he will have to add the following new parts to his base.
  input data
  linked list
  calc_mean
  calc. SD
  print results
Input Data
Linked List
Calc
. Mean
Calc
. SD
Print Result

## Slide 11: Identify and Size Proxies
The size of an added part is determined by using a proxy.
  Identify the part type, for example, calculation or IO.
  Estimate the number of items, for example, methods.
  Estimate the relative size of each part by comparing to the sizes of parts historically produced.
  Calculate the estimated size = size of an item * number of items.

## Slide 12: JD’s Added Parts
Parts (classes) | Type | Items (methods) | Relative size
Input_data | I/O | 1 | M
Linked_list | data | 5 | M
Calc_mean | Calc | 1 | M
Calc_sd | Calc | 1 | L
Print_result | I/O | 1 | L
Since JD doesn’t have historical data, he uses the C++ table in the text.
Based on JD conceptual design, JD identifies and sizes his added parts.

## Slide 13: Entering Added Part Data into the Size Estimating Template
Data on added parts is documented on the Size Estimating Template, which can be opened from the script menu.
For each added part
  Enter the part name.
  Select a part type.
  Enter the planned number of items.
  Enter the planned relative size.
  Planned size is automatically calculated.
Notes: Have the students enter the data on slide 11 into their copies of the tool now.

## Slide 14: Estimating Other Program Elements
If you will be modifying or including existing code, you will need to estimate the size of those other parts.
Base parts are existing parts that will be changed by additions, deletions, or modifications. For each base part that will be used, you need to estimate the size of
  base
  deleted
  modified
  added
Reused parts are parts that are NOT part of your base (e.g. from a library) and that will be used unmodified.
New reusable parts are parts that you contribute to the reuse library for later reuse.

## Slide 15: Program Size Type Relationships
Added & Modified [A&M]
Base program [B]
New program [T]
Deleted [D]
Added
Untouched
New
Reusable
New
Reusable
[NR]
Reused [R]
Modified [M]

## Slide 16: JD’s Other LOC Estimates
Now that JD understands what the different types of LOC mean, he can estimate his other LOC. He estimates that he will modify about 10% of the his base program, and maybe add 5% of new LOC to the base.

## Slide 17: Entering Base Parts Data
  In the Base Parts section, enter the name of the base part.
  Enter the planned size of the base part.
    Measure the size of the base part and enter it in the first field.
    Enter the estimated deleted, modified, and added size. If you prefer, you can drag the handles on the size accounting histogram to enter your estimates visually.

## Slide 18: Estimating Reused Parts
During planning, enter each reused part.
  Enter the name of the reused part.
  Enter the planned size of the reused part.

## Slide 19: Top Half of Size Estimating Template
After entering JD’s data, the Size Estimation template should look like this.

## Slide 20: Calculating Total Program Size
To calculate total program size, the individual estimates must be combined.
  Estimated proxy size (E) = BA + PA + M
The proxy size can be adjusted to create a projected added & modified size (P).
  PROBE method C assumes that you have some historical data but not enough to use statistical methods. You adjust E as follow
    P = (actual A&M size to date/estimated A&M size to date) * E
  PROBE method D assumes that you have no historical data and uses your estimate as the projection, P = E.
Total program size (T) is calculated as
    T = P + B - D - M + R

## Slide 21: PROBE Wizard
The PROBE Wizard automates these calculations. Click the hyperlink on the Size Estimating Template to open the Wizard, then follow the steps that the Wizard displays.

## Slide 22: JD’s Total Program Size
Since JD has no size history, the PROBE Wizard tells him he must select PROBE method D for size.
Once JD selects the PROBE method, the tool has all the information needed to calculate
  estimated proxy size (E) = BA + PA + M = 11 + 118 + 22 = 151
  estimated total Size (T) = P + B - D - M + R = 151 + 224 - 0 - 22 = 353

## Slide 23: Calculating Projected Effort
The projected development time is also based on the estimated proxy size (E).
  PROBE method C assumes that you have some historical data but not enough to use statistical methods. You calculate time by
    Projected Time = (actual total development time to date/ estimated A&M size to date) * E
  PROBE method D assumes that you have no historical data. You use engineering judgment to estimate time.

## Slide 24: JD’s Projected Effort
Since JD has no historical productivity data, the PROBE Wizard tells him he must select method D for time.
The Wizard provides a box for him to enter how long he thinks it will take to complete this program. Thinking that he needs at least a couple of minutes per LOC, he enters 5 hours.

## Slide 25: Estimates Saved to Size Estimating Template
Once you complete the Wizard, the estimates are automatically copied into the PROBE worksheet at the bottom Size Estimating Template.

## Slide 26: Estimates Transferred to Plan Summary
Size and Time estimates are automatically transferred to the Plan Summary automatically. Planned time is distributed across process phases based on historical percentages.

## Slide 27: JD’s PSP1 Project Plan Summary

## Slide 28: Inputting Actual Sizes
During postmortem the actual sizes of parts are entered on the size estimating template.
The actual size of the program is entered in Total, under Actual, in the Program Size Summary section of the project plan summary.

## Slide 29: JD’s Actual Size Data
JD measures the actual size of his program, and gathers the following data.
  JD runs all his source code files through his LOC counter, and finds the total LOC is 361.
  His LOC counter also provide data on the actual size of his added parts.
  He finds that he added 17 LOC and modified 12 LOC from his base.
Added Parts (classes) | Type | Items (methods) | Size (LOC)
Input_data | I/O | 2 | 20
Linked_list | data | 6 | 52
Calc_mean | Calc | 1 | 8
Calc_sd | Calc | 1 | 22
Print_result | I/O | 1 | 18

## Slide 30: Recording Actual Base Part Size
During postmortem, enter the size of each base part.
  Measure and enter the actual base, deleted, modified, and added size. (In the Process Dashboard, the Postmortem script contains a hyperlink to a tool that you may find helpful for measuring deleted, modified, and added LOC.)
Note:
  For a part not estimated, add it and enter zeros in Plan column.
  For a part not used, enter zeros in Actual column.

## Slide 31: Recording Actual Added Part Size
During postmortem, enter the size of each added part.
  Measure and enter the actual size.
  Measure and enter the actual number of items.
Note:
  For a part not estimated, add it and enter zeros in Plan column.
  For a part not used, enter zeros in Actual column.

## Slide 32: Recording Actual Reused Part Size
During postmortem, enter the size of each reused part.
  Measure and enter the actual size of the reused part.
Note:
  For a part not estimated, add it and enter zeros in Plan column.
  For a part not used, enter zeros in Actual column.

## Slide 33: JD’s Size Estimating Template with Actual Size Data

## Slide 34: Recording Total Actual Size
During postmortem, use your line of code counter to measure the actual total size and enter it here. Only total size is entered on the project plan summary.

## Slide 35: JD’s Project Plan Summary with Actual Total Program Size
JD is upset that his individual part estimates were not too accurate.
His instructor tells him that the goal is not to have perfect estimates for each part, but to have balanced estimates where individual errors cancel each other.
The instructor points out that his overall estimate is pretty close to the overall actual.

## Slide 36: Process Improvement Proposal -1
To improve your process, you will need to capture process problems and propose improvements for future reference.
You will need to know
  any problems you have encountered in using the process
  any suggestions you have for process improvements
  your observations and findings from doing the assignments

## Slide 37: Process Improvement Proposal -2
You should complete a PIP form for each assignment.
Open the PIP form by clicking the hyperlink in the Postmortem script.
The dashboard will ask you where you would like to place the file. Then it will create a document, and open it in your word processing application.

## Slide 38: Test Report Template
Use this form to document
  what tests to run
  how to run the tests
  the results that were obtained
Test reports are helpful for
  developing and recording test cases
  performing regression testing
Design your test cases in the design phase and run them in the test phase.

## Slide 39: Coding Standards
Coding standards
  establish a consistent set of coding practices
  provide criteria for judging the quality of the code that you produce
  facilitate size counting by ensuring you are consistent about what you put on each physical line.
The coding standard defines quality-oriented exit criteria for the code phase.

## Slide 40: Reminders
A banner on the Project Plan Summary form will remind you to enter actual size data for program 1.
Don’t forget to mark the project “complete” after you have checked and submitted your assignment.

## Slide 41: Ending the “Follow Along” Portion of the Tutorial
If you have been following along in the Process Dashboard during this tutorial, you will currently have two Process Dashboard windows open.
The main window, which displays “Process Dashboard” in the title bar, is displaying your actual metrics data.
The title bar for the second window will be displaying the name of the data backup ZIP file that you created for this tutorial.
Changes in this second window will be discarded when the window is closed, so it is important not to record any real data there. To prevent an accidental situation where your metrics are recorded in the wrong window,
please close that second window now.

## Slide 42: Messages to Remember
The principal objective of PSP1 is estimation.
PSP1 uses the PROBE estimating method for size and effort estimation.
Historical data are used where available
  in creating relative size tables
  in projecting estimates
Estimates are expected to fluctuate.
  The goal is to make independent estimates of program parts.
  Each part’s actual size may be very different from its planned size.
  As long as the differences balance themselves out, you end up with a pretty accurate overall estimate.