## BackuQuality Model Baseline (2) (hidden)
size | 10000 | LOC | Phase | Latent | Plan Hours | Defect Injection rate per hour | # Injected | Subtotal | Yield | Removed | Remaining | Baseline Densiity [Def/Kloc] | HOURS PER DEFECT REMOVED | BaselineTIME COST [HOURS] | 10000 |  | QPI
Prod Rate DLD-UT | 10 |  | Planning | 0 | 16.7785 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 16.7785 |  | DLD/Code | 1 | 10 | 100 | 16.7785
Design Review Rate | 10000 | Lines/Hr | Requirements | 0 | 50.3356 | 0.25 | 12.5839 | 12.5839 | 0% | 0 | 12.5839 | 1.2584 |  | 50.3356 |  | review/Const | 0 | 30 | 300 | 50.3356
Number Design Inspectors | 1 |  | System Test Plan | 12.5839 | 25.1678 | 0 | 0 | 12.5839 | 0% | 0 | 12.5839 | 1.2584 |  | 25.1678 |  | CR/Code | 0 | 15 | 150 | 25.1678
Design Inspection Rate | 10000 | Lines/Hr | REQ Inspection | 12.5839 | 25.1678 | 0 | 0 | 12.5839 | 70% | 8.8087 | 3.7752 | 0.37752 |  | 25.1678 |  | D/Kloc Comp | 32.6841 | 15 | 150 | 25.1678
Code Review Rate | 10000 |  | High-Level Design | 3.7752 | 100.6711 | 0.25 | 25.1678 | 28.943 | 0% | 0 | 28.943 | 2.8943 |  | 100.6711 |  | D/Kloc UT | 15.6492 | 60 | 600 | 100.6711
Code Inspection Rate | 10000 |  | Integration Test Plan | 28.943 | 25.1678 | 0 | 0 | 28.943 | 0% | 0 | 28.943 | 2.8943 |  | 25.1678 |  | D/KLOK/ST | 9.1627 | 15 | 150 | 25.1678
|  |  | HLD Inspection | 28.943 | 50.3356 | 0 | 0 | 28.943 | 70% | 20.2601 | 8.6829 | 0.86829 |  | 50.3356 |  |  |  | 30 | 300 | 50.3356
Number code Inspectors | 1 |  | Detailed Design | 8.6829 | 200 | 0.8 | 160 | 168.6829 | 0% | 0 | 168.6829 | 16.8683 |  | 200 |  |  |  | 90 | 900 | 151.0067
Inspection Rate | 200 | Lines/Hr | DLD Review | 168.6829 | 0 | 0 | 0 | 168.6829 | 0% | 0 | 168.6829 | 16.8683 |  | 0 |  |  |  | 45 | 450 | 75.5034
|  |  | Test Development | 168.6829 | 25 | 0 | 0 | 168.6829 | 0% | 0 | 168.6829 | 16.8683 |  | 25 |  |  |  | 15 | 150 | 25.1678
Each Code Insp yield | 0.7 |  | DLD Inspection | 168.6829 | 0 | 0 | 0 | 168.6829 | 0% | 0 | 168.6829 | 16.8683 |  | 0 |  |  |  | 45 | 450 | 75.5034
total Code insp yield | 0.7 |  | Code | 168.6829 | 200 | 2.35 | 470 | 638.6829 | 0% | 0 | 638.6829 | 63.8683 |  | 200 |  |  |  | 180 | 1800 | 302.0134
|  |  | Code Review | 638.6829 | 0 | 0 | 0 | 638.6829 | 0% | 0 | 638.6829 | 63.8683 |  | 0 |  |  |  | 90 | 900 | 151.0067
Each Design Insp yield | 0.7 |  | Compile | 638.6829 | 50 | 0.3 | 15 | 653.6829 | 50% | 326.8414 | 326.8414 | 32.6841 |  | 50 |  |  |  | 16 | 160 | 26.8456
total Design insp yield | 0.7 |  | Code Inspection | 326.8414 | 0 | 0 | 0 | 326.8414 | 0% | 0 | 326.8414 | 32.6841 |  | 0 |  |  |  | 90 | 900 | 151.0067
|  |  | Unit Test | 326.8414 | 150 | 0.067 | 10.05 | 336.8914 | 53.55% | 180.3991 | 156.4923 | 15.6492 | 1 | 180.3991 |  |  |  | 25 | 250 | 41.9463
|  |  | Integration Test | 156.4923 | 0 | 0 | 0 | 156.4923 | 0% | 0 | 156.4923 | 15.6492 | 10 | 0 |  |  |  | 0 | 0 | 0
|  |  | System Test | 156.4923 | 16.7785 | 0 | 0 | 156.4923 | 41.45% | 64.8651 | 91.6272 | 9.1627 | 24 | 1556.7627 |  |  |  | 10 | 100 | 16.7785
|  |  | Acceptance Test | 91.6272 | 0 |  | 0 | 91.6272 | 33.26% | 30.4716 | 61.1556 | 6.1156 | 24 | 731.319
|  |  | Baseline Total Plan [Hrs] |  | 935.4027 |  | 692.8017
|  |  | Baseline Total +Defect Fix [Hrs] |  | 2672.5645
|  |  | Development |  | 768.6242
|  |  | UT |  | 330.3991
|  |  | Final Test |  | 2454.8602

## Instructions
Purpose,
Examine the cost/benefit of reviews and inspections using a defect removal and injection model.
Assumptions
Effort time in this model applies only to the developers.
Defects are injected at a predictable rate in each phase
A predictable portion of latent defecgts are removed in each phase
if time is not spent in "Design", a comparable amount of time must be spent in code.
Defect removal is more effective when the defect density is low.
This is a simple pipe and filter defect model. Each process phase can be a defect injector, a remover, or both.
Injections use a rate of defects injected per hour in the activity.
Defect removals are based on Yield.
Data Adjustments can be made in any cell with yellow highlighting
Code and design reviews may a have value of either 0 or 1
This model assumes 10,000 Lines of Code (LOC) developed at a rate of 10 LOC/hr between DLD and UT.
Other phases have time in phase consistent with accumulated TSP data.
The Baseline model assumes no review or inspection in the DLD through UT phases
The Revised model applies a default 50% yield for review and per inspector These values may be overriddeen.
In the default settings, the baseline and revised models have the same outputs. These are displayed on 3 charts
1) Time in development, Unit Test (UT), and System Test (ST)
2) Effort by development phase
3) defect density (defects/KLOC) in each phase.
Inspections are often ineffective because they
developers are not trained
the time has not been planned for
results and effectiveness are not measured so results are not convincing
the delay in the benefit weakens the positive reinforcement of the feedback
the benefits are delayed while the cost is immediate.
pratitioners done believe the results will be achieved

## Quality Model
size | 10000 | LOC | [10 empty] | Phase | Plan Hours | Defect Injection rate per hour | # Injected | Subtotal | Yield | Latent | Removed | Remaining | Revised Densiity [Def/Kloc] | Hours Per Defecty Removed | Revised Time Cost [Hours]
Prod Rate DLD-UT | 10 |  |  |  | Detailed Design | 200 | 0 | [5 empty] | Planning | 16.7785 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 |  | 16.7785
Design Review Rate | 100 | Lines/Hr | Design Review | 0 | DLD Review | 0 | 0 | [5 empty] | Requirements | 50.3356 | 0.25 | 12.5839 | 12.5839 | 0% | 0 | 0 | 12.5839 | 1.2584 |  | 50.3356
Design Inspection Rate | 100 | Lines/Hr |  |  | Test Development |  | 0 | [5 empty] | System Test Plan | 25.1678 | 0 | 0 | 12.5839 | 0% | 12.5839 | 0 | 12.5839 | 1.2584 |  | 25.1678
Code Review Rate | 200 |  | Num. Design Inspectors | 0 | DLD Inspection | 0 | 0 | [5 empty] | REQ Inspection | 25.1678 | 0 | 0 | 12.5839 | 70% | 12.5839 | 8.8087 | 3.7752 | 0.37752 |  | 25.1678
Code Inspection Rate | 200 |  |  |  | Code | 200 | 0 | [5 empty] | High-Level Design | 100.6711 | 0.25 | 25.1678 | 28.943 | 0% | 3.7752 | 0 | 28.943 | 2.8943 |  | 100.6711
|  |  | Code Review | 0 | Code Review | 0 | 0 | [5 empty] | Integration Test Plan | 25.1678 | 0 | 0 | 28.943 | 0% | 28.943 | 0 | 28.943 | 2.8943 |  | 25.1678
[5 empty] | Compile |  | 0 | [5 empty] | HLD Inspection | 50.3356 | 0 | 0 | 28.943 | 70% | 28.943 | 20.2601 | 8.6829 | 0.86829 |  | 50.3356
|  |  | Num. code Inspectors | 0 | Code Inspection | 0 | 0 | [5 empty] | Detailed Design | 200 | 0.8 | 160 | 168.6829 | 0% | 8.6829 | 0 | 168.6829 | 16.8683 |  | 200
[13 empty] | DLD Review | 0 | 0 | 0 | 168.6829 | 0% | 168.6829 | 0 | 168.6829 | 16.8683 |  | 0
[8 empty] | Lines/Hr |  |  |  |  | Test Development | 25 | 0 | 0 | 168.6829 | 0% | 168.6829 | 0 | 168.6829 | 16.8683 |  | 25
|  |  | Inspection Rate | 200 | [8 empty] | DLD Inspection | 0 | 0 | 0 | 168.6829 | 0% | 168.6829 | 0 | 168.6829 | 16.8683 |  | 0
|  |  | Design Review Yield | 0.5 | [8 empty] | Code | 200 | 2.35 | 470 | 638.6829 | 0% | 168.6829 | 0 | 638.6829 | 63.8683 |  | 200
|  |  | Design Inspector Yield | 0.5 | [8 empty] | Code Review | 0 | 0 | 0 | 638.6829 | 0% | 638.6829 | 0 | 638.6829 | 63.8683 |  | 0
|  |  | Code Review Yield | 0.5 | [8 empty] | Compile | 50 | 0.3 | 15 | 653.6829 | 50% | 638.6829 | 326.8414 | 326.8414 | 32.6841 |  | 50
|  |  | Each Code Insptor yield | 0.5 | [8 empty] | Code Inspection | 0 | 0 | 0 | 326.8414 | 0% | 326.8414 | 0 | 326.8414 | 32.6841 |  | 0
[13 empty] | Unit Test | 150 | 0.067 | 10.05 | 336.8914 | 53.55% | 326.8414 | 180.3991 | 156.4923 | 15.6492 | 1 | 180.3991
|  |  | total Design insp yield | 0 | [8 empty] | Integration Test | 0 | 0 | 0 | 156.4923 | 0% | 156.4923 | 0 | 156.4923 | 15.6492 | 10 | 0
|  |  | total Code insp yield | 0 | [8 empty] | System Test | 16.7785 | 0 | 0 | 156.4923 | 41.45% | 156.4923 | 64.8651 | 91.6272 | 9.1627 | 24 | 1556.7627
[13 empty] | Acceptance Test | 0 |  | 0 | 91.6272 | 33.26% | 91.6272 | 30.4716 | 61.1556 | 6.1156 | 24 | 731.319
[13 empty] | Total Plan [Hrs] | 935.4027 |  | 692.8017 |  |  |  | 631.6461
[13 empty] | Total +Defect Fix [Hrs] | 2672.5645
[10 empty] | Development | UT | Final Test | [12 empty] | Reviewers | Inspectors
[9 empty] | New | 768.6242 | 330.3991 | 2454.8602 | [12 empty] | 0 | 0
[9 empty] | Baseline | 768.6242 | 330.3991 | 2454.8602 | [12 empty] | 1 | 1
2
3
4
5
6
7
8
9
10
Note on H5: William R. Nichols: Enter
Note on H7: William R. Nichols: enter 0 or 1

## Quality Model Baseline
size | 10000 | LOC | Phase | Latent | Plan Hours | Defect Injection rate per hour | # Injected | Subtotal | Yield | Removed | Remaining | Baseline Densiity [Def/Kloc] | HOURS PER DEFECT REMOVED | BaselineTIME COST [HOURS] | 10000 |  | QPI
Prod Rate DLD-UT | 10 |  | Planning | 0 | 16.7785 | 0 | 0 | 0 | 0% | 0 | 0 | 0 |  | 16.7785 |  | DLD/Code | 1 | 10 | 100 | 16.7785
Design Review Rate | 10000 | Lines/Hr | Requirements | 0 | 50.3356 | 0.25 | 12.5839 | 12.5839 | 0% | 0 | 12.5839 | 1.2584 |  | 50.3356 |  | review/Const | 0 | 30 | 300 | 50.3356
Number Design Inspectors | 1 |  | System Test Plan | 12.5839 | 25.1678 | 0 | 0 | 12.5839 | 0% | 0 | 12.5839 | 1.2584 |  | 25.1678 |  | CR/Code | 0 | 15 | 150 | 25.1678
Design Inspection Rate | 10000 | Lines/Hr |  | 12.5839 | 25.1678 | 0 | 0 | 12.5839 | 70% | 8.8087 | 3.7752 | 0.37752 |  | 25.1678 |  | D/Kloc Comp | 32.6841 | 15 | 150 | 25.1678
Code Review Rate | 10000 |  | High-Level Design | 3.7752 | 100.6711 | 0.25 | 25.1678 | 28.943 | 0% | 0 | 28.943 | 2.8943 |  | 100.6711 |  | D/Kloc UT | 15.6492 | 60 | 600 | 100.6711
Code Inspection Rate | 10000 |  | Integration Test Plan | 28.943 | 25.1678 | 0 | 0 | 28.943 | 0% | 0 | 28.943 | 2.8943 |  | 25.1678 |  | D/KLOK/ST | 9.1627 | 15 | 150 | 25.1678
|  |  |  | 28.943 | 50.3356 | 0 | 0 | 28.943 | 70% | 20.2601 | 8.6829 | 0.86829 |  | 50.3356 |  |  |  | 30 | 300 | 50.3356
Number code Inspectors | 1 |  | Detailed Design | 8.6829 | 200 | 0.8 | 160 | 168.6829 | 0% | 0 | 168.6829 | 16.8683 |  | 200 |  |  |  | 90 | 900 | 151.0067
Inspection Rate | 200 | Lines/Hr |  | 168.6829 | 0 | 0 | 0 | 168.6829 | 0% | 0 | 168.6829 | 16.8683 |  | 0 |  |  |  | 45 | 450 | 75.5034
|  |  | Test Development | 168.6829 | 25 | 0 | 0 | 168.6829 | 0% | 0 | 168.6829 | 16.8683 |  | 25 |  |  |  | 15 | 150 | 25.1678
Each Code Insp yield | 0.7 |  | DLD Inspection | 168.6829 | 0 | 0 | 0 | 168.6829 | 0% | 0 | 168.6829 | 16.8683 |  | 0 |  |  |  | 45 | 450 | 75.5034
total Code insp yield | 0.7 |  | Code | 168.6829 | 200 | 2.35 | 470 | 638.6829 | 0% | 0 | 638.6829 | 63.8683 |  | 200 |  |  |  | 180 | 1800 | 302.0134
|  |  |  | 638.6829 | 0 | 0 | 0 | 638.6829 | 0% | 0 | 638.6829 | 63.8683 |  | 0 |  |  |  | 90 | 900 | 151.0067
Each Design Insp yield | 0.7 |  | Compile | 638.6829 | 50 | 0.3 | 15 | 653.6829 | 50% | 326.8414 | 326.8414 | 32.6841 |  | 50 |  |  |  | 16 | 160 | 26.8456
total Design insp yield | 0.7 |  |  | 326.8414 | 0 | 0 | 0 | 326.8414 | 0% | 0 | 326.8414 | 32.6841 |  | 0 |  |  |  | 90 | 900 | 151.0067
|  |  | Unit Test | 326.8414 | 150 | 0.067 | 10.05 | 336.8914 | 53.55% | 180.3991 | 156.4923 | 15.6492 | 1 | 180.3991 |  |  |  | 25 | 250 | 41.9463
|  |  | Integration Test | 156.4923 | 0 | 0 | 0 | 156.4923 | 0% | 0 | 156.4923 | 15.6492 | 10 | 0 |  |  |  | 0 | 0 | 0
|  |  | System Test | 156.4923 | 16.7785 | 0 | 0 | 156.4923 | 41.45% | 64.8651 | 91.6272 | 9.1627 | 24 | 1556.7627 |  |  |  | 10 | 100 | 16.7785
|  |  | Acceptance Test | 91.6272 | 0 |  | 0 | 91.6272 | 33.26% | 30.4716 | 61.1556 | 6.1156 | 24 | 731.319
|  |  | Baseline Total Plan [Hrs] |  | 935.4027 |  | 692.8017
|  |  | Baseline Total +Defect Fix [Hrs] |  | 2672.5645
|  |  | Development |  | 768.6242
|  |  | UT |  | 330.3991
|  |  | Final Test |  | 2454.8602

## QProfParam (hidden)
Parameter | Value | Description
Design/Code Time | 100% | Design time as % of coding time
Code Review Time | 50% | Code review time as % of code time
Compile Defects/KLOC | 10 | Compile defects/KLOC
Unit Test Ddefects/KLOC | 5 | Unit test defects/KLOC
Design Review Time | 50% | Design review time as % of design time
Restore Qprofile Parameter Defaults

## PlanGuide (hidden)
General | - If your team does not have historical data, use these guidelines as standard planning factors. - In all cases, use your judgement. If some guideline does not fit your case, use your best estimate instead.
TSP Plans | Overall plan - produced first by the total team and later adjusted to conform to the balanced plan. Bottom-up plan - produced by each engineer for the next phase Balanced plan - the next phase plan after load balancing
Requirements | - The Requirements process depends heavily on The nature of The project, so no General guidelines are given. - In General, expect that all input materials will have be to inspected and substantially reworked.
Requirements Inspections | - The QUAL guideline provides a General factor to use In determining The time needed for The Requirements inspection. - Again, If this number is unrealistic for your project and situation, use your best estimate.
High-Level Design | - The High-Level Design process is highly variable and The time depends principally on The size, complexity, and General nature of The system, so no General guideline is given. - Without prior data, most teams substantially underestimate The time High-L
Implementation Phase | Implementation covers detailed design through unit test. - Calculate total implementation time from LOC/hour rates. - New or large modifications: about 10 LOC per hour. - Small changes to large systems: about 5 LOC per hour. - Pick a number that seems a
Implementation Allocation | In estimating the implementation phases, - Make an overall estimate based on LOC/hour rates. - Then use these percentages to Calculate The phase times.
Detailed design - 22.1%
Detailed design review - 11.1%
Detailed design inspection - 8.8%
Coding - 20.0%
Code review - 10.0%
Compiling - 3.4%
Code inspection - 8.8%
Unit test - 15.8%
Integration and System Test | For these phases, estimate the defect-free test time and add 5 hours per defect in integration and 10 hours in system test

## QualGuide (hidden)
Measure | Goal | Comments
Percent Defect Free (PDF)
Compile | > 10%
Unit Test | > 50%
Integration Test | > 70%
System Test | > 90%
Defects/KLOC:
Total defects injected | 75 - 150 | If not PSP trained, use 100 to 200.
Compile | < 10 | All defects
Unit Test | < 5 | All major defects (in source LOC)
Integration Test | < 0.5 | All major defects (in source LOC)
System Test | < 0.2 | All major defects (in source LOC)
Defect Ratios
Detailed design review defects /unit test defects | > 2.0 | All major defects (in source LOC)
Code review defects/compile defects | > 2.0 | All major defects (in source LOC)
Development Time Ratios
Requirements inspection/requirements time | > 0.25 | Elicitation in requirements time
High-level design inspection/high-level design time | > 0.5 | Design work only, not studies
Detailed design/coding time | > 1.00
Detailed design review/detailed design time | > 0.5
Code review/code time | > 0.5
Review and Inspection Rates
Requirements pages/hour | < 2 | Single-spaced text pages
High-level design pages/hour | < 5 | Formatted design logic
Detailed design text lines/hour | < 100 | Pseudocode ~ equal to 3 LOC
Code LOC/hour | < 200 | Logical LOC
Defect Injection and Removal Rates
Requirements defects injected/hour | 0.25 | Only major defects
Requirements inspection defects removed/hour | 0.5 | Only major defects
High-level design defects injected/hour | 0.25 | Only major defects
High-level design inspection defects removed/hour | 0.5 | Only major defects
Detailed design defects injected/hour | 0.75 | Only design defects
Detailed design review defects removed/hour | 1.5 | Only design defects
Detailed design inspection defects removed/hour | 0.5 | Only design defects
Code defects injected/hour | 2 | All defects
Code review defects removed/hour | 4 | All defects in source LOC
Compile defects injected/hour | 0.3 | Any defects
Code inspection defects removed/hour | 1 | All defects in source LOC
Unit test defects injected/hour | 0.067 | Any defects
Phase Yields
Team requirements inspections | ~ 70% | Not counting editorial comments
Design reviews and inspections | ~ 70% | Using state analysis, trace tables
Code reviews and inspections | ~ 70% | Using personal checklists
Compiling | ~ 50% | 90+ % of syntax defects
Unit test - at 5 or less defects/KLOC | ~ 90% | For high defects/KLOC - 50-75%
Integration and system test - at < 1.0 defects/KLOC | ~ 80% | For high defects/KLOC - 30-65%
Acceptance test - at < 1.0 defects/KLOC | ~ 65% | For high defects/KLOC - 30%
Before compile | >75% | Assuming sound design methods
Before unit test | > 85% | Assuming logic checks in reviews
Before integration test | > 97.5% | For small products, 1 defect max.
Before system test | > 99% | For small products, 1 defect max.

## Rates and Yields
Phase Yield Planning Guidelines |  |  |  | Defect Injection Rates Planning Guidelines
Planning | 0% |  |  | Planning | 0
Requirements | 0% |  |  | Requirements | 0.25 | Only major defects
System Test Plan | 0% |  |  | System Test Plan | 0
REQ Inspection | 70% | Not counting editorial comments |  | REQ Inspection | 0
High-Level Design | 0% |  |  | High-Level Design | 0.25 | Only major defects
Integration Test Plan | 0% |  |  | Integration Test Plan | 0
HLD Inspection | 70% | Using state analysis, trace tables |  | HLD Inspection | 0
Detailed Design | 0% |  |  | Detailed Design | 0.75 | Only design defects
DLD Review | 70% | Using state analysis, trace tables |  | DLD Review | 0
Test Development | 0% |  |  | Test Development | 0
DLD Inspection | 70% | Using state analysis, trace tables |  | DLD Inspection | 0
Code | 0% |  |  | Code | 2 | All defects
Code Review | 70% | Using personal checklists |  | Code Review | 0
Compile | 50% | 90+ % of syntax defects |  | Compile | 0.3 | Any defects
Code Inspection | 70% |  |  | Code Inspection | 0
Unit test - at < 5 defects/KLOC | 90% | For high defects/KLOC - 50-75% |  | Unit Test | 0.067 | Any defects
Integration test at < 1.0 defects/KLOC | 80% | For high defects/KLOC - 30-65% |  | Build and Integration Test | 0
System test - at < 1.0 defects/KLOC | 80% | For high defects/KLOC - 30-65% |  | System Test | 0
Acceptance test - at < 1.0 defects/KLOC | 65% | For high defects/KLOC - 30%
These tables implement test yields that increase inversely with defect density. This is an advanced feature that doesn't affect time as much as final escapes.
Unit test Def/KLOC | yield |  |  | phase | [min/def] | [def/hr]
100 | 0.3 | max | 0.9 | Design Review | 5 | 12
60 | 0.3 | min | 0.3 | Design Inspection | 22 | 2.7273
20 | 0.4 | 2 | 0.8 | Code Review | 2 | 30
15 | 0.5 | 60 | 0.3 | Compile
10 | 0.6 | m | -0.0086207 | Code Inspection | 25 | 2.4
8 | 0.75 | b | 0.81724 | Unit Test | 32 | 1.875
5 | 0.8 |  |  | Integration Test | 700 | 0.085714
3 | 0.8 |  |  | System Test | 1405 | 0.042705
1 | 0.8 |  |  | aceptance Test
0 | 0.9
[5 empty] | density | yield | 0.80862
System test Def/KLOC | yield | max | 0.8 |  | 1
100 | 0.2 | min | 0.3
20 | 0.3 | 1 | 0.8
16 | 0.3 | 20 | 0.3
8 | 0.4 | m | -0.026316
4 | 0.5 | b | 0.82632
2 | 0.66
1 | 0.8
0 | 0.8
Acceptance test Def/KLOC | yield
100 | 0.2 | max | 0.65
10 | 0.3 | min | 0.3
8 | 0.4 | 1 | 0.65
4 | 0.5 | 10 | 0.3
2 | 0.6 | m | -0.038889
1 | 0.65 | b | 0.68889
0 | 0.65
Code/Def Review Rate Def/KLOC | yield
0 | 0.7 | max | 0.7
100 | 0.7 | min | 0
125 | 0.65 | 100 | 0.7
150 | 0.6 | 1000 | 0
175 | 0.55 | m | -0.00077778
200 | 0.5 | b | 0.77778
225 | 0.4
250 | 0.3
275 | 0.2
300 | 0.1
400 | 0
500 | 0
600 | 0
700 | 0
800 | 0