## Sheet1
Product Name | Widget A
Estimate (hrs) | 100
Size: | 1000 | KLOC
Process Name | Programming Process
| Process Step | TSP Phase | Step % | Hours | Description of work to be implemented during the given step
| Plan | PLAN | 5% | 5
| Design | DLD | 20% | 20
| Design Review | DLDR | 10% | 10
| Design Inspection | REQINSP | 10% | 10
| Code | CODE | 20% | 20
| Code Review | CR | 10% | 10
| Code Inspection | CODEINSP | 10% | 10
| Test | UT | 10% | 10
| PM | PM | 5% | 5
Directions:
1. Understand the product to be created
2. Analyzed past data for similar examples that can be used as a basis for estimate
3. Identify the process to be used or create a new process to meet your needs
4. Based on past work and current understanding of product being created. List all the work to be implemented/accomplished for each process step
5. Estimate the total size of the product (consider estimation by parts)
6. Estimate the amount of time required to complete product (consider estimation by parts)
7. Review the Step % and Hours allocated to each step for reasonableness (will you be able to complete all the work outlined in the description within the estimated time)
8. Adjust estimate as needed
9. Review estimate with team during meeting 4 of the launch / re-launch.
a. Explain product
b. Explain process selected
c. Review description of work to be implemented during a given step for completeness
d. Review hour estimates for reasonableness
e. Adjust estimate as needed
Note on B1: Tim Chick: In this case product can be anything (code, specification, report, testing, etc.)
Note on C3: Tim Chick: Insert the size measure such as KLOC or text pages.
Note on F5: Tim Chick: Provide a detailed list of all the work anticipated during the given step.