Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR

| Team Member Name: | Team Member B |
| --- | --- |
| Team Name: | AIM |
| Role: | Implementation Manager/Backup Support Manager |
| Date Checkpoint Review Conducted: |  |
| Coach Name: |  |

| Time Logging | Observations |
| --- | --- |
| Are times mostly recorded as the work is done? | X |
| Is interrupt time tracked appropriately? | X |
| Is comment field used to help guide and remind member of work? | Comments field not being used |
| Other observations and questions for team member |  |

| Defect Logging | Observations |
| --- | --- |
| Do all defects have required data? | X |
| Were defect injected before they were removed? | X |
| Does every defect have a fix time? | X |
| Do defects injected in compile and tests have fix numbers? | N/A |
| Are defects adequately described? | X |
| Are defect types consistent with descriptions? | X |
| Are defect types consistent with phase injected? | X |
| Are defect types assigned consistently? | X |
| Other observations and questions for team member |  |
| MAINT-LD-952 INSP time is 43.6, Fix Time is 1.0. MAINT-LD-959 INSP time is 63.2, Fix Time is 2.0. Team Member B said he thought at that time there was a lot they did to put together the material for the inspection that just took time to do. |  |

| Defect log and time log consistency | Observations |
| --- | --- |
| Are defects being recorded for personal reviews and inspections? | X |
| Are defects being recorded for tests? | None Found |
| Are defects removed consistent with compile and test phase time and program size? | X |
| Is total compile defect fix times less than compile time? | X |
| Is total test defect fix times less than test time? | N/A |
| Are defect dates and phases consistent with the time log? | X |
| Other observations and questions for team member |  |

(continued on next page)

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR (continued)

| Tasks | Observations |
| --- | --- |
| Are all tasks < one week of effort in the next 2-4 weeks? | FINAL CM Package = 20 hours < 22 |
| Are all tasks following a process as defined in the PSSP? | X |
| Is the number of open task hours < 5% of the plan? | 10.7 < (5% of 286.1) |
| Are all open tasks hours < one week of effort? | 10.7 < 22 |
| Other observations and questions for team member |  |

| Schedule | Observations |
| --- | --- |
| Is vacation or other significant things scheduled? | X |
| Is the next launch or re-launch scheduled? | X |
| Other observations and questions for team member |  |

| Quality | Observations |
| --- | --- |
| Are actual phase yields close to or exceeding plan yields? | Y |
| Are actual defect injections lower than or close to planned inject rates? | N |
| Are review rates appropriate? | N, less |
| Do designs conform to team design standards? | Not doing detailed design for this cycle |
| Does code conform to team coding standards? | No coding standard specified |
| Is there evidence that checklists are being used in personal reviews? | X |
| Are review rates for inspections appropriate? | N, less |
| Are checklists being used in performing inspections? | X |
| Are Process Quality Indicator ratios close to expected? | N |
| Are the actual phase yields reasonable? | Y |
| Are checklists up to date? | Somewhat |
| Are reviews and inspections being done properly? | X |
| Other observations and questions for team member |  |
| Maint – LD, CR 1, CODE 4. 23.489 * 0.039 = 0.91 Defects, Found 5. ~1/12 and 1/8 ratios, plan was more like 1/6 and 1/3. |  |

(continued on next page)

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR (continued)

| Week | Observations |
| --- | --- |
| Is current plan date not > 1 week later than baseline date? | 5/10 before 5/31 |
| Is predicted date not > 2 weeks later than baseline date? | 5/24 before 5/31 |
| Is growth > 5% of plan? | -15.7% |
| Are schedule hours this cycle to date < 10% of plan? | 158.9/164.6, X |
| Are to date hours for task completed > 10% of plan? | 148.3/152.2, X |
| Are milestone dates being met? | X |
| Other observations and questions for team member |  |

| Summary data | Observations |
| --- | --- |
| Are actual sizes being recorded? | X |
| Other observations and questions for team member |  |

| Project Overview | Observations |
| --- | --- |
| Baseline Plan End Date | 5/31/2010 |
| Current Plan End Date | 5/10/2010 |
| Predicted End Date | 5/24/2010 |
| Earn Value Per Week (are most weeks ahead or behind baseline?) | Behind |
| Did the current plan change a lot from the baseline? | Yes. |
| How many actual hours are ahead of / behind plan? | 3.6 behind plan |
| Defects removed by phase (are they tracking defects? How does actual defects removed by phase compare to plan?) |  |
| Other observations and questions for team member |  |

(continued on next page)

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR (continued)

| Role Data (Scripts and Forms) | Observations |
| --- | --- |
| Is the team member performing all the responsibilities outlined in the role specification? | X |
| Is the team member following all the scripts for which they are responsible? | X |
| Are all the forms for which the team member is responsible being completed and maintained correctly? | X |
| Other observations and questions for team member |  |
| Some process deviations indicate that processes need to be updated or else deviations need to be approved. |  |
| People are looking up defect descriptions in the book since they aren’t on the TAB. |  |
| CM Scripts and Forms need to be reviewed and updated to reflect using ExtraView |  |
| Test script is being loosely followed/needs updating |  |
| WEEK also needs to be updated |  |