Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR

| Team Member Name: | Team Member G |
| --- | --- |
| Team Name: | AIM |
| Role: | Team Leader |
| Date Checkpoint Review Conducted: |  |
| Coach Name: |  |

| Time Logging | Observations |
| --- | --- |
| Are times mostly recorded as the work is done? | Sometimes, some backfill |
| Is interrupt time tracked appropriately? | X |
| Is comment field used to help guide and remind member of work? | X |
| Other observations and questions for team member |  |

| Defect Logging | Observations |
| --- | --- |
| Do all defects have required data? | X |
| Were defect injected before they were removed? | X |
| Does every defect have a fix time? | X |
| Do defects injected in compile and tests have fix numbers? | X |
| Are defects adequately described? | X |
| Are defect types consistent with descriptions? | X |
| Are defect types consistent with phase injected? | X |
| Are defect types assigned consistently? | X |
| Other observations and questions for team member |  |
| Where are defects 1 and 2? |  |

| Defect log and time log consistency | Observations |
| --- | --- |
| Are defects being recorded for personal reviews and inspections? | X, very little found |
| Are defects being recorded for tests? | X |
| Are defects removed consistent with compile and test phase time and program size? | X |
| Is total compile defect fix times less than compile time? | None Found in Compile |
| Is total test defect fix times less than test time? | X |
| Are defect dates and phases consistent with the time log? | X |
| Other observations and questions for team member |  |
| Latent Fix: 51 hours coding * 0.039 defects/hour = 1.989 Defects. 3 found |  |

(continued on next page)

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR (continued)

| Tasks | Observations |
| --- | --- |
| Are all tasks < one week of effort in the next 2-4 weeks? | No, Latent Fix @ 17 hours |
| Are all tasks following a process as defined in the PSSP? | X |
| Is the number of open task hours < 5% of the plan? | 2.6 hours open |
| Are all open tasks hours < one week of effort? | Yes |
| Other observations and questions for team member |  |

| Schedule | Observations |
| --- | --- |
| Is vacation or other significant things scheduled? | Not obvious |
| Is the next launch or re-launch scheduled? | X |
| Other observations and questions for team member |  |

| Quality | Observations |
| --- | --- |
| Are actual phase yields close to or exceeding plan yields? | Yes |
| Are actual defect injections lower than or close to planned inject rates? | Yes |
| Are review rates appropriate? | Better than Planned |
| Do designs conform to team design standards? | No design work |
| Does code conform to team coding standards? | No coding standard |
| Is there evidence that checklists are being used in personal reviews? |  |
| Are review rates for inspections appropriate? | X |
| Are checklists being used in performing inspections? |  |
| Are Process Quality Indicator ratios close to expected? | X |
| Are the actual phase yields reasonable? | X |
| Are checklists up to date? | X |
| Are reviews and inspections being done properly? | X |
| Other observations and questions for team member |  |
| Maint – Latent Defects. 3 Defects from Code. 2 Removed in CR, 1 in CODEINSP. |  |
| 20.12 hrs * 0.038D/HR = 0.76 expected defects. x 0.7 = 0.532 found in CR. |  |
| 4.352 CR/20.12 hrs = 0.216 hrs review rate. 51.101/296.389 = 0.172 Planned Review rate. Exceeded plan! |  |
| 10952, RR: 47LOC/HR; 10957, RR: 74LOC/HR, 10960, RR: 88/HR |  |

(continued on next page)

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR (continued)

| Week | Observations |
| --- | --- |
| Is current plan date not > 1 week later than baseline date? | 3 weeks out |
| Is predicted date not > 2 weeks later than baseline date? | == |
| Is growth > 5% of plan? | -31.9% |
| Are schedule hours this cycle to date < 10% of plan? | 75.8% of plan |
| Are to date hours for task completed > 10% of plan? | 61.25% of Plan |
| Are milestone dates being met? | No Milestone Dates |
| Other observations and questions for team member |  |

| Summary data | Observations |
| --- | --- |
| Are actual sizes being recorded? | X |
| Other observations and questions for team member |  |

| Project Overview | Observations |
| --- | --- |
| Baseline Plan End Date | 5/24/2010 |
| Current Plan End Date | 6/14/2010 |
| Predicted End Date | 5/24/2010 |
| Earn Value Per Week (are most weeks ahead or behind baseline?) | Behind |
| Did the current plan change a lot from the baseline? | Yes |
| How many actual hours are ahead of / behind plan? | 18.1 behind, but EV ahead |
| Defects removed by phase (are they tracking defects? How does actual defects removed by phase compare to plan?) | Exceed Plan |
| Other observations and questions for team member |  |

(continued on next page)

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR (continued)

| Role Data (Scripts and Forms) | Observations |
| --- | --- |
| Is the team member performing all the responsibilities outlined in the role specification? |  |
| Is the team member following all the scripts for which they are responsible? |  |
| Are all the forms for which the team member is responsible being completed and maintained correctly? |  |
| Other observations and questions for team member |  |