## Instructions
The purpose of this spreadsheet is to enable a team to see the changes that occur to various quality calculations when parameters are changed.
In general, enter data in yellow areas. White areas are calculated.
Enter planning data from launch notebook in order to see the impact of making changes to different variables.
Spreadsheet Version | 2007.11.12 | Original version by Tim Chick

## Quality
Phase | Latent | Plan Hours | Defect Injection rate per hour | # Injected | Subtotal | Yield | Removed | Remaining
Planning | 0 | 10 | 0 | 0 | 0 | 0% | 0 | 0
Requirements | 0 | 30 | 0.25 | 7.5 | 7.5 | 0% | 0 | 7.5
System Test Plan | 7.5 | 15 | 0 | 0 | 7.5 | 0% | 0 | 7.5
REQ Inspection | 7.5 | 15 | 0 | 0 | 7.5 | 70% | 5.25 | 2.25
High-Level Design | 2.25 | 60 | 0.25 | 15 | 17.25 | 0% | 0 | 17.25
Integration Test Plan | 17.25 | 15 | 0 | 0 | 17.25 | 0% | 0 | 17.25
HLD Inspection | 17.25 | 30 | 0 | 0 | 17.25 | 70% | 12.075 | 5.175
Detailed Design | 5.175 | 90 | 0.75 | 67.5 | 72.675 | 0% | 0 | 72.675
DLD Review | 72.675 | 45 | 0 | 0 | 72.675 | 70% | 50.8725 | 21.8025
Test Development | 21.8025 | 15 | 0 | 0 | 21.8025 | 0% | 0 | 21.8025
DLD Inspection | 21.8025 | 45 | 0 | 0 | 21.8025 | 70% | 15.2617 | 6.5408
Code | 6.5408 | 180 | 2 | 360 | 366.5408 | 0% | 0 | 366.5408
Code Review | 366.5408 | 90 | 0 | 0 | 366.5408 | 70% | 256.5785 | 109.9622
Compile | 109.9622 | 16 | 0.3 | 4.8 | 114.7622 | 50% | 57.3811 | 57.3811
Code Inspection | 57.3811 | 90 | 0 | 0 | 57.3811 | 70% | 40.1668 | 17.2143
Unit Test | 17.2143 | 25 | 0.067 | 1.675 | 18.8893 | 90% | 17.0004 | 1.8889
Integration Test | 1.8889 | 0 | 0 | 0 | 1.8889 | 80% | 1.5111 | 0.37779
System Test | 0.37779 | 10 | 0 | 0 | 0.37779 | 80% | 0.30223 | 0.075557
Acceptance Test | 0.075557 |  |  | 0 | 0.075557 | 65% | 0.049112 | 0.026445
Yellow = input fields
Phase |  | # Injected | Removed | Subtotal | Yield | Remaining
Planning |  | 0 | 0 | 0 | 0% | 0
Requirements |  | 7.5 | 0 | 7.5 | 0% | 7.5
System Test Plan |  | 0 | 0 | 7.5 | 0% | 7.5
REQ Inspection |  | 0 | 5.25 | 7.5 | 70% | 2.25
High-Level Design |  | 15 | 0 | 17.25 | 0% | 17.25
Integration Test Plan |  | 0 | 0 | 17.25 | 0% | 17.25
HLD Inspection |  | 0 | 12.075 | 17.25 | 70% | 5.175
Detailed Design |  | 67.5 | 0 | 72.675 | 0% | 72.675
DLD Review |  | 0 | 50.8725 | 72.675 | 70% | 21.8025
Test Development |  | 0 | 0 | 21.8025 | 0% | 21.8025
DLD Inspection |  | 0 | 15.2617 | 21.8025 | 70% | 6.5407
Code |  | 360 | 0 | 366.5408 | 0% | 366.5408
Code Review |  | 0 | 256.5785 | 366.5408 | 70% | 109.9622
Compile |  | 4.8 | 57.3811 | 114.7622 | 50% | 57.3811
Code Inspection |  | 0 | 40.1668 | 57.3811 | 70% | 17.2143
Unit Test |  | 1.8 | 17.0004 | 19.0143 | 89.41% | 2.0139
Integration Test |  | 0 | 1.5111 | 2.0139 | 75.03% | 0.50279
System Test |  | 0 | 0.30223 | 0.50279 | 60.11% | 0.20056
Acceptance Test |  | 0 | 0.049112 | 0.20056 | 24.49% | 0.15145
Phase | Latent | Plan Hours | # Injected | Defect Injection rate per hour
Planning | 0 | 10 | 0 | 0
Requirements | 0 | 30 | 7.5 | 0.25
System Test Plan | 0 | 15 | 0 | 0
REQ Inspection | 0 | 15 | 0 | 0
High-Level Design | 0 | 60 | 15 | 0.25
Integration Test Plan | 0 | 15 | 0 | 0
HLD Inspection | 0 | 30 | 0 | 0
Detailed Design | 0 | 90 | 67.5 | 0.75
DLD Review | 0 | 45 | 0 | 0
Test Development | 0 | 15 | 0 | 0
DLD Inspection | 0 | 45 | 0 | 0
Code | 0 | 180 | 360 | 2
Code Review | 0 | 90 | 0 | 0
Compile | 0 | 16 | 4.8 | 0.3
Code Inspection | 0 | 90 | 0 | 0
Unit Test | 0 | 25 | 1.675 | 0.067
Integration Test | 0 | 0 | 0 | 0
System Test | 0 | 10 | 0 | 0
Acceptance Test | 0 |  | 0 | 0