## Slide 1
TSP Coach Training
The Launch Process –
Meetings 8 and 9

## Slide 2: Lecture Objectives
At the end of this lecture, you will know
  the process for creating the management presentation
  the recommended content for the management presentation
  how to prepare the team, team leader, and management for the management review
  how to conduct meetings 8 and 9
  common situations that occur in the management review
Notes: <number>

## Slide 3: Lecture Overview
Overview of the management review
Meeting 8/9 exercise
Coaching considerations
Reference material
Notes: <number>

## Slide 4: The Launch Process Meetings
1. Establish
product and
business
goals
2. Assign roles
and define
team goals
4. Build overall
and
near-term
plans
5. Develop
the quality
plan
6. Build individual
and
consolidated
plans
7. Conduct
risk
assessment
8. Prepare
management
briefing and
launch report
Launch
postmortem
9. Hold
management
review
3. Produce
development
strategy
and process
A TSP team coach guides the team through a defined process to develop its plan and to negotiate that plan with management.
Notes: <number>

## Slide 5: Context for the Management Review
This is a critical part of the launch process.
In the first launch meeting, management established the product and business goals for the team.
In meetings 2 through 7, the team developed its plan for meeting those goals.
The management review is the team’s opportunity to convince management that its plan is responsive to those goals.
Handling this meeting properly is crucial for the team to negotiate a rational plan.
Notes: Almost all plans have longer schedules and cost more than management wishes.
This is not surprising; management has proposed the most aggressive date that they think the team can meet.
The team may need to tell management that the requested date cannot be met, at least with the resources provided

## Slide 6: Purpose of the Management Review
The team’s objectives for the management review are
  for management to understand the plan
  to convince management that the plan is a responsible answer to their request
  to convince management that the team is committed to meeting the plan
  for management to agree to the team plan, or to identify resolution actions and assign responsibilities
Notes: <number>

## Slide 7: Meeting 8/9 Exercise
Exercise purpose.
  understand how launch meeting 8 and 9 are conducted
  know what should be in the management presentation
  recognize issues that might arise and understand how to deal with them
Directions (see meeting 8/9 exercise workbook).
  assemble into your launch team groups
  prepare a management presentation on your plan, i.e., conduct launch meeting 8 using script LAU8
  each team will give their management presentation to the class; instructors will play the role of management during the presentations.
  class discussion of how process worked
After the exercise, we will conclude the module with a discussion of coaching considerations from the lecture slides.
Notes: <number>

## Slide 8: Coaching Considerations
Before the meeting
  Make sure the team is committed to the plan. Resolve any issues in meeting 8.
  Prepare an alternative plan(s) that come closer or meets management’s goals, if needed.
  Dry run the presentation.
  Raise significant issues with management before the meeting.
  Use the TSP Managing Briefing Guidelines
Notes: <number>

## Slide 9: Coaching Considerations (continued)
During the meeting
  Address performance against management’s goals early in the presentation.
  Separate the technical and business issues.
  Don’t let the team commit to changes they haven’t investigated and planned.
  Don’t let the team leader make new commitments for the team.
  Document next steps.
Notes: <number>

## Slide 10: Messages to Remember
The team presents its plan (and alternatives, if any) to management and answers questions.
Management determines whether
  the plan is based on sound estimates, historical data, and a quality process
  the team believes in their plan
  the plan or an alternative meets the business need
Management
  approves the plan or an alternative
  asks the team to look at a different alternative
Notes: <number>

## Slide 11: Reference Material
Preparing the presentation
Preparing the participants
Conducting the review
Notes: <number>

## Slide 12: TSP Coach Role In Preparation
By this time in the launch, the team should have developed cohesion and be functioning fairly well. You should be able to relax and watch the team perform.
The main responsibilities for the coach in developing the management presentation are as follows.
  Explain the strategy for the management presentation to the team at the beginning of meeting 8.
  Provide feedback to the team on their presentation.
    Does it cover all the topics?
    Does it answer likely management questions?
    Does it tell management at the beginning what the punch line is?
  Prepare the team, team leader, and management for the review.
Notes: Team members may not be familiar with using powerpoint, may need some help.
Team needs to create the gantt chart, will need some help doing this.
Team leaders are usually familiar with powerpoint.

## Slide 13: Preparing the Management Presentation
The steps for creating the management presentation are as follows.
  Plan the presentation (meeting 8).
  Create the slides and handout (individual work).
  Review the presentation and handouts (team meeting before the management meeting).
  Fix any problems found in the team review.
  Make copies of the presentation and handouts.
Notes: <number>

## Slide 14: Conducting Meeting 8
Refer to the TSP Launch Meeting 8 Script (LAU8).
The coach
  reviews the objectives and procedures for the meeting
  explains the strategy/content for the management presentation
The team leader leads the team in planning the agenda for the management meeting. The team decides
  what material to present
  what material to include in a handouts
  who will give the presentation
  who will develop each item
  when to meet to assemble and review the presentation and handouts
The team working style in this meeting varies between open group and closed group, depending on the team and team leader.
Notes: Meeting 8 normally is held in the afternoon of the third day.
At the end of meeting 8, the team members work individually on their assignments for creating pieces of the management presentation and the handout.
Depending on the timing, the team either reassembles later during the third day or early on the fourth day to review the assembled management presentation and handout.
The team leader leads the team in reviewing the presentation and handout.
Any problems found in the team review are corrected and final copies are prepared for the management presentation.
Having team members present part of the plan is a good way to show it’s the team’s plan, not just the team leaders.

## Slide 15: Strategy for the Presentation -1
Establish credibility by demonstrating that the team has done a thorough and complete job.
  Describe the planning process.
  Explain what the team produced.
Answer management’s implied question, “Did they hear me?”
  Restate management’s goals from launch meeting 1.
  Include implied goals and quantified objectives.
  Summarize briefly how the base plan (and alternate plans, if any) compare with management’s goals.
Notes: <number>

## Slide 16: Strategy for the Presentation -2
Explain the base plan (and any alternate plans, if the base plan does not meet management’s goals).
  Present a list of key milestones events and corresponding dates.
  Include a summary of the quality plan, and explain its impact on test time and maintenance costs.
  Present alternate plans, with key milestones.
    Show schedules with several resource levels.
    Describe how added resources would improve goal performance.
If there are multiple plans, ask management for their preference.
Notes: <number>

## Slide 17: Strategy for the Presentation -3
Present the risks that the team identified.
  Summarize only a few of the key risks.
  Mention the team’s plans for managing these risks.
  Mention any mitigation help that the team will need from management.
Open the meeting to questions and discussion.
Close the meeting with a summary of the action items and who will handle them.
A suggested outline for the presentation is provided in the guideline entitled TSP Management Briefing Guidelines.
Notes: <number>

## Slide 18: Suggested Slides for the Presentation
Title slide
Agenda
Purpose of meeting
Team members
TSP launch process
TSP launch products
Goals
Plan versus goals summary
Plan
  conceptual design
  size estimates
  strategy: builds and content
  quality plan summary
  Gantt chart of key milestones
Alternate plans
Risks
Discussion
Summary
Notes: Point out here that the presentation is at a summary level.

## Slide 19: Prepare the Team
When the team reviews the management presentation, take a couple of minutes to review the points below.
If management asks for a change in the team’s plan, the team needs to
  understand what plan changes are desired
  understand what resources or work content changes to plan are for
  study the changes and replan the work before agreeing to a new schedule or plan
Make one last check that the team is committed to the plan. If there are any issues within the team with respect to the plan, address those issues now, before the management review.
Notes: A question in the back of management’s mind will be, “Did this team really try to do what we want, or are they playing it safe?”
There is no way for management to know if the team really tried hard, so it comes down to a question of trust.
Management’s most important single consideration in deciding whether or not to trust the team’s plan is their perception of the team’s attitude.
At the management review, the team members need to demonstrate that they all
  are committed to the plan
  believe it is the best plan they can make

## Slide 20: Prepare the Team Leader -1
Get a few minutes with the team leader to discuss the following points.
The team leader should tell management the “bottom line” at the very beginning of the management review meeting. Otherwise, management will
  spend the entire meeting wondering what is coming
  not know when to bore in and ask questions
  not know when to relax and listen
A good way to do this is during the agenda review with some words like this.
“Here is what we will be telling you. The bottom line is that we do not precisely meet your desired date. We will show you what we can do, and present several alternate plans that come quite close to your objectives for the project.”
Notes: Also, consider letting management know earlier in the week with words from p 176.

## Slide 21: Prepare the Team Leader -2
The team leader cannot make commitments to management without consulting the team.
  The team owns the plan and is committed to it.
  If the team leader agrees to a management-requested change to the plan without consulting the team, it becomes the team leader’s plan, not the team’s.
If management asks for a change in the plan, the team leader must inform management that the team will
  review the changes
  let management know what the impact will be
Notes:   One of the most common mistakes for a team leader to make during the presentation is to make commitments to management without consulting the team.

## Slide 22: Prepare the Team Leader -3
Review the presentation hints in the TSP STATUS specification with the team leader.
1. Start the meeting by briefly covering the purpose and agenda.
  State any key issues or problems to be raised.
  Let them know that the problems will be discussed later.
  If they wish to discuss the problems now, do so.
2. Move quickly.
  Managers are bright people and catch on quickly.
  Cover the pertinent facts, but nothing extra.
  Don’t lecture or try to teach.
  Ask if there are questions.
3. Use plain language. Avoid terms that require a verbal explanation.
Notes: <number>

## Slide 23: Prepare the Team Leader -4
4. Be crisp.
  Have a team member record any action items during the meeting.
  At the end of the meeting, briefly review actions items, making sure that the team understands them.
5. Know when to stop.
  Once management has approved the plan, stop.
  You have nothing to gain by continuing, and you could cause management to reexamine their decision.
6. Make sure that you understand the outcomes. Do not leave the meeting confused about what management said or what they want you to do.
Notes: <number>

## Slide 24: Prepare the Team Leader -5
7. Bring lots of backup.
  Have a complete copy of the team’s plan.
  When you get to the discussion of the plan details, make these points.
    The team has done a great deal of work.
    The plan has considerable detail.
  Let team members answer questions.
    gives members management exposure
    shows that the members support the plan
Notes: <number>

## Slide 25: Prepare Management
If significant issues will be raised at the management review, either the coach or the team leader should warn management before the meeting. (See the earlier discussion of team leader preparation.)
The coach may talk with management to recommend that they review their TSP preparation guidelines for meeting 9.
In the meeting, management should assure themselves that the team
  has done its best to meet management’s goals
  is committed to meeting the plan
Notes: You don’t to “drop a bomb” on management at this meeting.

## Slide 26: Conducting Meeting 9
Refer to TSP Launch Meeting 9 Launch Script (LAU9).
The team leader presents the team’s plan, using the presentation developed in meeting 8.
The team answers any management questions on the base plan and alternatives.
At the end of the meeting, management and the team should either agree on a plan (the base plan or an alternative) or on resolution actions.
The meeting ends with a review of action items.
Notes: Do some war stories with this
teradyne 9 month requested – 18 month plan – tried to separate the team
EBS – wanted system in 9 months – 24 months earliest – multi-team plan was powerful in convincing that 9 months wasn’t possible.