## Slide 1
TSP Coach Training
Other Launch Considerations
Notes: Things to add:
  Need to bring in the PSP comparison,
  try contrasting the tsp and psp by looking at the process phases. Psp planning compares to tsp launch only it’s for a team, not an individual. Work phases are not so similar but the concepts relate. A tsp plan goes for just a phase, psp encompasses a module. Psp plans are not used to make commitments, tsp launches include management agreement on the plan. Continue with these comparisons.
  Both have scripts, forms,standards, measures etc
  Engineers plan and track work including quality.
  Engineers track time on task, defects, size, and schedule status
  Forms are similar plan summary – sump, task, schedule, etc
Overall, need to bring this into the lecture so it relate to their knowledge of psp.
Need more launch coach skills/characteristics.

## Slide 2: Lecture Objectives
At the end of this lecture, you will understand
  the TSP launch postmortem process
  how to prepare for a launch
  how to conduct a relaunch
  coaching considerations for launch postmortems, launch preparation, and relaunches
Notes: <number>

## Slide 3: Lecture Overview
The launch postmortem
Launch preparation procedures
Conducting a relaunch
Notes: <number>

## Slide 4: The Launch Process Meetings
1. Establish
product and
business
goals
2. Assign roles
and define
team goals
4. Build overall
and
near-term
plans
5. Develop
the quality
plan
6. Build individual
and
consolidated
plans
7. Conduct
risk
assessment
8. Prepare
management
briefing and
launch report
Launch
postmortem
9. Hold
management
review
3. Produce
development
strategy
and process
New teams:
TSP process
review
Notes: <number>

## Slide 5: Launch Postmortem Purpose
The postmortem provides a structured way to learn what worked and what did not work during the launch. It allows the team to
  identify and discuss lessons learned
  evaluate the launch process and submit process improvement proposals
  wrap up the launch
Notes: coaching hint:
this meeting re-affirms to the team that the TSP is now their process: they should make improvements to it, and make it work for them.

## Slide 6: The TSP Postmortem Procedure
The TSP postmortem procedure is guided by TSP Launch Postmortem Script (LAUPM).
The coach reviews the work to be performed in this meeting.
The planning manager reviews launch data with the team, and makes sure that responsibility has been assigned for recording and saving launch data and launch artifacts.
The coach leads the team in evaluating the launch process.
  what worked
  what did not work
  what needs to change (process improvement proposals)
  launch evaluation forms
Notes: <number>

## Slide 7: Launch Evaluation Forms
Launch evaluation forms are distributed to the
  team members
  TSP coach
The coach submits copies of the evaluation forms to the SEI with the team’s launch data using the SEI Partner Resource Center website
(https://partner-resources.sei.cmu.edu/).
Notes: <number>

## Slide 8: The Project Notebook
The contents of the project notebook are described in the TSP Project Notebook (NOTEBOOK).
The project notebook should hold a complete record of the project, including
  size summary and quality summary (SUMS and SUMQ)
  task and schedule plan and actual data
  component data
  quality documents
  risks and issues
  support plans
  launch artifacts
  weekly meeting reports and management reports
  project summary reports
The format of the project notebook is not important.
Notes: <number>

## Slide 9: Coaching Considerations for Postmortems
Encourage every team member to participate.
Make sure that any PIPs generated by the team are forwarded to the appropriate people for resolution.
Notes: Example of getting carried away: team member gets run over by a truck is a risk, the team identifies dozens of risks, the team does not identify any risks.

## Slide 10: Launch Prerequisites
One of the principal responsibilities of a coach is to ensure that prerequisites for conducting the launch have been satisfied.
The coach has to make sure that the team is prepared.
Consider
  project and team characteristics
  team member qualifications and PSP training
  management commitment and PSP training
  license agreements
The coach is also responsible for launch logistics.
Notes: <number>

## Slide 11: Team Characteristics
The team size can vary from 3 to 15 team members.
  The ideal team size is somewhere between the two limits.
  For larger teams, a TSP process extension (such as TSP for multi-teams or TSPm) may be more appropriate.
Team characteristics may also determine whether one of the following TSP process extensions is more appropriate.
  functional teams (TSPf)
  integrated project teams (TSPI)
  distributed teams (TSPd)
  TSP with an organizational or CMMI focus (TSP+)
  academic teams (TSPi)
  See Knowledge Area 6.2 of the TSP BoK for a complete description of the TSP Process Variations
Notes: <number>

## Slide 12: Project Characteristics
What phase is the project in?
  Requirements phase is the ideal time to start.
  Later phases are acceptable, but at some point, the value added may not be there. (For example, the project is already in test.)
What is the team composition?
  all software
  all non-software
  a mix
Notes: A project in test phase may be a TSP candidate if the organization has completed several other TSP projects and has project data from these projects in earlier phases.

## Slide 13: Team Member Qualifications
The coach must ensure that
  all software developers on the team have completed PSP training
  all non-software team members have completed the TSP Team Member Training
  all launch participants will be actively involved in the project
    observers are discouraged
    an exception to the “observers not allowed” rule may be made for a provisional coach’s mentor.
Notes: <number>

## Slide 14: Management Training and Commitment
Management commitment is critical to both the launch and the TSP effort. Management must be committed to
  actively participating in the launch
  tracking the work of the team
  setting process standards for the team to follow
The coach must ensure that all managers in the management chain above the team have participated in the appropriate PSP/TSP training.
Following the SEI TSP introduction strategy helps to ensure that team members and management are trained and committed.
Notes: <number>

## Slide 15: Launch Preparation Guidelines
The following documents help the team to prepare for a launch.
  Launch Preparation Checklist (PREPL & PREPW)
  Team Launch Preparation Guidelines
  Product Discussion Guidelines
  Senior Management Goals Discussion Guidelines
  Team Member Meeting 1 Discussion Guidelines
  Team Leader Meeting 1 Discussion Guidelines
  Senior Management Plan Review Guidelines
  Team Leader Plan Review Guidelines
  Team Member Plan Review Guidelines
These documents are located in the Launch Preparation package.
Notes: <number>

## Slide 16: Timeline for Launch Preparation -1
A month before the launch: Download the TSP coach package from the SEI Partner Resource Center (PRC) web site. The package will include
    templates for letters to the organization
    launch preparation checklists and guidelines
    launch participant preparation packages
    the TSP process and scripts
    TSP tool
    instructions and materials for preparing launch notebooks
A few weeks before the launch: Send the first mailing to the organization. With this mailing, include the initial letter, the launch preparation checklist, and the name, phone number, and e-mail address of the coach. A sample initial letter will be provided by the SEI.
Notes: <number>

## Slide 17: Timeline for Launch Preparation -2
Before the launch: If you have not received answers to your questions in the initial letter, call the organization to get the information. The initial letter asks the organization to provide answers to the following four quesions
    project name, a brief description of the project, and its status
    names of all team members and the team leader
    completion status of required training for all team members and the team leader
    name, phone number, and e-mail address of the launch coordinator
Notes: <number>

## Slide 18: Timeline for Launch Preparation -3
Before the launch
    Prepare enough launch notebooks so that there is one for each team member, the team leader, one or two coaches, plus one or two extra. Follow the notebook preparation instructions provided by the SEI.
    Send a second mailing to the organization so that the launch notebooks arrive at least a few days before the launch.
Notes: <number>

## Slide 19: Timeline for Launch Preparation -4
One week before the launch
    Make sure that the following people have received and reviewed their launch preparation materials.
      team members: Launch Notebook, Team Workshop Preparation Package
      team leader: Launch Notebook, Team Leader Workshop Preparation Package
      management: Senior Management Workshop Preparation Package
      marketing: Marketing Management Workshop Preparation Package
      other attendees: Other Attendee Workshop Preparation Package
Notes: <number>

## Slide 20: Considerations for Internal Coaches
TSP coaches who are internal to an organization can modify some of the steps outlined in the previous slides.
Instead of sending initial and second mailings, internal coaches meet with management, project leaders, and other interested parties to answer pre-launch questions
  get a launch coordinator assigned to the launch
  work with the launch coordinator to handle launch logistics
  work with launch coordinator to distribute materials
Internal coaches may consider holding meetings for launch participants prior to the launch to
  make sure that all participants have received launch materials
  give participants a chance to ask any questions
Notes: Four pre-launch questions on slide 17
<number>

## Slide 21: Coaching Considerations for Launch Preparation
You should know how to deal with one or more of the following problems.
  Team leader and/or team members are not trained.
  Team leader is not hired.
  Not all team members are present for all launch meetings.
  Nobody shows up for a launch.

## Slide 22: What is a Relaunch?
A relaunch
  is a launch with a project team that has already done a launch on this project
  builds upon the goals, commitments, and plans from previous launches on a given project
  is a normal, planned activity on a TSP project
Relaunch
Postmortem
Cycle 4
Relaunch
Cycle 3
Postmortem
Relaunch
Cycle 2
Postmortem
Launch
Cycle 1
Postmortem

## Slide 23: Process Differences from the Launch
In a relaunch, the team
  has already worked together
  knows what to do
  has already committed to management what they intend to do
The focus of a relaunch is on updating team plans, based on what they have accomplished and learned since the prior launch or relaunch.
A relaunch follows a similar process to a launch, but the management meetings are eliminated (meetings 1, 8, and 9). Meeting 1 is replaced with an overview of project status.
Notes: <number>

## Slide 24: Logistical Differences from the Launch
The relaunch is scheduled for less time than the launch.
Relaunch preparations follow script PREPR.
Script REL describes the overall relaunch process.
  Meeting 1 is run according to script REL1, which has significant changes from script LAU1.
  Meetings 8 and 9 are eliminated.
  Meetings 2 through 7 focus on planning in detail for the next cycle.
Notes: <number>

## Slide 25: Relaunch Preparation -1
Preparing for a relaunch is very similar to preparing for a launch.
The following documents help the team to prepare for a launch.
  Relaunch Preparation Checklist (PREPR)
  TSP Workshop Relaunch Preparation Package – Team Leader, Member, and other attendee
    Team Relaunch Preparation Guidelines
    Team Leader Status Report Guidelines
    TSP STATUS Specification
These documents can be found in the Relaunch Preparation package.
Notes: <number>

## Slide 26: Relaunch Preparation -2
The coach has to ensure that
  any new team members are trained and qualified
  any new management members have been trained
  a launch coordinator has been assigned
    meeting facilities and catering has been arranged
    computers (and other equipment) are ready
    relaunch preparation materials have been distributed to participants
  the team leader is ready to present
    project status
    performance against team goals
    any changes in management’s goals
Notes: <number>

## Slide 27: The Relaunch Process - Script REL
The relaunch process is guided by TSP Team Relaunch (Script REL).
This script is located in the Meeting 1 tab of your launch notebook.
Notes: <number>

## Slide 28: Relaunch Meeting 1
The coach reviews the work to be performed in this meeting.
New team members, if any, are introduced.
Project status against the plan is reviewed and discussed.
Performance against the goals is reviewed and discussed.
Changes in management’s goals for the project, if any, are presented.
Notes: <number>

## Slide 29: Other Relaunch Differences -1
Meetings 2 through 7 have identical scripts for both the launch and relaunch. However, the focus of the meetings is different.
Meeting 2
  Update and document the team’s goals.
  Allow rotation among the team roles if desired by the team.
Meeting 3
  Revisit the conceptual design.
  Adjust the development strategy, if necessary.
  Revisit the current team processes and create new processes as needed to address next-cycle work.
  Detail the next-cycle process plan and support plan.
Meeting 4
  Ensure that any changes to the overall plan are consistent with previous commitments.
  Detail the next-cycle plan.
Notes: <number>

## Slide 30: Other Relaunch Differences -2
Meeting 5: Update the quality plan.
Meeting 6
  Allocate next-cycle work to team members.
  Produce a balanced next-cycle plan for the team and each team member.
Meeting 7: Identify and evaluate any new risks.
Notes: <number>

## Slide 31: Coaching Considerations for Relaunches
Observe as much as possible. Make the team take ownership of the relaunch.
Make the team perform “due diligence.”
  Walk through each step of the script.
  Perform all required activities.
Ask questions as necessary.
  Was the postmortem from the previous cycle effective?
  Were the plans from the previous cycle detailed enough? Too detailed?
  How did the roles work in the previous cycle?
  Are risks being tracked effectively?
  What process changes have been made in response to PIPs?
Notes: <number>

## Slide 32: Messages to Remember
It is your responsibility as a coach to make sure that you and your team are prepared for the launch.
  Preparation for a launch involves planning and tracking.
  Preparation for a launch starts a couple of months (or more) ahead of the launch.
  Preparation guidelines and checklists facilitate the job of preparing for a launch.
Time allocated specifically for the launch postmortem allows a team to reach launch closure. It is
  a time for reflection on what worked and did not work
  an opportunity to improve the next time
The relaunch is a
  normal, planned activity for a TSP project
  streamlined version of the launch
Notes: <number>