## Slide 1
TSP Coach Training
Running the TSP Project –
Tracking and Reporting
Notes: Things to add:
  Need to bring in the PSP comparison,
  try contrasting the tsp and psp by looking at the process phases. Psp planning compares to tsp launch only it’s for a team, not an individual. Work phases are not so similar but the concepts relate. A tsp plan goes for just a phase, psp encompasses a module. Psp plans are not used to make commitments, tsp launches include management agreement on the plan. Continue with these comparisons.
  Both have scripts, forms,standards, measures etc
  Engineers plan and track work including quality.
  Engineers track time on task, defects, size, and schedule status
  Forms are similar plan summary – sump, task, schedule, etc
Overall, need to bring this into the lecture so it relate to their knowledge of psp.
Need more launch coach skills/characteristics.

## Slide 2: Outline: Running the Project
TSP roles: getting roles to be successful on a team
Tracking and reporting: collecting data, the weekly team meeting, reporting to management
Maintaining the baseline plan: keeping the team commitment, evaluating status, adjusting plans when necessary
Maintaining a quality focus: responsibilities for quality, TSP quality methods
Coaching the team: areas where the coach helps TSP discipline
Coaching the team leader: handling problems with a TSP team leader
Post-launch Coaching: post-launch coaching strategy and plan
Notes: <number>

## Slide 3: Lecture Objectives
At the end of this lecture, you will be able to
  assist a TSP team in tracking and reporting against their plan
  recognize common occurrences and problems with tracking and reporting, and apply hints for dealing with them
Notes: <number>

## Slide 4: Lecture Overview
TSP schedule tracking
Plan Management
The weekly team meeting
Reporting to management
Notes: <number>

## Slide 5: From the Launch
The team
  has completed a TSP launch and has planned their work
  has made a commitment and obtained management approval to proceed
  begins to carry out their plan
The team will not get the intended benefits of TSP if they do not follow the process, which includes collecting and tracking data.
Notes: <number>

## Slide 6: Schedule Tracking
Schedule tracking in TSP is based on
the team’s plan
task hour and task completion data
plan and earned value
Individual plans facilitate precise schedule tracking.
Team members are each responsible for
  gathering data on their work
  tracking status against their personal plans
  the quality of the work that they produce
  keeping the team informed of their progress
Individual team member data are consolidated each week so that the team can assess progress against goals.
Notes: <number>

## Slide 7: Sample – Cumulative EV

## Slide 8: Sample – Planned and Actual Hours

## Slide 9: After the Launch
From the launch, each team member has a
  Task plan
  Schedule plan
  EV plan
  Quality plan
It is the first working day after the launch.
What do they do?

## Slide 10: Day-to-Day Plan Management
Day-to-day
  Task management
  Time management
  Defect management
  Size management

## Slide 11: Task Management
  On most days, task management involves nothing more than
  opening the task plan to make sure that the tasks to be worked on that day are in the plan
  marking tasks complete as work is finished
  On some days, task management may also involve
  re-organizing tasks
  adding tasks
  deleting tasks
  merging tasks
  splitting tasks
  recognizing problems with tasks
  bucket tasks
  load balancing

## Slide 12: Completing Tasks
Marking tasks complete is important.
In the TSP, there is a Planned Value (PV) associated with each task.
The PV is the percentage that task contributes to total planned task hours.
  A 10 plan-hour task of a 100 plan-hour total has a PV of 10.0
A task earns it’s planned value when it is marked complete.
  There is no partial credit (0 Earned Value or 100% EV per task)
  The EV is always equal to the PV (regardless of the actual effort expended on the task)

## Slide 13: Organizing Tasks
Each morning, before individuals start work, they should open their task plan and
  Move completed tasks to the top of the task plan
  Move open tasks right below the completed tasks.
  Make sure the tasks they will be working on for the next two weeks (or the near term) are right below the open tasks.
If they don’t see a task for the work they will be doing today, they should add it to the plan (tell their team).
If they see a task in their plan that they know they will not be doing, they should delete it from their plan (tell their team).

## Slide 14: Recognizing Problems with Tasks -1
If tasks are structured badly, lots of tasks will be incomplete.
This may indicate too many parallel tasks.
How is this likely to affect the team’s status?
What should the team do about this?
B
start
done
A
C
D
B
start
done
A
C
D
instead
of

## Slide 15: Recognizing Problems with Tasks -2
Tasks are too large.
  Effort estimates for single tasks are much larger than an individual’s average weekly scheduled task hours.
  Actual time for completed single tasks is much larger than an individuals average weekly scheduled task hours.
How is this likely to affect the team’s status?
What should the team do about this?
B
start
done
A
B
start
done
A
C
D
instead
of

## Slide 16: Indicators of TASK Problems
The difference between Actual “Schedule hours this cycle to date” (24.8) and Actual “To-date hours for tasks completed” (2.1) shows the hours locked in unfinished tasks.
A general rule of thumb is that there should be no more than one week’s worth of open task hours (12.4).
What are some other indicators of task problems?
Notes: Estimates are incorrect.
Tasks are too big.
Tasks are too small.
Tasks are in the wrong order.
The correct tasks are not in the plan.
Etc,..

## Slide 17: Bucket Tasks
It is common to allocate resources for tasks team members know they will be doing that are scattered throughout the project, or will come up on an event-driven basis.
Examples include
  Role tasks
  Requirements elicitation meetings
  System test tasks
  Build and integration tasks
For these tasks, they may want to include a “bucket” of hours in your plan.
They “borrow” hours from the “bucket” as they execute some of the tasks.

## Slide 18: Load Balancing Tasks
As work progresses, some team members will get ahead of schedules as others fall behind.
To move tasks from team member 1 to team member 2
  Assign task to team member 2.
  Re-estimate the task using team member 2’s historical data if appropriate

## Slide 19: Why Do They Need Sufficient Schedule Hours?
If the task plan shows a total of 200 estimated hours for all tasks in the plan, then the schedule plan should show an availability of at least 200 task hours.
Enough available hours are needed to enable calculation of planned completion dates, PV, and EV.

## Slide 20: Impact of Task Modification -1
What impact does task addition/deletion/modification have on
  Baseline plan hours
  Plan hours
  Plan value of completed, open, and to-do tasks
  Earned value of completed, open, and to-do tasks
  To-Date plan value
  To-Date earned value
  Planning summary
  Quality summary
  Can you think of other impacts?
Notes: Project tab
Schedule tab
Week tab

## Slide 21: Impact of Task Modification -2
  Notice the total plan hours on the task plan and WEEK form increase/decrease to reflect the new/deleted tasks.
  The baseline hours on form WEEK reflect the original estimate.
  As Baseline hours diverge from Current hours, what should you do?
Notes: See section on determining project status.

## Slide 22: Time Management
Time management in the TSP involves two activities
  tracking time
  updating available hours

## Slide 23: Time Management – A Time Log
Notes: Log the time as soon as you remember.
Worst case, make a rule like “I won’t go to lunch without updating my time log” or “I won’t leave work without updating my time log”

## Slide 24: Time Management – Schedule Plan
Schedule plans change
  Vacation dates change
  People get sick
  People get pulled off this project to work on other projects
Schedule plans should only be changed for the future, never the past.
Schedule plans are updated as team members learn more about their actual schedules.

## Slide 25: Defect Management – A Defect Log

## Slide 26: Size Management
Actual size data is tracked using a TSP tool.
Actual size data should be entered by the owner of the work product in his or her TSP tool.

## Slide 27: The Weekly Team Meeting - 1
See Video
Notes: <number>

## Slide 28: The Weekly Team Meeting - 2
The weekly team meeting is the most important single activity that the team can perform to maintain energy and cohesion.
The weekly team meeting is the forum that the team uses for
  tracking progress against the plan
  tracking the status on the project's issues and risks
  communicating with each other
For the meeting, all individual plans are consolidated into a team plan to assess team progress.
The coach works with the team to prepare for and conduct the weekly team meeting.
Notes: <number>
Contrast this with a typical team meeting (I.e., non-TSP).

## Slide 29: Individual Responsibilities
Before the planning manager prepares the weekly summary of team data, each individual must ensure that their status is current.
  updated task, schedule, size, and defect data
For the meeting, each individual should prepare
  status against their individual role manager responsibilities
  status against goals assigned to them
  status or updates against risks and issues
  updated task and schedule plans
  list of tasks planned for the next week
Notes: <number>

## Slide 30: Planning Manager Responsibilities
The planning manager ensures that all individuals have updated their plans.
  If they haven’t, the planning manager should ask them to do so.
  If they habitually don’t update their plans, they must answer to the team in the weekly meeting.
  In a short time, each person should learn to keep their plans current without intervention.
The planning manager prepares the team summary reports for the meeting.
  graph of earned value (plan versus actual)
  graph of actual versus planned hours
  WEEK form, showing tasks completed and planned tasks for the next week
Notes: <number>

## Slide 31: WEEK Script
Refer to the script WEEK.
  The team leader provides a summary of any new developments or team issues.
  Each role manager reports on their assigned role responsibilities.
  Status is reported against team goals, if status is due.
  Risks are reviewed as required for that particular week.
  Each individual reviews progress and status.
  The planning manager summarizes team progress and status.
  Each individual reports on tasks planned for the next week, including any dependencies.
  The team leader reviews expected issues or actions for dealing with the dependencies.
  The team leader wraps up the meeting.
Notes: <number>

## Slide 32: Coaching During the Meeting
The team leader
  leads the weekly meeting
  ensures that all individuals are providing status and are actively involved in the meeting
The team leader should advise the team on specifically what will be reported to management.
  helps to motivate the team
  triggers issues that need to be raised to management
The meeting is intended to promote communication, but should still be held to the times on the agenda.
Any issues that need to be discussed in detail should be discussed in a separately-scheduled meeting.
Notes: <number>
On this slide, discuss team leader behavioral shift.

## Slide 33: Reporting to Management
Most TSP projects start with strong management support.
  The launch process produced a plan, committed the team, and gained acceptance by management.
  Management expects the team to work to their plan and to meet their commitments.
If management does not hear from the team, they get nervous.
  They suspect problems.
  They may revert to micromanagement.
Keep managers informed of the project's status.
  Report team data from the weekly meetings.
  Adjust the level of detail so that your management is comfortable and not over- or underwhelmed.
  Answer the need or intent, not the question.
Notes: <number>

## Slide 34: Weekly Reporting to Management
As a starting point, the team should report the following to management on a weekly basis.
  earned value for the project
  summary of the WEEK form
  summary of the risks and issues
  minutes from the weekly meeting
Based on management’s reaction, the team can modify the format and content of the report accordingly.
Notes: <number>

## Slide 35: Periodic Reporting to Management
Periodically, projects may meet with management and/or the customer.
  The STATUS script is used to guide the meeting.
  The STATUS specification is used to help prepare accurate, complete, concise, and informative management status reports.
Notes: <number>

## Slide 36: Coaching Considerations
The coach can work with the team to look at data
  on a daily basis
  on a weekly basis
  at the completion of tasks
  at the completion of phases
  at the completion of cycles
  at the completion of parts or assemblies
At each of these points, data are available to help individuals understand where they are and to indicate whether commitments can still be made.
Notes: <number>

## Slide 37: Coaching: On-task Time
If individuals are not getting the number of hours planned, they should consider these questions.
  What are the things that are interrupting on-task time?
  How can these interruptions be reduced or eliminated?
  Should the planned hours be changed, thus suggesting the need for reassessing the committed dates?
If individuals are getting more hours than planned, they should consider these questions.
  Can they actually increase their planned hours in the future?
  Can they accelerate their work?
  Can they take on more work and still keep their commitments?
Over time, the detailed plans will be more comprehensive, and fewer tasks will be missed.
Notes: <number>
As weeks pass, individuals can look at their actual versus planned hours on the SCHED form.
As the team gains experience using the TSP process and detailed planning, they will get better at it.
Consequently, on-task time will improve over time because interruption time and unplanned task time will go down.
Other ways to improve on-task time include
  comprehensively planning for every task
  dedicating periods of time each week to working on tasks
  monitoring actual on-task time each week
  recognizing and assess unplanned time and interruptions
  trying to account for unplanned time and interruptions in future plans

## Slide 38: Coaching: Quality Data
Defects found provide clues for finding and preventing similar defects in the future.
  When were the defects found?
  When were they injected?
  How could they have been found earlier?
  How could they be prevented in the future?
After testing phases, the quality/process manager should lead a review of defects with the entire team.
  Assign someone to look for and fix remaining defects.
  Update the quality plan (predicted defects based on actual counts).
  Update the process with needed changes.
Notes: <number>

## Slide 39: Messages to Remember
The team’s success relies on accurate tracking, collecting, and reporting of individual data.
Individuals have data that they can periodically look at to
  assess their progress
  make adjustments in their detailed plans, when necessary
If the plan doesn’t match the work, change the plan.
The weekly team meeting is an effective forum in which the team can
  review consolidated data
  assess progress against the team goals
  make adjustments to team plans, if needed
Notes: <number>