## Slide 1
TSP Coach Training
Running the TSP Project –
Maintaining the Baseline Plan
Notes: Things to add:
  Need to bring in the PSP comparison,
  try contrasting the tsp and psp by looking at the process phases. Psp planning compares to tsp launch only it’s for a team, not an individual. Work phases are not so similar but the concepts relate. A tsp plan goes for just a phase, psp encompasses a module. Psp plans are not used to make commitments, tsp launches include management agreement on the plan. Continue with these comparisons.
  Both have scripts, forms,standards, measures etc
  Engineers plan and track work including quality.
  Engineers track time on task, defects, size, and schedule status
  Forms are similar plan summary – sump, task, schedule, etc
Overall, need to bring this into the lecture so it relate to their knowledge of psp.
Need more launch coach skills/characteristics.

## Slide 2: Outline: Running the Project
TSP roles: getting roles to be successful on a team
Tracking and reporting: collecting data, the weekly team meeting, reporting to management
Maintaining the baseline plan: keeping the team commitment, evaluating status, adjusting plans when necessary
Maintaining a quality focus: responsibilities for quality, TSP quality methods
Coaching the team: areas where the coach helps TSP discipline
Coaching the team leader: handling problems with a TSP team leader
Post-launch Coaching: post-launch coaching strategy and plan
Notes: <number>

## Slide 3: Lecture Objectives
At the end of this lecture, you will be able to
  assist a TSP team in maintaining their baseline plan
  recognize common occurrences and problems with maintaining a baseline plan and apply hints for handling them
Notes: <number>

## Slide 4: Lecture Overview
Dynamic workload balancing
Interpreting team plan data
Updating the overall plan
Notes: <number>

## Slide 5: Plan Dynamics
If you can’t plan accurately, plan often.
- Watts Humphrey
Detailed plans are accurate only for brief periods of time.
  As team members work, they learn more about the job.
  The work among individuals becomes unbalanced.
  Organizations and teams are dynamic.
As plans become less accurate, they are less useful in guiding the work.
Teams need detailed plans to make realistic commitments and to coordinate and track their work.
Consequently, teams must dynamically maintain their plans.
Notes: <number>
  As data are collected, individuals see how long tasks actually take.
  As the product evolves, individuals learn more about how they need to develop it.
  Organizational structures change.
  Team assignments and staffing profiles change.
  Team dynamics evolve, including relationships and behaviors.
  Engineers may finish tasks ahead of or behind the plan.
  Tasks may be done out of sequence.
  There will be overlooked tasks.
  There will be occasional trends in poor estimates.

## Slide 6: Why do Plans Change?
Plans need to be continuously updated to reflect reality as
  The project is better understood
  Requirements change
  Planning parameters change (effort hours, productivity)
  The process is better understood
  New team members join the team, or team members leave the team
  Risks become issues
Can you think of other reasons that cause plans to change?

## Slide 7: Better Understanding of a Project
As a team better understand a project, they may find
  It is smaller than anticipated
  Larger than anticipated
  They missed tasks that are necessary to complete the project
  There is a skill set they need before they can complete the project
  The project requires a commercial off the shelf piece of software
How should they handle each of these situations?

## Slide 8: Requirements Change
Stakeholders may request changes such as
  A new feature
  An earlier date
  Changes in priorities
  Different order of completion
  An unplanned demo or one-off release
It is important to handle each of these in a rational manner
  Ensure they understand the request
  Respond with the impact and the choices the stakeholder has
If those impacts are accepted, they should update their plan to reflect the current reality.

## Slide 9: Planning Parameters Change
When a team makes its initial plan, they used some planning parameters
  effort distribution amongst phases
  productivity
  defect injection and removal rates
  task hour availability
If the team or individuals discover these parameters were incorrect, it is important to re-plan.

## Slide 10: Processes Change
As teams starts doing the work, they may find that the processes they are using need to change.
Process changes may be needed if
  The process steps are in the wrong order
  The process steps are not granular enough
  The process steps are too granular
  The process needs additional steps
  The process needs fewer steps
  The process is not producing high quality products
  Can you think of other reasons process changes may be needed?

## Slide 11: Team Composition Changes
As projects execute
  team members are added or removed from the team
  team members may be assigned to other work temporarily
  team member resource allocation to this project may change
How should these changes be reflected in a team’s plan?
Notes: If a team member is replaced, the new team member gets the incomplete tasks from the old team member’s plan.
  The new team member re-estimates tasks based on personal historical data
  Consider adding a buffer for a learning period
  New team member enters their own schedule plan
Consider impact on existing team roles.
When a team member is assigned to other work temporarily, or their resource allocation changes, update that team member’s schedule plan. If possible, load balance.

## Slide 12: Communicating Commitment Changes
Whenever changes are made to the plan, the team must make sure they
  review plan changes
  verify they understand why the changes were made
  review impact to commitments
If the change to the plan impacts commitments
  consider alternatives
  offer choices and recommendations to stakeholders

## Slide 13: Dynamic Workload Balancing
There is always fluctuation. To keep from getting badly imbalanced, the team rebalances the workload as needed.
Do the following on a weekly basis.
  Examine each individual’s progress and projected completion of tasks.
  Determine who is ahead and behind.
  Balance the work where necessary.
If the basic plan was a good one, this is likely to keep the team on the original plan.
Notes: <number>
Plan updates makes everybody nervous.
  Managers anticipate schedule slippage.
  Team leaders question their ability to make commitments.
  Team members start to doubt their effectiveness.
The team must manage the plan dynamically and make every effort to hold to their commitments.
  If competently made, the original plan should have been based on historical size and task-hour data.
  Without external changes, the overall plan should be accurate.
  Adjustments may be needed for normal estimating fluctuations at the detailed level.
  Dynamic planning is intended to preserve and improve the team’s schedule.
External changes may result in overall plan changes as well.

## Slide 14: Rebalancing the Workload
At week 8
Notes: <number>
Individuals can make updates to their plans without affecting other team member plans or the overall team plan.
When a team member must make changes to their plan and it affects other team member plans, the situation is an imbalance.
The team leader must work with the team to dynamically balance the work.
  Each individual needs to look at their actual data and refine their detailed plans where necessary.
  The planning manager produces the consolidated team plan, based on revised detailed plans.
  The team follows the dynamic load-balancing procedure described in launch meeting 6.
Cover how do you add an assembly? task?

## Slide 15: Interpreting Team Data
Team progress can adequately be described using two indicators: task hours and earned value.
  Trends in actual versus planned task hours show whether current trends in expended time are above or below the plan.
  Trends in earned versus planned value show whether current trends in earned value are above or below the plan.
Based on trends in hours and earned value, the team can determine whether
  the project is on track
  the project will finish as planned, assuming that the current pace is maintained
  causes of plan deviation can be identified and adjustments to the project can be made to address these causes
Notes: <number>

## Slide 16: Interpreting Team Data Example -1
Notes: <number>

## Slide 17: Interpreting Team Data Example -2
Notes: <number>

## Slide 18: Possible Causes of Plan Deviation
The estimates used to produce the plan may be inaccurate.
  not based on historical data
  used poor size estimate and/or productivity rates
Team members may not be getting the task time as planned.
  frequent interruptions
  unplanned work
The team may not have adequate or appropriate staff.
Team members may be doing superficial work.
Individuals may be doing the work wrong because they misunderstand the
  work
  process
The team may be struggling with teamwork issues.
Notes: <number>
  Make sure that the team is not “managing the numbers” and making the data say what it is supposed to say.
  Make sure that tasks are being completed in sequence and dependencies are not being ignored.
  Make sure that the team is adhering to their quality plan.

## Slide 19: Making the Schedule
When earned value is on or above planned value, the team is making their schedule.
As long as the actual hours expended are close to the plan, the team is right on track.
Things to consider
  If actual hours are not as planned, the team has an estimating problem that they need to address before they make another plan.
  If actual hours are as planned or lower, the team may be doing a superficial job on important quality activities.
Notes: <number>

## Slide 20: Falling Behind
When earned value is below planned value, the team is at risk of not making their schedule.
  The team seems to have underestimated the job.
  The team may not be getting their planned task hours.
Things to consider
  Figure out how to get back on schedule.
    Work with the team to do a major plan reassessment.
    Don’t blow the whistle prematurely.
    Review the situation with management as soon as you have more details.
  Compare earned value status with actual hour status.
    If the team was fully staffed and met the planned task hours, would earned value be above or below plan?
    Use the relative comparison between earned value and actual hours as a way to explain plan deviations and secure support to get back on track.
  Recognize that early in a project, there can be wide fluctuations in actual versus planned measures.
Notes: <number>

## Slide 21: When Things Look Too Great
Work with the team to make sure that the situation is real and not just a temporary variation.
Some suggestions for looking deeper into the status
  Make sure that the team is not “managing the numbers” and making the data say what it is supposed to say.
  Make sure that tasks are being completed in sequence and dependencies are not being ignored.
  Make sure that the team is adhering to their quality plan.
Approach management with the status.
  Do they want the team to accelerate the schedule?
  Do they want to add functionality?
  Do they want to reassign staff to other projects?
Notes: <number>

## Slide 22: Updating the Overall Plan
After dynamic changes are made to individual plans, the team determines if the new consolidated plan is consistent with the original baseline plan.
  Are tasks in the current phase still consistent?
  Are tasks for future phases consistent?
  Have the individual estimates affected the team’s commitments or scheduled dates?
If the team is not reasonably close to maintaining the baseline plan, the team needs to
  interpret their data, including actual versus planned hours and earned versus planned value
  make adjustments to their work and their plans
  possibly involve management and renegotiate commitments
  possibly relaunch
Notes: <number>
The decision to conduct a relaunch should be based on team needs.
  The workload is imbalanced.
  The plan is not guiding their work.
  New members are added to the team.
  There are external changes.
  There is a significant and unrecoverable deviation from the original plan.
Updating the plan takes time, and plan changes generally make it harder to track progress. Therefore
  update individual detailed plans first
  if needed, update the overall plan as a last resort
  conduct relaunches only if necessary

## Slide 23: Messages to Remember
Detailed plans are accurate only for brief periods of time. Therefore, it is essential to periodically rebalance plans.
Continuous planning helps
  team members to be more efficient
  teams to better manage their workload
Analysis of data gives insight into team progress and suggests potential overall plan corrections. Look at
  earned versus planned value
  actual versus planned task hours
Notes: <number>