## Slide 1
TSP Coach Training
Coaching the Team Leader
Notes: Things to add:
  Need to bring in the PSP comparison,
  try contrasting the tsp and psp by looking at the process phases. Psp planning compares to tsp launch only it’s for a team, not an individual. Work phases are not so similar but the concepts relate. A tsp plan goes for just a phase, psp encompasses a module. Psp plans are not used to make commitments, tsp launches include management agreement on the plan. Continue with these comparisons.
  Both have scripts, forms,standards, measures etc
  Engineers plan and track work including quality.
  Engineers track time on task, defects, size, and schedule status
  Forms are similar plan summary – sump, task, schedule, etc
Overall, need to bring this into the lecture so it relate to their knowledge of psp.
Need more launch coach skills/characteristics.

## Slide 2: Outline: Running the Project
TSP roles: getting roles to be successful on a team
Tracking and reporting: collecting data, the weekly team meeting, reporting to management
Maintaining the baseline plan: keeping the team commitment, evaluating status, adjusting plans when necessary
Maintaining a quality focus: responsibilities for quality, TSP quality methods
Coaching the team: areas where the coach helps TSP discipline
Coaching the team leader: handling problems with a TSP team leader
Post-launch Coaching: post-launch coaching strategy and plan
Notes: <number>

## Slide 3: Lecture Objectives
At the end of this lecture, you will
  know the key responsibilities of the team leader
  understand how to handle common problems with the team leader
  understand how team leaders should deal with common management, team, and individual problems
Notes: <number>

## Slide 4: Lecture Overview
Team leader responsibilities
Problems with the team leader
Coaching the team leader
Notes: <number>

## Slide 5: Context
Some of the areas that we discuss in this module will be covered in depth in a separate course for team leaders.
They are included here because you are likely to need to coach new team leaders in these areas.
Notes: <number>

## Slide 6: The Team Leader’s Responsibilities -1
The TSP team leader role differs from the traditional project leader role.
  Project responsibilities are handled by the team role manager.
  The team leader focuses on leading and coaching the team.
The team leader ensures that the team
  has aggressive goals and is working hard to meet them
  has a defined process and is following it
  is gathering and using TSP data
  establishes and maintains high standards
  maintains its focus on product quality
Notes: <number>

## Slide 7: The Team Leader’s Responsibilities -2
The team leader supports the team by
  obtaining resources
  negotiating for needed support
  resolving customer issues
  supporting and representing the team with higher management
The team leader also
  represents management to the team
  handles personnel issues
Notes: These are the traditional roles for a first line manager.
The first group is the team leader support to the team.
The second group is the “management “ responsibilities.
Between this and the previous slide, the point to make is that the team leader’s role has changed, there is a culture shift necessary. Before the team leader took the responsibility for the project, planning, tracking, managing all aspects. Now the team leader has relinquished much of the project responsibility to the team, and the team leader now handles the previous responsibilities, plus retains these.

## Slide 8: Problems with the Team Leader -1
There are many possible problems that you could encounter with the team leader; we can’t cover them all.
Two general situations
  The team leader doesn’t follow the process.
  The team leader doesn’t require the team to follow the process.
What are some examples of these?
Notes: Team leader
  doesn’t attend training, doesn’t have time for it
  Doesn’t make engineers attend the training
  Doesn’t hold weekly meeting
  Makes commitments for the team
  Changes the team plan
  Does nothing about a team member that isn’t following the process

## Slide 9: Problems with the Team Leader -2
Root causes of team leader problems
  The team leader doesn’t understand what to do, but believes in using the TSP.
    leader needs guidance and support
    situation can be handled with coaching or training
  The team leader doesn’t believe in using the TSP, or believes that he/she knows better.
    situation is usually serious
    generally disables a team if the problem is not fixed
    is likely to require support from management
Notes: <number>

## Slide 10: Problems with the Team Leader -3
This is the general procedure for handling a problem with the team leader.
  Find out why the team leader is not following the process or requiring the team to follow the process.
  Assume that the team leader wants to do the job properly and is confused or needs guidance. Provide whatever help you can.
  If the team leader does not respond to guidance or refuses it, discuss the situation with senior management. The objective is to enlist their help in changing the team leader’s attitude, not to get the team leader reassigned, disciplined, or dismissed.
  If it becomes clear the team leader can’t be turned around, urge management to promptly appoint a new team leader.
Notes: Ask questions here.
How should you approach Management?
What should you tell the team lead prior to going to management?
Can the team succeed on this path?
Make this slide animated, one item at a time.
On point 4, make sure to point out you’re not suggesting to team leader be fired.

## Slide 11: Example: The Hard-Head
Marsha is the team leader for a new TSP project. She
  has managed a number of projects
  had PSP/TSP manager’s training
  does not believe that the emphasis on process discipline is necessary
  feels that she can continue with her traditional management style on this project, even though management has told her to use TSP
Discussion: What should the TSP coach do?
Notes: Here is an example of the previous scenario.
<number>

## Slide 12: The Hard-Head: What Happened
The coach
  knew that Marsha’s team was not gathering their data or following the process
  talked to Marsha, but could not convince her to do anything about it
  talked to senior management, but they would not tell Marsha to motivate her team to use the process, nor would they replace her
When Marsha’s team finished the project, the coach looked at the results. She
  found that Marsha’s team had taken almost four months longer to complete testing than any other TSP project
  showed senior management the public data and explained how much Marsha’s failure to demand process discipline had cost the company
Management removed Marsha from her job.
Notes: This is based on an actual story.
Talk about coach following steps 1 & 2.
Marsha’s failure to follow the process cost her her job. As a coach, a duty to the team lead is to help her succeed. The ultimate failure here was management, yet Marsha was the one punished.
Animate the slide?

## Slide 13: Coaching the Team Leader
The rest of this presentation covers some of the situations that the team leader may face and suggests how the team leader can deal with them.
  “impossible” projects
  team issues
  individual issues
We cover these here to help you in guiding and coaching the team leader.
Notes: Work on context for these, give guidance on TSP
Separate engineering from management problems.

## Slide 14: “Impossible” Projects
Some projects seem to be cursed; nothing seems to work, and there is a disproportionate amount of “bad luck.”
  The previous manager was fired.
  The best employees are quitting.
  The original designers have left.
One thing these “impossible” projects have in common is that no one on the team believes that the job can be done on the required schedule.
Three categories of “impossible” projects are
  an impossibly short schedule
  an unreasonable customer
  a demanding executive
Notes: How can a TSP project wind up this way?
Dysfunctional team leader, not following the process.
External changes.
This really is likely to be the case when a non-TSP project is in trouble, and a TSP trained/experienced TL is asked to take over the project.

## Slide 15: An Impossibly Short Schedule
A project has an impossibly short schedule when no realistic plan can be built. Since teams can’t make a realistic plan, they often do illogical things and end up taking longer than they would have done with a rational plan and schedule.
The way to handle such projects is to
  thoroughly assess where the project is
  make a comprehensive team plan
  review the plan with management and the customer
  agree on how to proceed
The project has a sound basis for proceeding once it has a comprehensive plan that
  the team leader and the team agree is feasible
  management and the customer have reviewed and accepted
Notes: Discuss Steve McConnell’s example of infeasible schedule region.
Use WinWord example from page 207 of Rapid Development.
The surprising fact is that the more important the project and the worse trouble it is in, the more likely it is that the customer and management will agree to a rational plan.

## Slide 16: An Unreasonable Customer
The customer is likely to be unhappy when
  a project is in trouble
  the product can’t be delivered on the original schedule and for the agreed-upon costs
Most customers are surprisingly reasonable, even under the most adverse conditions, if they
  understand the problems that the project faces
  have the flexibility to change requirements
When they don’t have this flexibility, expect them to be very difficult to negotiate with.
Notes: <number>

## Slide 17: Handling the Unreasonable Customer
There are no simple rules for handling unreasonable customers. The best guideline is for the team leader and team to act responsibly.
If the customer requests any change that impacts the project’s cost or schedule, the team leader should get the issue on the table immediately.
If the customer insists that the change is within the original contract, the team leader should make sure that
  management agrees and is willing to cover the added costs
  the customer will accept the schedule delay
If either party does not agree, the team leader must get the issue settled before accepting the change.
If the team leader doesn’t do this, the
  situation will only get worse
  project is likely to end up being canceled
Notes: Two problems here. TSP helps with the engineering problem, I.e., the discipline to evaluate every change and make the impact known.
Then it is up to management to decide how to handle this. Obviously the best situation is for management to stand up to the customer.

## Slide 18: A Demanding Executive
Executives are often demanding and impose seemingly impossible challenges.
  These demands are often ploys to get their people to try harder.
  Few people are truly unreasonable, particularly executives.
  The problem for the team leader is to separate the bluffs and ploys from the truly unreasonable demands.
Notes: <number>

## Slide 19: Handling the Demanding Executive
The approach that usually works is for the team to
  assume that the executive is truly interested in the best results that the team can produce
  produce a plan that does the best job that the team is capable of doing
To protect the team in case the executive is truly impossible, the team should construct another plan that meets the executive’s schedule, even if this plan
  takes another 25 employees
  triples the team budget
  defers all non-essential functions
While this is likely to protect the team leader from being fired, there are no guarantees.
Notes: TSP helps the team leader separate the ploys from the unreasonable demands.

## Slide 20: Summary on “Impossible” Projects
The safest strategy for handling what seems like an “impossible” project is for the team leader to have the team concentrate on doing the best job that they know how.
  Have the team follow the TSP launch process.
  Have the team define how to do the work in a technically sound way.
  Make sure that the entire team has been involved in producing the plan.
  Make sure that the entire team is convinced that this is the best plan that it can make.
The team should meet with management and the customer to present the plan.
When management and the customer realize that the team has done its homework, they usually end up accepting the team’s plan.
Notes: <number>

## Slide 21: Team Issues
The team leader has these responsibilities to the team.
  set the pace for the team
  maintain the team
  build trust with the team
Notes: <number>

## Slide 22: Set the Pace
Lee Iacocca said, “The speed of the boss is the speed of the team.”
If the team leader is not in much of a hurry, the team will relax and coast.
The critical issue here is the team leader’s behavior.
  Does the team leader really believe the team’s goals?
  Is the team leader working aggressively to meet them?
  Is the team leader challenging the team member to do their best?
The team leader’s job is to motivate the team members to do the best work that they are capable of doing.
Notes: <number>

## Slide 23: Maintain the Team
The launch should have resulted in a cohesive team that is ready to jell.
One of the key responsibilities of the team leader after the launch is to maintain the team.
Some key considerations for maintaining the team are
  holding frequent team meetings
  treating the team as a team
  sharing a common workspace
Notes: <number>

## Slide 24: Build Trust with the Team
One way for the team leader to build trust with the team is to show that he/she trusts the team by asking for their help.
Team leaders can ask the team for help in maintaining their own process discipline. They can
  ask the team to remind them when they do not follow the defined process
  ask the quality and process managers to monitor the quality of their personal data
When team leaders share their data with the team, the team members are more likely to share their data with the team leader.
Notes: <number>

## Slide 25: Individual Issues
Some individual issues that the team leader should deal with are
  evaluating team members
  handling difficult team members
Notes: <number>

## Slide 26: Measuring and Evaluating People
The principal objective in evaluating people is to help them improve.
Evaluating people is not difficult, particularly when team leaders know as much about a team member’s performance as they will with the TSP.
But, team leaders must think carefully about how they will use what they know.
The team leader should
  not use measurement values to evaluate people
  consider process and process discipline. Ask if the team member is
    using sound methods
    gathering and reporting his or her data
  tell the team members how they will be evaluated
    what is being looked for
    where they could show improvement
    not mention any measurement values
Notes:   If the engineers think their evaluations will be based on some numerical measures and that the team leader has some specific targets for those measures, they will do their utmost to meet those targets, regardless of how their actions may impact any other objectives.
  Use story of trans-Siberian railroad, people measured on the number of cars crossing the continent. So they had many trains of empty cars crossing the continent. They changed the measure to require the cars be loaded and the worker filled the cars with anything available, including water.

## Slide 27: Handling Difficult Team Members
As a manager, the team leader’s job is to get the best possible work from all of his or her people.
Some people are easy to manage and some are difficult. One of the most challenging tasks for a manager is to handle the difficult people.
The team leader should do these things.
  Take the time to listen to and understand these people and try to establish personal rapport. Many times, this solves the problem.
  If problems continue, discuss the situation with his or her manager and agree in advance on precisely how to handle it.
  Try to motivate the employee to do good work, even if it takes time.
  When nothing else works, take a hard line; it frequently works. (Be prepared to follow through.)
Whatever team leaders decide to do, they should first make sure that their manager agrees with what they plan to do.
Notes: It’s important to take care of a difficult person because of the effect they have on the team. The team leader either needs to change their attitude so that they become productive team members or have them removed from the team so they don’t disrupt the team.

## Slide 28: Example: Would Not Join the Team -1
Janet’s team was having their first TSP launch. Janet
  was a long-time employee
  resented having a manager young enough to be her daughter
  for years had worked a late schedule
  refused to come to work in time for the first launch meeting
  refused to take a team role
  claimed she knew how to develop software and didn’t need the TSP process
Linda, the team leader, felt that this behavior would
  destroy the team as a cohesive unit
  undermine her authority as team leader
When discussing this issue, Linda’s manager suggested that she tell Janet that if she didn’t participate as a full member of this team, she would have to get another job. They would give her 30 day’s severance pay, plus any accrued vacation.
Notes: <number>

## Slide 29: Example: Would Not Join the Team -2
When Linda explained management’s position to Janet, she was shocked. Janet had worked for the company for many years, was nearing retirement, and had never had a manager talk to her like this.
The next day, she was at the team meeting on time, and she agreed to take the test manager role.
Notes: <number>

## Slide 30: Messages to Remember
The team leader is key to the team’s performance. The team leader must
  believe that the TSP is the right way to work
  know how to lead and coach
Problems with the team leader can be serious; if they are not addressed, the team is unlikely to really follow the TSP process.
The coach must be prepared to
  deal with problems with the team leader
  guide and coach the team leader with project, team, and individual issues
Notes: <number>