## Slide 1
TSP Coach Training
The Launch Process - Meeting 3
Notes: <number>

## Slide 2: Lecture Objectives
At the end of this module, you will be able to
  assist a TSP team in conducting launch meeting 3 and developing a conceptual design and team strategy
  coach the individual role managers in conducting meeting 3
  use the forms that support meeting 3
  recognize common occurrences and problems with meeting 3 and apply hints for handling them
Notes: <number>

## Slide 3: Lecture Overview
The TSP planning process
Purpose of meeting 3
Meeting 3 exercise
Coaching considerations
Reference material
Notes: <number>

## Slide 4: The TSP Planning Process
The logic for the TSP planning approach is much like that used in system design.
  Devise the structure for the total job.
  Break the job down into parts, phases, or cycles.
  Focus in detail on each part, phase, or cycle.
The TSP team launch script LAU outlines the process.
  develop a list of products to be built
  produce the project strategy and process
  account for process and support work
  develop the overall plan
  produce the quality component of the plan
  develop individual detailed plans
  consolidate team plans and balance the workload
The launch provides
  an overall plan for the job
  detailed plans to guide the team members’ work in the next phase or cycle
Notes: <number>

## Slide 5: TSP Launch Planning Flow
Project strategy
Process, support
List of products
Development strategy
Conceptual
design
Overall plan
Available time
Estimate resources
Define tasks
Estimate size
Quality plan
Quality goals
Defects injected
Defects removed
Balanced
plan
Allocate tasks
Individual plans
Balance workload
Notes: <number>
Look to terminology wall chart

## Slide 6: The Launch Process Meetings
1. Establish
product and
business
goals
2. Assign roles
and define
team goals
4. Build overall
and
near-term
plans
5. Develop
the quality
plan
6. Build individual
and
consolidated
plans
7. Conduct
risk
assessment
8. Prepare
management
briefing and
launch report
Launch
postmortem
9. Hold
management
review
3. Produce
development
strategy
and process
A TSP team coach guides the team through a defined process to develop its plan and to negotiate that plan with management.
Notes: <number>

## Slide 7: Meeting 3 Exercise
Exercise purpose.
  understand how launch meeting 3 is conducted
  be able to define an overall and next-phase or cycle process
  recognize issues that might arise and understand how to deal with them
Directions (see meeting 3 exercise workbook).
  assemble into your launch team groups
  conduct launch meeting 3 with these changes (Optional)
    conceptual design was done before the launch
    development strategy was done before launch
  class discussion of how process worked and teams’ development process
After the exercise, we will conclude the module with a discussion of coaching considerations from the lecture slides.
Notes: <number>

## Slide 8: Conceptual Design Considerations
Don’t confuse the conceptual design with the actual design.
The level of detail should be appropriate for the project phase or cycle.
The purpose of the conceptual design is to estimate the work.
If the team is having trouble developing a conceptual design,
the team should consider asking for outside confirmation of assumptions.
Consider having the team draft notional conceptual designs prior to the launch.
Size is not that important. It should only be used when size is easy to correlate with effort. When using size, it is often helpful to measure the size of existing products to make the team more comfortable with their estimates.
Notes: <number>

## Slide 9: Coaching Considerations for Process Definition
Allow the team to deviate from the TSP scripts, as long as their process
  maps back to the TSP for data collection
  enables the team to guide their work and track their data
Don’t drive the team to a level of detail that is beyond their comfort level.
Emphasize the quality process and ensure that the team is committed to doing the job right.
Ensure that everyone on the team understands and agrees with the process.
Don’t confuse process with products. You apply a process to a product.
Only define processes that you need to use to build the near-term plan.
Notes: <number>

## Slide 10: Overall Coaching Considerations
You want everyone to participate in creating the conceptual design and defining the team’s process. It
  fosters creativity
  ensures that everyone buys into the plan from the start
Allow the meeting to be very “open.”
The team leader, coach, or any one individual must not dominate this meeting.
Notes: <number>

## Slide 11: Messages to Remember
In meeting 3, the team accomplishes three important prerequisites to building the team plan.
  identifies all of the “work” the team needs to do
  identifies the “strategy” the team will use to develop the product
    Integration strategy
    Test strategy
    Development strategy
  identifies or defines the “processes” the team will follow to do the work
Project strategy
Process, support
List of products
Development strategy
Conceptual
design

## Slide 12: Reference Material
Overview of meeting 3
Conceptual design
Development strategy
Products to be produced
Development process
Process and support work
Notes: <number>

## Slide 13: Meeting 3 Artifacts
The following artifacts are produced in meeting 3.
  a conceptual picture of what the product might look like
  a STRAT form that includes
    how the software will be developed in cycles
    size and time estimates for each component or feature
  a SUMS form that includes a list of products to be produced
  a flip-chart version of the team development process
    overall process for the project
    detailed process for the next phase or cycle
  an INV form that includes additional products or work to be produced by the team (work not captured on SUMS)
Notes: <number>

## Slide 14: Product Conceptual Design
Refer to step 3 of LAU3.
Conceptual designs are needed as the starting point for planning.
  The team may not know all of the requirements.
  Requirements typically describe what the customer wants, not what will be built.
  Since there are many ways to build a product, the team must agree on a conceptual design for planning.
The conceptual design is used to produce size and subsequent effort estimates for the products to be produced.
Notes: <number>

## Slide 15: Conceptual Design Technique
In the meeting, the conceptual design is created on a flip chart or whiteboard using bubble diagrams, block diagrams, flow charts, or lists.
The team estimates the size of each component and/or feature in the conceptual design.
Later, the conceptual design (including the size estimates) will be entered into SUMS.
Plan to spend two to three hours for average projects, or a full day if the TSP team is very large.
The team may have produced a conceptual design as part of the prelaunch preparation.
Notes: <number>
To make a conceptual design, ask these questions.
  Based on what is known now, how can this product be built?
  What are the principal components needed?
  What functions must these components provide?
  How big are these components likely to be?

## Slide 16: Example: Security System
Alarm
Control panel
Process messages and status
Generate alarm
Execute self test
Maintain configuration
Monitor sensors
Handle user interface
Manage data and files
Sensor
Phone
750
2900
2700
625
1500
12,875 Total N+C LOC
1200
3200

## Slide 17: Development Strategy
Refer to step 4 of LAU3.
The team needs to consider a development strategy.
  how they will build their product
  how they will put their system together
  what steps or cycles or iterations they will go through
The team considers
  gross size of each component or feature
  one or multiple development/release cycles
  content of each cycle
  size and hours for each cycle
  prototypes
The results of this step are recorded on STRAT.
Notes: <number>

## Slide 18: Using the STRAT Form
Use the STRAT form to record strategic decisions.
  allocate parts and/or features to development cycles
  document estimates of size and hours for each feature
The Reference column can be used to document traceability between the feature and the need statement, SRS paragraph, sentence number, or other reference for the feature.
The Feature column contains the list of features (or parts) to be included in the product, as taken from the conceptual design.
The Cycle LOC columns are used to estimate the new and changed LOC for each feature per cycle.
The Cycle Hours columns are used to estimate the hours for each feature per cycle.
Notes: <number>

## Slide 19: Estimating Size and Hours
Size and hours estimates per feature are a basis for judging which features can be implemented in the available time.
Produce the preliminary size estimate.
  Record how many LOC for each feature will be required in each cycle.
  Size estimates are hypothetical, since the team has not yet decided how to build the product.
Produce the preliminary time estimate.
  Use estimated LOC counts and productivity rates to estimate how long each feature is likely to take.
  Use PSP course experience, historical team data, or the TSP planning guidelines.
  On larger projects, and especially new development, consider using 50% of the productivity rates in the PSP data.
Notes: <number>

## Slide 20: Recording the Conceptual Design on STRAT
See the example STRAT form handout.
Notes: <number>

## Slide 21: Products to be Produced
Refer to step 5 of LAU3.
In addition to the principal software components, the team needs to identify other products to be produced.
  requirements documents and specifications
  design documents and specifications
  prototypes
  installation, user, and maintenance manuals
  test programs, scripts, data, and plans
Use a level of detail that is appropriate for the phase or cycle being planned.
The items identified are recorded on SUMS.
Notes: <number>

## Slide 22: System, Assemblies, and Parts
On SUMS, each line represents an assembly or part of the system.
  The system is composed of assemblies and parts.
  An assembly is composed of parts or other assemblies.
  Parts are the lowest possible level of planning detail.
  The top-level assembly is the system.
In general, summary data are available at the assembly and system levels, but not at the part level.
Part
Part
Part
Part
Part
Part
Assembly
Assembly
Part
Assembly
Assembly
Assembly
System

## Slide 23: SUMS for Security System
Notes: <number>

## Slide 24: Development Process
Refer to step 6 of LAU3.
The team needs to agree on the process that they will follow to develop the product.
The team process focuses on the activities that need to be executed by the team to do the job right.
The team will use this process to derive the tasks that will ultimately be used to
  build a task list
  determine the schedule
Notes: <number>
During process definition in meeting 3, the team focuses on doing the job right.
During the planning steps in meetings 4 and beyond, the team tends to focus on the schedule.
  If the team focuses on the schedule without first thinking about the process, they will unconsciously think about whether they can do the job in the time available.
  Consequently, they may bias their schedule to cut corners from the process.
Defining the process first ensures that the team is committed to doing the job the right way.
This produces a better plan and simplifies the estimating job.

## Slide 25: The TSP Scripts
The TSP has scripts that define the prescribed development process.
  The DEV script covers new development.
  The MAINT script covers maintenance and enhancement.
  Each of these two scripts refers to an additional level of detail for requirements, high-level design, implementation, and test.
  There are also support scripts for inspections, the standard meeting process, the weekly team meeting process, and status reporting.
Forms are available to support these scripts.
The tool that the team uses must support the use of these scripts and the forms that are identified.
Notes: <number>

## Slide 26: Two Process Levels
Overall project process
  Start by building on the organization’s standard process, or use the TSP scripts if no other process exists.
  Walk through the phases and activities to ensure that the process covers all of the activities that the job requires.
  Phases must be defined so that a quality plan can be produced.
Detailed process for the next phase or cycle
  Define sufficient detail to support individual task planning.
  Define the steps that ensure quality.
  Define product baselines.
Using INV, document steps to develop or modify the team’s process.
Notes: <number>
If the team has a process defined by their organization, they most likely are process literate.
  They can see the mapping between their process and the TSP.
  They can adapt their process so that the TSP forms, tools, measures, and data can be used.
If the team does not have a process, they should start out by using the TSP scripts “as is.”
We are not forcing the TSP process, simply ensuring that the team defines their process in a detail that they can execute, specifically for the next phase or cycle.
The first step is to agree on this high-level, overall process.

## Slide 27: Using the INV Form
Under Process Elements, list the products that the team plans to produce or modify.
Under Work Units, list the size of the product to be produced.
Under Date Needed, enter when each product will be needed.
Under Estimated Hours, list the hours needed to develop or modify the product.
Under Team Member, list the name of the team members who will either develop or obtain the product.
These items will all need to be incorporated into the team’s plan.
Notes: <number>

## Slide 28: Process Development Work
Refer to step 7 of LAU3.
This part of the meeting identifies the process development work so that it can be put on the team’s plan.
Some examples of process elements include
  modifications to the documented organizational process
  modifications to the TSP scripts
  design, code, size, naming, and message standards
  change control and change management procedures
  standards, guidelines, and checklists
These items need to be added to the plan, using the INV form.
Notes: <number>
The process that the team has defined is important and must be formally documented and controlled.
  defines the right way to get the job done
  provides a reference for identifying tasks for planning
  provides a foundation for later review and enhancement of plans
  documents what the team has committed to do so that the team can enforce process discipline
The process manager walks through a team discussion of the process items that need to be developed. These items need to be added to the team’s list of items on INV.
A brainstorming technique can be used.
It is useful to walk through the process defined previously and determine if the process is documented and understood.
Any parts of the process that are not documented or understood need to be added to the INV form.

## Slide 29: Support Work
Refer to step 8 of LAU3.
Consider the team’s support needs.
  Is the development environment adequate?
  Are there suitable design and implementation tools?
  Are databases or other facilities needed?
These items need to be added to the plan, using the INV form.
Notes: <number>
There may be an opportunity to generate process requirements for the SEPG. For example, the team may ask the SEPG for a CM process with specific requirements for change control.

## Slide 30: CCB Membership
Refer to step 9 of LAU3.
The team needs to identify the membership of the configuration control board (CCB) and the CCB chair.
Teams may not be ready to discuss this subject.
The team needs some control mechanism.
The team needs to identify who will represent them on the CCB.
Notes: <number>
There may be an opportunity to generate process requirements for the SEPG. For example, the team may ask the SEPG for a CM process with specific requirements for change control.

## Slide 31: Role Tasks
Refer to step 10 of LAU3.
The coach leads the team in defining the tasks and weekly reporting for each role, and records the tasks on form INV.
Teams often struggle when trying to enact the roles.
This step in the launch process helps to clarify what the important elements of each role are.
Depending on which phase the project is in, some roles may be emphasized more than others.
Notes: <number>
There may be an opportunity to generate process requirements for the SEPG. For example, the team may ask the SEPG for a CM process with specific requirements for change control.