## Slide 1
TSP Coach Training
The Launch Process - Meeting 4
Notes: <number>
From PSP, what does it take to produce a schedule? list of tasks, sequence, size and time estimate, available resources, etc.

## Slide 2: Lecture Objectives
At the end of this lecture, you will be able to
  assist a TSP team in conducting launch meeting 4 and producing an overall team plan
  coach the individual role managers in conducting meeting 4
  use the forms that support meeting 4
  recognize common occurrences and problems with meeting 4 and apply hints for handling them
Notes: <number>

## Slide 3: Lecture Overview
Overview of meeting 4
Meeting 4 exercise
Coaching considerations
Reference material
Notes: <number>

## Slide 4: The Launch Process Meetings
1. Establish
product and
business
goals
2. Assign roles
and define
team goals
4. Build overall
and
near-term
plans
5. Develop
the quality
plan
6. Build individual
and
consolidated
plans
7. Conduct
risk
assessment
8. Prepare
management
briefing and
launch report
Launch
postmortem
9. Hold
management
review
3. Produce
development
strategy
and process
A TSP team coach guides the team through a defined process to develop its plan and to negotiate that plan with management.
Notes: <number>

## Slide 5: Planning Data from Meeting 3
STRAT
list of functions
cycle LOC
cycle hours
milestone objectives
order of events
INV
list of processes
list of support needs
SUMS
assembly/part ID
size data
product owner
work breakdown structure
Notes: <number>
Meeting 3 Outcomes
The team has defined and agreed to the following.
  conceptual design of what they are going to produce
  strategy for developing the product(s)
  a list of the products that they will produce
  the overall project and the detailed next phase or cycle process
  assignments for completing any process, support, and/or role work
They have all of the work identified for planning purposes.
All members have actively participated in the launch so far and understand what work they are about to plan and subsequently commit to.

## Slide 6: Purpose for Meeting 4
The team needs to develop a plan for doing the work.
  overall project plan
  detailed next-phase or cycle plan
In meeting 4, the team lays out the tasks to be accomplished in building the products and providing the services that were defined in meeting 3.
The team produces the overall plan as a group so that each individual is
  aware of every product, service and task
  more supportive of the result
  more likely to commit to the dates
Notes: <number>

## Slide 7: TSP Plans
Overall team plan
  top-down
  optimal
  all phases or cycles
Individual plans
  bottom-up
  detailed
  next-phase or cycle only
Next-cycle team plan
  consolidated
  balanced
  realistic
  next-phase or cycle only
Individual plan
Individual plan
Individual plan
.
.
.
Next-phase or cycle team plan
Overall team plan
Meeting 4
Meeting 6
Notes: <number>
Show files in folder of overall and individual and consolidate plans.
This meeting will produce individual and team detailed next phase or cycle plan.
  The overall plan should be at a level of detail consistent with the information the team has at that time.
  Next phase or cycle plans need to be at a level where 2 to 4 tasks can be scheduled and completed each week.
  Detailed tasks should be in the 8 to 10 hour range.
  This level of granularity will allow the team to track earned value accurately.
Once the plan is detailed, balanced, and consolidated, the team has the most realistic plan that they can produce, without adjusting for risk.

## Slide 8: Meeting 4 Exercise
Exercise purpose.
  understand how launch meeting 4 is conducted
  be able to develop an overall plan using the TSP tool
  recognize issues that might arise and understand how to deal with them
Directions (see meeting 4 exercise workbook).
  assemble into your launch team groups
  conduct launch meeting 4 using script LAU4
  class discussion of how process worked
After the exercise, we will conclude the module with a discussion of coaching considerations from the lecture slides.
Notes: <number>

## Slide 9: Coaching Considerations for Tasks
Make sure that the estimates make sense and that the productivity rates are appropriate.
Make sure that all on the team are engaged in the discussions and agree with the results.
Consider having new teams start with a conservative estimate on weekly individual task hours and then gradually ramp up to the level they are comfortable with.
Try to keep the TSP tool from being a bottleneck during the meeting.
  work with the planning manager to set things up before the meeting
  find someone that is comfortable working with software applications
  only do it yourself as a last resort
Notes: <number>

## Slide 10: Overall Coaching Considerations
If the team plan doesn’t meet management’s schedule date, have the team see what it would take to meet management’s date.
  additional resources
  reduced functionality
If there is a serious difference between management’s goals and the team’s plan, consider letting management know that now.
Notes: <number>
Producing alternative plans gives the team and management confidence that the team is trying to meet the goals set forth in meeting 1. When devising alternative plans, consider outcomes based on whether
  more or fewer resources were available to work on the project
  the team could get more on-task hours
  the team could reduce the functionality or somehow re-distribute the functionality across cycles
  the team could negotiate schedule dates
Team leader trying to steer towards a date:
  Team leaders may have a Gantt chart they need to fit.
  Individuals all must participate and interact throughout this meeting.
  You may need to talk to the team leader and consider having the team conduct parts of these meetings without the team leader.
The team may produce a Gantt chart schedule using MS Project or other tool if they need additional visibility into
  internal team dependencies and contingencies
  external project dependencies and contingencies

## Slide 11: Messages to Remember
In launch meeting 4, the team creates the overall plan.
  the estimated sizes of the products and services to be produced (how big is the job)
  the tasks needed to do the work (with effort estimates)
    next- phase or cycle tasks, detailed to the work-step level
    later phases or cycles at a high level
  the estimated team hours available each week for the work
  an initial schedule for the project
The team may consider alternative plans if management goals are not met.
Overall plan
Available time
Estimate resources
Define tasks
Estimate size
Notes: <number>

## Slide 12: Reference Material
Overview of meeting 4 process
Estimating size
Determining project tasks
Estimating overall resources
Estimating resource availability
Generating the overall plan
Reviewing and assessing the plan
Notes: <number>

## Slide 13: Meeting 4 Process
Refer to the TSP Launch Meeting 4 Script (LAU4).
The design manager leads the team in estimating size.
The team leader leads the team in identifying the overall and next-phase or cycle project tasks.
The planning manager leads the team in
  estimating the resources required for every task
  estimating the resources available
  generating the overall plan
The team leader leads the team in reviewing and assessing the plan.
This meeting uses the open style of communication.
Notes: <number>

## Slide 14: Meeting 4 Artifacts
The following artifacts are produced in meeting 4.
  documented overall size and resource estimate (SUMP, SUMS, and TASK)
  documented development plan with scheduled commitment dates (TASK, SCHED)
  earned value plan
Notes: <number>

## Slide 15: Estimating Size
Refer to step 3 of LAU4.
Size can help the planning process.
  Resource estimates are derived from size estimates.
  Quality data and goals will be derived from size data.
The size of the software products, as well as all other products, should be estimated.
In meeting 3, initial size estimates for some products were made.
In meeting 4, the initial size estimates are refined (if needed) and entered on the proper forms for planning.
It is often helpful to measure existing products to obtain historical data for use in estimating new products.
Notes: <number>
Everyone on the team must have an opportunity to state their views on size. When there is disagreement, take the time to try to achieve consensus. If there is still disagreement, make multiple estimates and decide on the criteria for which one to use, for example
  Compare to known similar products.
  Consider the risk or impact of choosing one versus the other.
Make a team decision and proceed with planning.
  Document the discrepancy between the estimates.
  In most cases, take the more conservative estimate.
  Document the risk or opportunity that the alternative estimate presents.
When a team launches for the first time, they may not have historical data to use for planning. Team members are encouraged to use to use the PSP course data to help make size estimates. Team members may also look to other teams in their organization for historical data. Use professional judgment when no historical data are available.
  As a minimum, break products down into assemblies and parts.
  Try to look for historical data for at least some of the assemblies or parts.

## Slide 16: Determining Project Tasks
Refer to step 4 of LAU4.
The team defines a comprehensive list of project tasks that
  follows the process defined by the team
  applies the process to building all identified products
  accounts for all process and support work
Project tasks must be defined at
  a high level for the whole project, but with enough detail to do quality planning
  a detailed level for the next phase or cycle
The list of tasks are entered onto the TASK form.
Notes: <number>
Thus far, the team has identified sources of tasks in at least these places.
  SUMS: there should be tasks to produce each product.
  Team process : the products to be produced should each have a task for every phase of the process.
  STRAT: the list of tasks may be iterated for multiple cycles.
  INV: the products on INV need to be entered onto TASK.
  Process and support tasks: these should have been entered onto INV and then put onto TASK.
The tasks should be sequenced on TASK in the order that they need to be accomplished.
The plan must contain sufficient detail for quality planning. Break the implementation phase into TSP sub-phases. This level of detail will be used in meeting 5 when quality goals and plans are developed. Without this detail, it will not be clear if the team is planning for quality or has allowed enough time to do thorough reviews and inspections.

## Slide 17: The TASK Form
The TASK form contains columns for recording plan data and actual data (once the tasks are completed).
Each row represents a task.
  mapped to an assembly
  mapped to a phase
  assigned resources
  size estimate
  units of size measure
Cumulative plan hours, plan value, plan week, and plan date are calculated based on available resources.
  productivity rate
  estimated hours based on size and rate
  number of team members
  total hours to be planned
Notes: <number>
Bring up the TASK form and show how tasks are entered onto the form.
Use GENERATE TASK LIST first.
Add additional tasks from INV, process, etc.
Show the full task list for case study.
Point out level of detail.
Consider the window of planning visibility.
  Teams must commit to a project that often extends beyond three months.
  Individuals can only see out about three months in detail.
  Consequently, the team plan will be done at a high level for the whole project, and in detail only for only the next phase.
The list of tasks will reflect this window of visibility.
  Next phase tasks should be of a duration that can be completed in a matter of days.
  Downstream tasks are estimated at the “ball-park” level.

## Slide 18: Estimating Overall Resources
Refer to step 5 of LAU4.
The intent is to estimate resources
  for all tasks entered on TASK
  using historical data and/or PLAN guidelines
Overall resource estimate
  Use team data or available standards (PLAN guidelines).
  Enter resources required for all tasks throughout the project.
Overall next-phase or cycle effort estimate
  Use personal data and/or team data, when available.
  Enter time required for each task to be completed during the next phase or cycle.
In a launch, the estimation of resources typically is done at the same time that tasks are identified and placed on TASK.
Notes: <number>
Once projects are completed using the TSP, data are available from those projects (productivity rates as “size per time” (LOC/hr) and percentage of total time spent in phase). With that data, the team can look at the size of assemblies and
  develop the total time estimate for each assembly based on the size of the assembly and the productivity rate
  spread the total time estimate across the phases based on historical percentages
Documents can be estimated in a similar way. The team may also be able to use other data from similar past projects to estimate the non-software development tasks.
In absence of historical data, teams may use the TSP planning guidelines provided as part of the TSP process.
The planning guidelines have been developed over time from data from individuals using PSP and teams using TSP.
  reflect a wide range of projects that may not be similar to the one being launched
  need to be reviewed by the team and adjusted based on the teams knowledge of their organization and capability
Teams should be urged to use their own data wherever possible. Even with limited data from their own organization, they can make appropriate adjustments to the planning guidelines.

## Slide 19: Where are We Now?
The team has produced size and time estimates for all of the work to be done.
The team should have followed the launch process, using
  historical data
  plan guidelines
  forms and tools
Notes: <number>
What else do we need to know to produce a schedule?

## Slide 20: Estimating Resource Availability
Refer to step 6 of LAU4.
The only other piece of information needed to produce a team schedule is resource availability.
Based on the size and time estimates made, resource availability will determine how quickly the project can be done (in terms of schedule).
The team needs to discuss the number of
  staff available to work on the project
  hours per week that each individual can commit to the team
Resource availability is planned using the SCHED form.
Notes: <number>
Team members and managers typically expect to work a 40-hour week. In most organizations, the number of hours actually worked on tasks ranges from 10 to 20 hours per week. The remainder of the week is spent doing other things that don’t directly relate to the planned tasks, such as meetings, proposals, e-mail, phone interruptions, role responsibilities.
In absence of historical data, most teams use 20 hours per week per individual.
  This may be all that their management can accept without having gone through the on-task time discussion on prior projects.
  This is aggressive on teams with no prior experience on TSP teams.
If the team is making a firm commitment to an outside customer, they should use a more conservative number, such as 15 to 18 hours per week.
Over time, the team can look at their actual on-task time and make adjustments.

## Slide 21: Use of SCHED
On the SCHED form, the team estimates the total number of hours that they expect to work on tasks for each week.
The cumulative planned hours must exceed the total number of hours estimated on the TASK form.
When planning available hours, the team should account for major things such as vacations, conferences, and other events that will take significant time away from on-task time.
Notes: <number>
Go through example on second projector.

## Slide 22: SCHED-TASK Relationship
The team has now estimated all tasks and resource available.
With TASK and SCHED, a schedule can be produced.
Notes: <number>

## Slide 23: Generating the Overall Plan
Refer to step 7 of LAU4.
The intent is to produce a schedule on the TASK form and then to review and assess this schedule with respect to management and team goals.
In meeting 6, the overall plan will be split into detailed plans.
  The original overall plan is archived for reference.
  Additional detail and changes to plans in the future should use the overall plan as a reference.
Notes: <number>

## Slide 24: Reviewing and Assessing the Plan
Refer to step 8 of LAU4.
The overall plan represents the team’s optimum plan. It assumes that
  there are no task interdependencies
  sufficient resources will be available
  individuals and their skills are interchangeable
However, this plan may be based on a brute force design and the team may find a better way.
Assess the plan against the following criteria.
  Is an acceptable process being used?
  Are appropriate guidelines used in estimating?
  Are goals being met?
If the plan does not meet one or more sets of goals, the team needs to look at alternative plans.
Notes: <number>

## Slide 25: Summary of the Planning Data
STRAT
list of functions
cycle LOC
cycle hours
milestone objectives
order of events
INV
list of processes
list of support needs
SUMS
assembly/part ID
size data
product owner
work breakdown structure
TASK
list of tasks
plan hours
cumulative plan hours
plan value
plan date
SCHED
available hours
cumulative available hours
plan value
Notes: <number>