## Slide 1
TSP Coach Training
The Launch Process - Meeting 5
Notes: <number>
We have a plan. What is missing? QUALITY.
Did we allow enough time to do reviews? What are defects injected and removed and resulting defect density?

## Slide 2: Lecture Objectives
At the end of this lecture, you will be able to
  assist a TSP team in conducting launch meeting 5 and developing a quality plan
  coach the individual role managers in conducting meeting 5
  use the forms and tools that support meeting 5
  recognize common occurrences and problems with meeting 5 and apply hints for handling them
Notes: <number>

## Slide 3: Lecture Overview
Overview of meeting 5
Meeting 5 exercise
Coaching considerations
Reference material
Notes: <number>

## Slide 4: The Launch Process Meetings
1. Establish
product and
business
goals
2. Assign roles
and define
team goals
4. Build overall
and
near-term
plans
5. Develop
the quality
plan
6. Build individual
and
consolidated
plans
7. Conduct
risk
assessment
8. Prepare
management
briefing and
launch report
Launch
postmortem
9. Hold
management
review
3. Produce
development
strategy
and process
A TSP team coach guides the team through a defined process to develop its plan and to negotiate that plan with management.
Notes: <number>

## Slide 5: Meeting 4 Outcomes
The team has developed an overall team plan.
The plan includes times for all tasks, including those tasks that
  inject defects
  remove defects
Notes: <number>
Team members are supportive of results so far and understand all components of the plan, including historical data/guidelines used.

## Slide 6: Purpose for Meeting 5
With a quality strategy, the team can gain the maximum benefits from using the TSP.
  Schedules will be optimum.
  Schedules will be more predictable.
  Product quality will be higher.
Teams can also reduce their time in integration and system testing.
Notes: <number>
The team needs to look at a quality strategy.
  What are acceptable quality goals?
  How do defect injection rates affect the planned effort?
  How do defect removal yields affect the planned effort?
  What defects would remain in the delivered product?
  How could better yields affect overall cost and schedule?
  How could the team set high quality targets and meet them?
  What is the resulting overall plan that the team is committing to?

## Slide 7: Appropriate Actions
The focus in meeting 5 is on building a defect management plan.
On some projects a high level quality goal is not needed, or appreciated, thus the motivation and desire to plan, track and manage defects does not exist within the team.
How would you address this issue?
Are their times when quality really doesn’t matter?
Notes: The key point is the discussion between "what is quality?" and "what is a defect?" in a team's particular domain. Other domains may not think in terms of defects at all, but they may respond to "rework", "double work", "lost time", or even some form of customer feedback that isn't "good job". (We have seen several places where defects officially did not matter - "Is it good enough to ship?" - right up until the company president or general manager got a call from the customer, usually after midnight!) This is where the coach will have an advantage if he/she has done the Team Member Training with the team, or better yet, works in the organization - the discussion should already have been started, and the coach can get the team thinking about quality in their own terms.
Another problem of course is that TSP is built for software development and can be stretched without too much trouble into general systems & engineering development. People who work in those domains generally will understand a discussion on defects. The bigger problem will be how to capture what "poor quality" will cost (assuming that you've been able to agree to a definition of "poor quality"!), and then translate to something you can track, esp. given that TSP is structured around defect management per se. The PIP is a generic way to do this. Another option is the IRTL, or however they track issues. On the one real services team we worked with, everything was tracked by "service tickets" which could include real defects (hardware or software not working/not working correctly), arguable defects (think "operator error"), and non-defects ("we'd like this new feature"). Since they tracked all of their efforts back to tickets (including all new feature development) they knew EXACTLY what poor quality cost them operationally.
<number>

## Slide 8: Coaching for Appropriate Actions
The focus in meeting 5 is on building a defect management plan.
  How many defects are injected in each phase?
  What is the estimated removal of defects in the defect removal phases?
  The coach should coach the team to take appropriate action in relationship to their quality goals. (Note: Setting of quality goals is covered in “Leading Development Teams”)
  The team should only build detailed quality plans for processes where it is important to track defect such that they can manage to high quality results.
Notes:   If a team is building a software system where near zero defects results are of high importance, the team should have high focus on building a detailed quality plan.
  If a team is working in a situation where
<number>

## Slide 9: When Tracking Defects Matters - 1
The team needs data to manage quality, but until they have data it is hard to convince them to collect the defect data.
    Have a discussion on what is a defect and get them to agree on a definition. Write it down.
    Try to get them to agree to collect data during certain phases such as all inspection phases. While this will not give them a complete picture, during the PM they should realize how much more insight they would have if they collected all the data.
    Make sure the data that is collected is used in order to encourage and improve the desired behavior.
      Help the Quality Manager analyze the data and present findings during weekly team meetings.
      Use the data during Checkpoints and Postmortems.

## Slide 10: When Tracking Defects Matters - 2
While quality matters, the team may already be producing a product that is “good enough” thus will not agree to collect defect data as prescribed in PSP/TSP.
  Don’t fight with them, just discuss the topic of quality and move on. Make sure they note this decision in their presentation with management and their rational for not needing to collect defect data at this time
  During the checkpoint and/or cycle/phase/project PM talk about any quality issues they have encountered. How could they have avoided it? How could they have detected it sooner? Etc. Then try to get them to start collecting some data.

## Slide 11: When Tracking Defects Doesn’t Matter - 1
Sometimes the work being produced by a team is “good enough,” thus quality doesn’t seem to matter. While this is almost never the case for software development, it can occur in other types of Knowledge Work.
In these cases, the teams are using TSP for the self-directed aspects of the TSP framework. They want to be able to
plan and track their own work
make and meet their own commitments
own their processes
set and commit to their own goals
In these situations the process improvement proposal (Form PIP) becomes extremely important as it is the only mechanism the team has to capture improvement ideas needed to eliminate rework and optimize the team’s overall performance.

## Slide 12
Once the team has mastered the self-directed aspects of TSP, the coach should try to encourage the team to give defect tracking another try in order to validate the assumption that defect data is of little value and not worth collecting.
  Some teams are just not willing or able to focus on defects until they get planning and tracking under control and consistently apply process discipline.
  If they give it a whole hearted attempt for a complete cycle, they will usually find new ways in which they can improve the team’s performance.
  After the self-directed aspects of TSP have been adopted, very few additional performance improvements will be accomplished without defect data.
When Tracking Defects Doesn’t Matter - 2

## Slide 13: Planning and Tracking Quality
Notes: FOR THE TEAM TO GET THIS INFORMATION, THEY MUST RECORD GOOD DATA…. Which sets up for the next slide
Inspections assumes 2 inspectors + 1 producer
NOTE: To be effective this data must include all people affected by a defect time to Find, Fix etc.
For example in system test, it is the time
--- for tester to see the symptom
-- to reproduce it
-- to record it
--- reproduce it for the developer
--- the developer to find the root cause
--- likely time to be processed in CCB
--- time to fix
--- time to review, inspect, unit test the fix
--- release it
--- test it in system test
--- run regression tests
<number>

## Slide 14: Producing Defect-free Products
Code
Unit test
Compile
Personal review
Integrate
Team inspection
Defects removed
Remaining in the product
200 defects
injected
.5 * 60 = 30
.7 * 30 = 21
.6 * 9 = 5
4
9
30
How many defects would remain if the personal review was not done?
If it achieved 90% yield?
.7 * 200 = 140
60
70%
50%
70%
60%
Yields
Notes: <number>
This is why teams need individuals who are PSP trained.

## Slide 15: Producing Defect-free Products
Code
Unit test
Compile
Personal review
Integrate
Team inspection
Defects removed
Remaining in the product
200 defects
injected
.5 * 200 = 100
.7 * 100 = 70
.6 * 30 = 18
12
30
100
How many defects would remain if the personal review was not done?
If it achieved 90% yield?
70%
50%
70%
60%
Yields
Notes: <number>
This is why teams need individuals who are PSP trained.

## Slide 16: Producing Defect-free Products
Code
Unit test
Compile
Personal review
Integrate
Team inspection
Defects removed
Remaining in the product
200 defects
injected
.5 * 20 = 10
.7 * 10 = 7
.6 * 3 = 2
1
3
10
How many defects would remain if the personal review was not done?
If it achieved 90% yield?
.9 * 200 = 180
20
90%
50%
70%
60%
Yields
Notes: <number>
This is why teams need individuals who are PSP trained.

## Slide 17: Leading Indicators of Quality
So how does the team know how they are doing before they are done?
  First they must track defect or rework data accurately in LOGD
  They can get early indicators of process yields early
    Example: if you find 5 defects in personal review and the inspection finds 20, the personal review had a 20% Yield. As more defects are discovered that yield will get worse – but we know that it is low and can be improved
  Inspectors can use the Capture/recapture Method which provides a statistical means to determine the effectiveness of an inspection with multiple inspectors
Notes: <number>

## Slide 18: Meeting 5 Exercise
Exercise purpose.
  understand how launch meeting 5 is conducted
  be able to make adjustments to the quality plan
  recognize issues that might arise and understand how to deal with them
Directions (see meeting 5 exercise workbook).
  assemble into your launch team groups
  conduct launch meeting 5 using script LAU5
  class discussion of how process worked
After the exercise, we will conclude the module with a discussion of coaching considerations from the lecture slides.
Notes: <number>

## Slide 19: Coaching Considerations
New teams are likely to need help with this meeting, guide the team through the process of building their first quality plan.
The quality guidelines are somewhat aggressive, make sure that the team justifies yields of 60% or greater.
The default quality guidelines sometimes produce strange results, make sure the team cross checks the results by looking at the data, in various ways.
When a team has historical quality data, they should use it in place of the quality guidelines.
Don’t not be surprised during the LAU that the team doesn’t care about quality
work with team leaders ahead of time to identify issues
If it appears during preparation that the team leader and/or team members don't care about the quality aspect BUT management does, the coach should ensure that management has an explicit goal in the meeting 1 presentation
Notes: <number>

## Slide 20: Messages to Remember
In launch meeting 5, the team builds a quality plan that estimates the
  number of defects that will be injected in each phase
  number of defects that will be removed in each phase
  quality (defect density) of the final products & services
  quality (process quality index) of the development process
The team ensures that the plan meets the quality goals.
Teams don’t produce high quality products by accident.
Quality plan
Quality goals
Defects injected
Defects removed
Notes: <number>

## Slide 21: Reference Material
Meeting 5 process
Setting quality goals
Estimating defects injected
Estimating defects removed
Producing the quality plan
Notes: <number>

## Slide 22: Meeting 5 Process
Refer to the TSP Launch Meeting 5 Script (LAU5).
The quality manager leads the team in this meeting.
  The team establishes quality guidelines based on their own historical data, or on the PLAN and QUAL guidelines included in the TSP process.
  The team sets quality goals for acceptable levels of defects in their products and for acceptable yields.
  The team estimates defects injected and defects removed in each phase, based on injection rates and yields.
  The team produces and reviews the resulting quality plan.
This meeting is conducted using the open style of communication.
Notes: <number>

## Slide 23: Meeting 5 Artifacts
The following artifacts are produced or updated (if necessary) in meeting 5.
  a quality plan (SUMP, SUMQ)
  if necessary, a revised development plan with scheduled commitment dates (TASK, SCHED)
  if necessary, an updated earned value plan
Notes: <number>

## Slide 24: Summary of the Planning Data
STRAT
list of functions
cycle LOC
cycle hours
milestone objectives
order of events
INV
list of processes
list of support needs
SUMS
assembly/part ID
size data
product owner
WBS
TASK
list of tasks
plan hours
cumulative plan hours
plan value
plan date
SCHED
available hours
cumulative available hours
plan value
SUMP
size summary
time in phase
defects injected
defects removed
SUMQ
defect injection and removal rates
yield
defect densities
Notes: <number>

## Slide 25: Setting Quality Goals
Refer to step 3 of LAU5.
The quality goal(s) defined in launch meeting 2 is/are refined in this meeting.
Historical data and/or the quality and plan guidelines are used to help set goals and evaluate the quality plan.
The team defines goals for producing near defect-free products & services and for reducing integration and test time.
  Reduce defect densities in system test and delivered products to 10% of the average non-TSP project.
  Reduce test time to 20% of the average non-TSP project.
  Reduce the costs of warranty and maintenance service.
Notes: <number>
With goals established, the team must work backwards and look at their plans for each phase.
  How much time is planned?
  How many defects are planned to be injected and removed?
  What are the resulting defect densities and test times?
  Will the plan meet the team’s quality goals?
The quality plan is that portion of the team’s overall plan that quantifies these terms. (Quality without numbers is just talk.)
  development time ratios
  defect ratios
  review rates
  defect injection and removal rates
  defect densities
  yields
These values are planned and tracked using SUMP and SUMQ.

## Slide 26: Sample – Quality Goals
Parameter | Value | Description
Design/Code Time | 100% | Design time as % of coding time
Code Review Time | 50% | Code review time as % of code time
Compile Defects/KLOC | 10 | Compile defects/KLOC
Unit Test Ddefects/KLOC | 5 | Unit test defects/KLOC
Design Review Time | 50% | Design review time as % of design time

## Slide 27: Estimating Defects Injected
Refer to step 4 of LAU5.
The TSP uses defect injection rates and time in phase to estimate defects injected.
  Review the suggested guideline rates and use them for estimating. (The team should replace these with their own organizational and team data, once available.)
  Enter defect injection rates.
  Use these rates with the planned phase time to generate the number of defects estimated to be injected in each phase.
Notes: <number>
Quality plan guidelines
The data that makes up the quality plan should
  be realistic and achievable
  show improvement from prior projects
Many teams do not have historical data.
The TSP quality guidelines can be used by teams as a starting point.
Teams track their plans and record quality data to be used on future jobs.

## Slide 28: Example – Estimating Defects Injected
Defect Injection Rates (Defects Injected Per Hour) |  |  | Plan
Planning |  |  | 0
Requirements |  |  | 0.25
System Test Plan |  |  | 0
REQ Inspection |  |  | 0
High-Level Design |  |  | 0.25
Integration Test Plan |  |  | 0
HLD Inspection |  |  | 0
Detailed Design |  |  | 0.75
DLD Review |  |  | 0
Test Development |  |  | 0
DLD Inspection |  |  | 0
Code |  |  | 2
Code Review |  |  | 0
Compile |  |  | 0.3
Code Inspection |  |  | 0
Unit Test |  |  | 0.067
Build and Integration Test |  |  | 0
System Test |  |  | 0

## Slide 29: Estimating Defects Removed
Refer to step 5 of LAU5.
The TSP uses phase yield to estimate defects removed in a phase.
  The number of defects removed in a phase is equal to the phase yield times the number of defects entering the phase.
  Enter yield values.
  The team should replace the guideline yield with their own organizational and team data, once available. In the meantime they should use professional judgement.
Notes: <number>
Walking through example.

## Slide 30: Example – Estimating Defects Removed
Phase Yields |  |  | Plan
Planning |  |  | 0%
Requirements |  |  | 0%
System Test Plan |  |  | 0%
REQ Inspection |  |  | 70%
High-Level Design |  |  | 0%
Integration Test Plan |  |  | 0%
HLD Inspection |  |  | 70%
Detailed Design |  |  | 0%
DLD Review |  |  | 70%
Test Development |  |  | 0%
DLD Inspection |  |  | 70%
Code |  |  | 0%
Code Review |  |  | 70%
Compile |  |  | 50%
Code Inspection |  |  | 70%
Unit Test |  |  | 90%
Build and Integration Test |  |  | 80%
System Test |  |  | 80%
Acceptance Test |  |  | 65%

## Slide 31: Producing the Quality Plan
Refer to step 6 of LAU5.
Once defects injected and removed are estimated, the resulting quality plan can be generated automatically by the tool.
The team must check the quality levels presented by the plan.
  Do defect densities make sense?
  Do times in integration and test make sense with respect to defects remaining?
  Do defects remaining meet quality goals?
Make adjustments until all quality criteria are met.
Notes: <number>
Work through example.