## Slide 1
TSP Coach Training
The Launch Process - Meeting 6
Notes: <number>

## Slide 2: Lecture Objectives
At the end of this lecture, you will be able to
  assist a TSP team in conducting launch meeting 6 and developing a balanced team plan
  coach the individual role managers in conducting meeting 6
  use the forms and tools that support meeting 6
  recognize common occurrences and problems with meeting 6 and apply hints for handling them
Notes: <number>

## Slide 3: Lecture Overview
Overview of meeting 6
Meeting 6 exercise
Coaching considerations
Reference material
Notes: <number>

## Slide 4: The Launch Process Meetings
1. Establish
product and
business
goals
2. Assign roles
and define
team goals
4. Build overall
and
near-term
plans
5. Develop
the quality
plan
6. Build individual
and
consolidated
plans
7. Conduct
risk
assessment
8. Prepare
management
briefing and
launch report
Launch
postmortem
9. Hold
management
review
3. Produce
development
strategy
and process
A TSP team coach guides the team through a defined process to develop its plan and to negotiate that plan with management.
Notes: <number>

## Slide 5: Meeting 5 Outcomes
The team has developed an overall team plan that includes the following:
  planned size and time for all tasks
  overall team estimate of resource availability
  quality goals, plans, and criteria
  schedule for the completion of all tasks
Notes: <number>
The team members have taken ownership of the results of the planning process so far and understand the quality strategy that the team has committed to.

## Slide 6: Purpose for Meeting 6
The purpose of meeting 6 is to develop a consolidated team plan for the next project phase or cycle that includes detailed, balanced, individual plans.
The detailed plans will guide the individual’s work.
  defines individual task assignments
  contains the appropriate level of detail
  rolls up to the consolidated team plan
The consolidated team plan will be used to plan and track team progress against goals.
Notes: <number>

## Slide 7: TSP Plans
Overall team plan
  top-down
  optimal
  all phases or cycles
Individual plans
  bottom-up
  detailed
  next-phase or cycle only
Next-cycle team plan
  consolidated
  balanced
  realistic
  next-phase or cycle only
Individual plan
Individual plan
Individual plan
.
.
.
Next-phase or cycle team plan
Overall team plan
Meeting 4
Meeting 6
Notes: <number>
Show files in folder of overall and individual and consolidate plans.
This meeting will produce individual and team detailed next phase plan.
  The overall plan should be at a level of detail consistent with the information the team has at that time.
  Next phase plans need to be at a level where 2 to 4 tasks can be scheduled and completed each week.
  Detailed tasks should be in the 8 to 10 hour range.
  This level of granularity will allow the team to track earned value accurately.
Once the plan is detailed, balanced, and consolidated, the team has the most realistic plan that they can produce, without adjusting for risk.

## Slide 8: Meeting 6 Exercise
Exercise purpose.
  understand how launch meeting 6 is conducted
  recognize issues that might arise and understand how to deal with them
Directions (see meeting 6 exercise workbook).
  assemble into your launch team groups
  conduct launch meeting 6 using script LAU6
  class discussion of how process worked
After the exercise, we will conclude the module with a discussion of coaching considerations from the lecture slides.
Notes: <number>

## Slide 9: Coaching Considerations
Allocating tasks
  Make sure the team is comfortable with the allocations
    team leaders tend to assign work based on similar past work
    team members often want to try new things
  Workload balance can be checked during the allocation step by using the Excel autofilter feature. This can make the final workload balancing easier.
Creating individual plans
  provide written directions
  do one-on-one coaching with each team member
  team members should use their personal processes and historical data in place of team aggregate data
  leave unassigned tasks in plan with zero engineers to facilitate final load balancing
Notes: <number>

## Slide 10: Coaching Considerations (continued)
Consolidating plans
  make sure all the plans have been updated
  do a sanity check on overall hours before and after the detailed plans are made, make sure the differences are justified
    unassigned tasks not zeroed out
    number of engineers not properly set
  after the workload is balanced, have the team members remove the unassigned tasks from their plans
Notes: <number>

## Slide 11: The Baseline Plan
When the detailed plans are completed, balanced, and consolidated, the tasks for the next phase or cycle may extend beyond the time allowed for that phase or cycle in the initial overall plan.
When this occurs, the overall plan phases or cycles beyond the next phase or cycle must be shifted in time so that the detailed task plan can be completed.
If the tasks extend beyond the allotted time, the team needs to consider the following.
  Are all tasks in the detailed plan really part of the next phase or cycle?
  Can the subsequent phases or cycles merely be shifted in time to compensate?
  Might there be additional work in the subsequent phases or cycles that extend the dates even further?
  Once satisfied with the detailed plan, the plan should be baselined.
Notes: <number>
The team may produce a Gantt chart schedule using MS Project or other tool if they need additional visibility into
  internal team dependencies and contingencies
  external project dependencies and contingencies

## Slide 12: Messages to Remember
In launch meeting 6, the team allocates tasks to the team members who build individual work plans for their tasks for the next phase or cycle.
In building their plans, the team members
  refine size and effort estimates using their own data and processes
  break tasks to the granularity of around 10 task hours per task or less
  estimate their own available task hours for each week
  create an earned-value plan
The team reviews individual plans and balances workloads across all team members.
Balanced
plan
Allocate tasks
Individual plans
Balance workload
Notes: <number>
The tasks for the next phase in the overall plan are allocated to the engineers, who produce individual plans for the next phase.
In building their plans, the team members
  break tasks larger than 12 hours into smaller tasks
  refine effort estimates using their own data
  use their own calendar of estimated hours available for the work

## Slide 13: Reference Material
Meeting 6 process
Allocating tasks
Producing individual plans
Balancing the team workload
Producing the next-phase or cycle-development plan
Notes: <number>

## Slide 14: Meeting 6 Script Review
Refer to the TSP Launch Meeting 6 Script (LAU6).
The team leader leads the team through allocating tasks to team members.
Individual team members develop their detailed plans.
The planning manager leads the team through balancing and reviewing the final plan.
This meeting is conducted using the open style of communication.
Notes: <number>
The planning manager coordinates the use of the team plan in the tool, i.e., splitting and consolidating.

## Slide 15: Meeting 6 Artifacts
The following artifacts are produced in meeting 6.
  a detailed next-phase or cycle plan at the team and the individual levels (SUMS, SUMP, SUMQ, TASK, SCHED)
  an updated earned value plan
Notes: <number>

## Slide 16: Allocating Tasks to Team Members
Refer to step 3 of LAU6.
The team allocates tasks for the next phase or cycle to individual team members.
The team may do load balancing during task allocation or after each team member has produced their individual plans.
Notes: <number>
The team considers the tasks and the individual skills available on the team. Experience, skills, opportunities, desires.
Begin with the overall plan for the next phase.
  The team leader allocates tasks to individuals.
  The individuals make detailed plans for their tasks.
  The tasks are then balanced by reallocating the tasks until all team members finish their tasks roughly at the same time.
  This approach can take a long time, especially if the team is large.
The second approach involves an attempt to balance the workload as the tasks are initially assigned.
  The entire team works through the task allocation process one week at a time.
  Each week, the members track their time they have available and take on tasks that they can commit to.
  The team ensures that each engineer is fully occupied each week.
  The priority tasks are handled in a logical order.
  When finished allocating all tasks, the workload is balanced.

## Slide 17: Splitting the Workbook
Individual workbooks must be created so that team members can work on their own detailed plans.
The planning manager must set up an environment where the workbooks can be maintained. Consider these details ahead of time.
  network connections or disk transmittal
  size of the files, number of team members, and space available
  timing and performance of the tool
  how files and data will be transmitted back and forth between the team members and the planning manager
Notes: <number>
Show directory structure on line.
NOTE: this is not a tool course. These are things should be considered regardless of which TSP Tool is used.

## Slide 18: Building Individual Plans
Refer to step 4 of LAU6.
The team members use their individual workbooks to build their detailed plans.
  The team may go back to their desks to work on this task.
  Individuals plan in detail the tasks that they are responsible for during the next phase or cycle.
The team should agree on some specific guidelines for making updates to their individual plans.
  Naming conventions must be kept consistent.
  Everyone must understand the mechanics of updating their workbooks.
Notes: <number>
If you are assigned module A, may break it down into smaller pieces and develop PSP plan for first piece to be implemented.

## Slide 19: Balancing the Workload
Refer to step 5 of LAU6.
Individual plans should now be accurate, comprehensive, and detailed for the next phase or cycle.
The planning manager consolidates the individual workbooks and produces an individual plan.
The planning manager generates the task and schedule plans and distributes them to the team.
The team may work from an overhead projector or use print-outs of the team’s plan when balancing the workload.
Notes: <number>

## Slide 20: Producing the Team Plan
Refer to step 6 of LAU6.
Once the workload is balanced and all tasks line up appropriately, the planning manager can generate the balanced team plan.
Some teams take this opportunity to finalize milestone events/dates based on task completions to be negotiated with management during meeting 9.
Task, schedule, and earned value plans should be produced and distributed for team review.
Notes: <number>

## Slide 21: Sample – Team Plan

## Slide 22: Sample – Resource Loading
Name | Initials | Phone | e-mail | Workbook Filename | Planned Tasks | Planned Task Hours | Planned Schedule Weeks | Planned End Date | Predicted End Date
Tim M | TM |  |  | TM.xls | 92 | 44.73 | 155 | 12/17/2007 | 
Eddie O | EO |  |  | EO.xls | 32 | 54.76 | 155 | 12/17/2007 | 
Ellen S | ES |  |  | ES.xls | 83 | 31.48 | 10 | 12/10/2007 | 
Chuck L | CL |  |  | CL.xls | 17 | 38.752 | 155 | 12/17/2007 | 
Alan N | AN |  |  | AN.xls | 22 | 54.918 | 155 | 12/10/2007 | 
 |  |  |  |  | 246 | 224.64 | 155 | 12/17/2007 | 1/0/1900
 |  |  |  |  | Total |  | Max |  | 

## Slide 23: Sample – Earned Value

## Slide 24: Reviewing the Plan
Assess the scheduled dates with respect to the management and marketing goals.
Assess the schedule and quality plan with respect to the team goals established during meetings 2 and 5.
If the plan is inconsistent with the goals, adjustments may be required.
  Is the plan optimum for the available staff?
  Are there additional staff needed? available?
  How would additional staff affect the plan?
  Are there tasks that can be omitted without sacrificing the quality strategy?
  Are there opportunities to deliver less than full functionality?
Ultimately, the team must agree and commit to the plan and any alternative plans that may be presented to management.
Notes: <number>